## 30-Ocb Month Running Fit Sa (2)
SL No. | Style | Department | Sample types | Fabric Color | Fabric Supplier | Sample qty | Req. Date | Running Status | Sent date | Remarks
1 | 1039214 - light weight jacket with hood | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-16 | Done | 2023-09-26
2 | 1042631 - hybrid vest | Outlet- MCA | Fit Sample |  |  | 9 | 2023-09-17 | Done | 2023-09-26
3 | 1042632 - padded jacket | Outlet- MCA | Fit Sample |  |  | 9 | 2023-09-17 | Sewing Running (Hasmot)
4 | 1042722 - softshell jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-18 | Done | 2023-09-26
5 | 1042721 - light weight jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-18 | Done | 2023-10-04 | Style move to VN
6 | 1032427 - light padded bomber jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-23 | Sewing Running (Hasmot)
7 | 1043514 - hooded lightweight jacket | Outlet- WCA | Fit Sample |  |  | 9 | 2023-10-03 | Sewing Running (Azahar)
8 | 1043548 - hooded lightweight jacket | Outlet- WCA | Fit Sample |  |  | 9 | 2023-10-14 | Pattern Running
9 | 1043550 - casual softshell coat | Outlet- WCA | Fit Sample |  |  | 9
10 | 1043579 - long hooded vest | WCA TT Plus | Fit Sample |  |  | 6 | 2023-10-05 | Sewing Running (Azahar)
11 | 1043577 - hooded lightweight coat | WCA TT Plus | Fit Sample |  |  | 6 | 2023-10-05 | Sewing Running (Azahar)
12 | 1042484 -swim shorts | Boys | Fit Sample |  |  | 9
13 | 1042485 -swim shorts | Mini Boys | Fit Sample |  |  | 9
14 | 1042294 -printed swim shorts | TTDM | [7 empty] | Fabric PSO not approved
15 | 1042306 -printed swim shorts | MCA | [7 empty] | Fabric PSO not approved
17 | 1042101 -short puffer jacket | TTDF | Fit Sample |  |  | 6 | 2023-10-11 | Sewing Running-Azhar
| 1042101 -short puffer jacket | TTDF | Sleeve Mockup |  |  | 5 | 2023-10-11 | Sewing Running-Azhar
18 | 1039271 -hooded lightweight coat | WCA | Mock up |  |  | 15 | 2023-10-08 | Sewing Running-Azhar
20 | 1041346 -hybrid jacket | TTDM | Fit Sample
21 | 1041310 -lightweight vest | MCA | Mock up
22 | 1041311 -lightweight jacket | MCA | Mock up
23 | 1041312 -lighweight jacket aop print | MCA | [7 empty] | Same as 1041311
24 | 1041314 -transeasonal jacket | MCA | Mock up
25 | 1041315 -softshell jacket | MCA | Fit Sample
26 | 1041343 -hybrid vest | TTDM | Fit Sample
27 | 1041779 -softshell wind breaker | TTDM | Fit Sample
28 | 1042201 -plus transeasonal jacket | MCA Plus | Fit Sample |  |  | 6
29 | 1042820 -long puffer vest | Outlet- TTDF | Fit Sample |  |  | 9

## Sep Month Running Sample
Tom Tailor, Running sample status, 23
SL No. | Style | Department | Sample types | Colorway | Fabric code | Shell supplier | Sample qty | Req. Date | Tentative ready date | Submission date | Running Status | Remarks
1 | 1042208 -casual puffer jacket with hood | MCA | Proto | Available | FB- WOV-04964 -'TJ-230138 | Taiji | 3 | 2023-08-17 | 2023-08-21 | 2023-09-04 | Done
2 | 1041315 -softshell jacket | MCA | Proto | Available | FB- WOV- 16452, SFT20230706H | Sunflower | 2 | 2023-08-21 | 2023-08-25 | 2023-09-03 | Done | New development softshell
3 | 1041779 -softshell wind breaker | TTDM | Proto | Available | FB- WOV-16452, SFT20230706J | Sunflower | 2 | 2023-08-21 | 2023-08-25 | 2023-09-03 | Done | New development softshell
4 | 1041348 -trans- seasonal blouson | TTDM | 2nd Proto | Available | FB- WOV- 20362, HB23AB064 | Huibo Tex | 3 | 2023-08-22 | 2023-08-26 | 2023-09-04 | Done
5 | 1040683 - short summer jacket | TTDF | Fit Sample | 34880 - faded leaf green | FB- WOV- 16866 - SD210221 | ShiduTex | 6 | 2023-08-17 | 2023-08-21 | 2023-09-06 | Done | Submitted to Imon via Ebrahim at morning
6 | 1041280 - stand- up collar blouson | TTDM | Fit Sample | 29999 - Black | FB- WOV- 11739, HB19AB076100D | Huibo | 9 | 2023-08-26 | 2023-08-30 | 2023-09-08 | Done | Submitted to Minhaz via Anawer on Friday
7 | 1040930 - oversized bomber jacket | Kids Girls | Fit Sample | 22201 - cream toffee | FB- WOV- 20168 -SFT20230324G | Sunflower | 6 | 2023-08-22 | 2023-08-26 | 2023-09-15 | Done | Submitted to Arif via Anawer on Friday
8 | 1041002 - softshell printed jacket | Mini Girls | Fit Sample | 35033 - dark blue butterfly | FB- CKN- 19263, SFT170828A | Sunflower | 6 | 2023-08-26 | 2023-08-30 | 2023-08-28 | Done
9 | 1041779 -softshell wind breaker | TTDM | Hood Mockup | N/A |  | Huibo Tex | 3 | 2023-08-26 | 2023-08-30 | 2023-08-31 | Sewing done | hopefully send by today before lunch
10 | 1041001 -light weight puffer vest | Mini Girls | Fit Sample | 35247 - fresh summertime pink | FB- WOV- 12428, XLAS-19091604 | Wujiang Xinli | 9 | 2023-08-28 |  | 2023-09-22 | Done
11 | 1041004 -quilted flower jacket | Mini Girls | Fit Sample | 10668 - sky captain blue | FB- WOV- 12428, XLAS-19091604 | Wujiang Xinli | 12 | 2023-08-28 |  | 2023-09-15 | Done | Submitted to Arif via Anawer on Friday
12 | 1040974 -stretch swim shorts | MCA | Fit Sample | 35028 - teal navy summer design | FB- WOV-20086, SFT20220819B | Sunflower | 6 | 2023-08-30 |  |  | Cutting done
13 | 1040975 -color block swim shorts | MCA | Fit Sample | 34921 -caribbean turquoise | FB- WOV- 20086, SFT20220819B | Sunflower | 6 | 2023-08-29 |  | 2023-09-08 | Done | Submitted to Minhaz via Anawer on Friday
14 | 1042265 -swim shorts | MCA | Fit Sample | 34921 -caribbean turquoise | FB- WOV-20057, SFT20220111B | Sunflower | 9 | 2023-08-29 |  | 2023-09-08 | Done | Submitted to Minhaz via Anawer on Friday
15 | 1040891 -swim shorts | TTDM | Fit Sample | 28420 -cadmium bright orange | FB- WOV- 20057, SFT20220111B | Sunflower | 6 | 2023-08-30 |  | 2023-09-13 | Done | Submitted to Minhaz via Ebrahim
16 | 1042280 -allover printed swimshorts | TTDM | Fit Sample | 35679 - navy leaves print | FB- WOV- 20613, SFT20220111B | Sunflower | 9 | 2023-08-29 |  | 2023-09-13 | Done | Submitted to Minhaz via Ebrahim
17 | 1040969 -quilted vest | Mini Boys | Fit Sample | 16945 -light fern green | FB- WOV- 20167, SFT20230330A | Sunflower | 6 | 2023-09-03 |  | 2023-09-18 | Done | Submitted to Arif via Ashraf
18 | 1040973 - swim shorts | MCA | Fit Sample | 12642 -Hazy Coral Rose | FB- WOV- 20057, SFT20220111B | Sunflower | 6 | 2023-09-03 |  | 2023-09-08 | Done | Submitted to Minhaz via Anawer on Friday
19 | 1040976 -quilted vest | Boys | Fit Sample | 29476 - coal grey | FB- WOV- 20167, SFT20230330A | Sunflower | 6 | 2023-09-06 |  | 2023-09-15 | Done | Submitted to Arif via Anawer on Friday
20 | 1039271 - hooded lightweight coat | WCA | 1st Bulk Sample | 16348 -pink velvet, 35768 -dark sage | FB- WOV- 18918 - HRT82384; 41gsm 100%PA |  | 4 | 2023-08-30 |  | 45174 | Done | Already sen
21 | 1039271 - hooded lightweight coat | WCA | Mock up | 16348 -pink velvet, 35768 -dark sage | FB- WOV- 18918 - HRT82384; 41gsm 100%PA |  | 4 | 2023-09-04 | 2023-09-05 | 45175 |  | we have already sent to buyer
22 | 1042208 -casual puffer jacket with hood | MCA | Mock up | Available | FB- WOV-04964 -'TJ-230138 | Taiji | 3 | 2023-09-06 |  | 2023-09-13 | Done | Submitted to Minhaz via Anawer on Wed
23 | 1042923 - softshell jacket | Mini Boys | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
24 | 1042871 - Printed softshell jacket | Mini Girls | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
25 | 1039214 - light weight jacket with hood | TTDM | Fit Sample | 29999 - Black | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-16 |  |  | Done
26 | 1042631 - hybrid vest | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-17 |  |  | Done
27 | 1041347 - stand- up collared jacket | TTDM | 2nd Proto | Available | FB- WOV- 19527- Ribstop SD220807- U2 | ShiduTex | 3 | 2023-09-17 |  |  | Done
28 | 1042632 - padded jacket | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 19307 - 100%PL |  | 9 | 2023-09-17 |  |  | Cutting Done
29 | 1041775 - hooded puffer jacket | TTDM | 2nd Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-18 |  |  | Done
30 | 1042722 - softshell jacket | TTDM | Fit Sample | 10362 - Dark Gable Green | FB- WOV- 16452 - softshell | Sunflower | 9 | 2023-09-18 |  |  | Done
31 | 1042721 - light weight jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16044 - 100%PL, HB20AB261, | Sunflower | 9 | 2023-09-18 |  |  | Sewing Running(Azhar)
32 | 1042204 - casual vest | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-18 |  |  | Done
33 | 1042206 - padded jacket | MCA | Proto | 10668 - sky captain blue | FB- WOV- 20798 - TJ- 230132 | Taiji | 3 | 2023-09-20 |  |  | 1 pcs test sample Done
34 | 1042207 - sporty puffer jacket | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-20 |  |  | Sewing Running(Azhar)
35 | 1042208 - casual puffer jacket with | MCA | 2nd Proto | 29999 - Black | FB- WOV- 20746 - TJ- 230138 100% Nylon,r | Taiji | 3 | 2023-09-20 |  |  | Cutting Done
36 | 1041774 - fleece jacket | TTDM | Proto | 10668 - sky captain blue | FB- CKN- 17957 - Bonded Teddy |  | 3 | 2023-09-21 |  |  | Cutting pending
37 | 1041776 - stand- up puffer jacket | TTDM | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-21 |  |  | Sewing Running(Azhar)
38 | 1041319 - cord overshirt | MCA | Proto | Available | FB- - 19520 - WOVEN - MY32569， |  | 3 | 2023-09-21 |  |  | Sewing Running(SHA)
39 | 1041324 - hybrid puffer jacket | MCA | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F | Sunflower | 3 | 2023-09-21 |  |  | Sewing Running(Hasan)
40 | 1042924 - college jacket | Mini Boys | Proto | 10668 - sky captain blue | FB- WOV- 12428 - 100PL Tafetta | Hiuibo | 3 | 2023-09-21 |  |  | Sewing Running(SHA)
41 | 1032427 - light padded bomber jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16527 - Semi dull taslan, SFT20190825 |  | 9 | 2023-09-23 |  |  | Cutting done
42 | 1043011 - puffer vest | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Sewing Running(SHA)
43 | 1043017 - bomber jacket | Boys | Proto | Available | FB- WOV- 16527 - Semi dull taslan, | Sunflower | 3 | 2023-09-24 |  |  | Cutting Done
44 | 1042922 - puffer vest | Mini Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Cutting Pending
45 | 1042121 - corduroy shirt jacket | TTDM | Proto | Available | FB- WOV- 13526 - 8W corduroy, |  | 3 | 2023-09-25 |  |  | Cutting Pending
46 | 1042661 - padded checked overshirt | MCA | Proto | Available | FB- WOV- 20842 - Woven, 100% Co | paramount | 3 | 2023-09-25 |  |  | Cutting Done
47 | 1043035 - heavy puffer jacket | Boys | Proto | Paving stone | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-25 |  |  | Cutting Pending
48 | 1043380 - cropped padded vest | Girls | Proto | Available | FB- WOV- 12428 - 100PL Tafetta, | Xinli | 3 | 2023-09-25 |  |  | Cutting Pending
49 | 1043383 - cropped padded bomber jacket(OP-1) | girls | Proto | Available | Available | Sunflower | 3 | 2023-09-25 |  |  | Cutting Done
50 | 1043383 - cropped padded bomber jacket(OP-2) | girls | Proto | Available | FB- WOV- 20880 - Dummy - Sunflower | Sunflower | 3 | 2023-09-25 |  |  | Sewing Running(SHA)
51 | 1038522 - Tom Tailor Alexa skinny | WCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Wash Done
52 | Camo Design | MCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Hold
53 | 1042926 - colorblock puffer jacket | Mini Boys | Proto | Available | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-21 |  |  | Cutting Done
54 | 1043036 - arctic parka | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Cutting Pending
55 | 1042928 - parka jacket | Mini Boys | Proto | 30000 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Cutting Pending
56 | 1043398 - puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
57 | 1043399 - long puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
58 | 1042874 - Light weight puffer vest | Mini Girls | Proto | 29999 - Black |  |  | 3 | 2023-09-26 |  |  | Cutting Done
59 | 1043037 - reversible quilted jacket | Boys | Proto | 29999 - Black |  |  | 3 | 2023-09-27 |  |  | Requisition done
60 | 1042876 - Peached puffer jacket | Mini Girls | Proto | Available |  |  | 3 | 2023-09-27 |  |  | Requisition done
61 | 1042916 - long puffer coat | WCA | Proto | Available |  |  | 3 | 2023-09-28 |  |  | Requisition done
62 | 1042875 - Quilted light weight jacket | Mini Girls | Proto | 29999 - Black | FB- WOV- 12428 - 100%PL | Xinli | 3 | 2023-09-28 |  |  | Requisition done
63 | 1043388 - cropped lightweight jacket | Girls | Proto | 30000 - Black | FB- WOV- 12428 - 100%PL | Xinli | 3 | 2023-09-28 |  |  | Requisition done
64 | 1042878 - Modern puffer jacket | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-27 |  |  | Requisition done
65 | 1043396 - cropped puffer jacket w. hood | Girls | Proto | Available | FB- WOV- 20813 - Dummy 85% Recycle Polyester ,15% polyamide |  | 3 | 2023-09-28 |  |  | Requisition done
66 | 1042905 - winterly raincoat | WCA | Proto | Available | FB- CKN- 16887 - TLL- 150(A) |  | 3 | 2023-09-28 |  |  | Requisition done
67 | 1042913 - stand- up collar puffer coat | WCA | Proto | Available | FB- WOV- 19073 - Leadwon “LW- 220917- 1”/ |  | 3 | 2023-09-28 |  |  | Requisition done
68 | 1042906 - arctic parka | WCA | Proto | Available | FB- WOV- 04671 - 100PL; 240gsm |  | 3 | 2023-09-28 |  |  | Requisition done
69 | 1042887 - hooded puffer jacket | TTDF | Proto | Available | FB- WOV- 20758 - 100%PL Ribstop |  | 3 | 2023-09-30 |  |  | Requisition done
70 | 1041348 - hooded technical jacket | TTDM | 3rd Proto | Available | FB- WOV- 19527 - Shidutex strech Ribstop | Shidutex | 3 | 2023-09-30 |  |  | Requisition done
71 | 1042877 - Puffer coat with belt(Op-1) | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-30 |  |  | Requisition done
72 | 1042877 - Puffer coat with belt(Op-2) | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-30 |  |  | Requisition done
73 | 1043514 - hooded lightweight jacket | WCA | Fit Sample | 10668 - sky captain blue |  |  | 9 | 2023-10-03 |  |  | Requisition done
74 | 1043548 - hooded lightweight jacket | WCA | Fit Sample |  |  |  | 9
75 | 1043550 - casual softshell coat | WCA | Fit Sample |  |  |  | 9
76 | 1043579 - long hooded vest | WCA TT Plus | Fit Sample | 10668 - sky captain blue |  |  | 6 | 2023-10-05 |  |  | Requisition done
77 | 1043577 - hooded lightweight coat | WCA TT Plus | Fit Sample | 14482 - deep black |  |  | 6 | 2023-10-05 |  |  | Requisition done
| 1038910 - casual blouson | MCA | Proto |  |  |  | 3 | 2023-10-01 |  |  | Sewing-SHA
| 1038910 - casual blouson | MCA | Proto |  |  |  | 3 | 2023-10-01 |  |  | Sewing-SHA
Formulas:
Tentative ready date = [Req. Date]+4

## NWEE
Tom Tailor, Running sample status, 23
SL No. | Style | Department | Sample types | Colorway | Fabric code | Shell supplier | Sample qty | Req. Date | Tentative ready date | Submission date | Running Status | Remarks
1 | 1042923 - softshell jacket | Mini Boys | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Cutting done
2 | 1042871 - Printed softshell jacket | Mini Girls | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Cutting done
3 | 1039214 - light weight jacket with hood | TTDM | Fit Sample | 29999 - Black | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-16 |  |  | Req done
4 | 1042631 - hybrid vest | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-17 |  |  | Req done
5 | 1041347 - stand- up collared jacket | TTDM | 2nd Proto | Available | FB- WOV- 19527- Ribstop SD220807- U2 | ShiduTex | 3 | 2023-09-17 |  |  | Sewing Running
6 | 1042632 - padded jacket | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 19307 - 100%PL |  | 9 | 2023-09-17 |  |  | Cutting done
7 | 1041775 - hooded puffer jacket | TTDM | 2nd Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-18 |  |  | Cutting done
8 | 1042722 - softshell jacket | TTDM | Fit Sample | 10362 - Dark Gable Green | FB- WOV- 16452 - softshell | Sunflower | 9 | 2023-09-18 |  |  | Cutting done
9 | 1042721 - light weight jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16044 - 100%PL, HB20AB261, | Sunflower | 9 | 2023-09-18 |  |  | Cutting done
10 | 1042204 - casual vest | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-18 |  |  | Cutting done
11 | 1042206 - padded jacket | MCA | Proto | 10668 - sky captain blue | FB- WOV- 20798 - TJ- 230132 | Taiji | 3 | 2023-09-20 |  |  | Cutting Running
12 | 1042207 - sporty puffer jacket | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-20 |  |  | Cutting done
13 | 1042208 - casual puffer jacket with | MCA | 2nd Proto | 29999 - Black | FB- WOV- 20746 - TJ- 230138 100% Nylon,r | Taiji | 3 | 2023-09-20 |  |  | Cutting done
14 | 1041774 - fleece jacket | TTDM | Proto | 10668 - sky captain blue | FB- CKN- 17957 - Bonded Teddy |  | 3 | 2023-09-21 |  |  | Cutting pending
15 | 1041776 - stand- up puffer jacket | TTDM | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-21 |  |  | Cutting pending
16 | 1041319 - cord overshirt | MCA | Proto | Available | FB- - 19520 - WOVEN - MY32569， |  | 3 | 2023-09-21 |  |  | Cutting pending
17 | 1041324 - hybrid puffer jacket | MCA | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F | Sunflower | 3 | 2023-09-21 |  |  | Cutting pending
18 | 1042924 - college jacket | Mini Boys | Proto | 10668 - sky captain blue | FB- WOV- 12428 - 100PL Tafetta | Hiuibo | 3 | 2023-09-21 |  |  | Cutting Running
19 | 1032427 - light padded bomber jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16527 - Semi dull taslan, SFT20190825 |  | 9 | 2023-09-23 |  |  | Requisition done
20 | 1038522 - Tom Tailor Alexa skinny | WCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Running
21 | Camo Design | MCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Running

## Sep Month Running Sample (2)
Tom Tailor, Running sample status, 26-Sep
SL No. | Style | Department | Sample types | Colorway | Fabric code | Shell supplier | Sample qty | Req. Date | Tentative ready date | Submission date | Running Status | Remarks
1 | 1042923 - softshell jacket | Mini Boys | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Sewing Done
2 | 1042871 - Printed softshell jacket | Mini Girls | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Sewing Done
3 | 1039214 - light weight jacket with hood | TTDM | Fit Sample | 29999 - Black | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-16 |  |  | Sewing Running(HASM)
4 | 1042631 - hybrid vest | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-17 |  |  | Sewing running (Hassan)
5 | 1041347 - stand- up collared jacket | TTDM | 2nd Proto | Available | FB- WOV- 19527- Ribstop SD220807- U2 | ShiduTex | 3 | 2023-09-17 |  |  | Sewing Running
6 | 1042632 - padded jacket | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 19307 - 100%PL |  | 9 | 2023-09-17 |  |  | Cutting done
7 | 1041775 - hooded puffer jacket | TTDM | 2nd Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-18 |  |  | Cutting done
8 | 1042722 - softshell jacket | TTDM | Fit Sample | 10362 - Dark Gable Green | FB- WOV- 16452 - softshell | Sunflower | 9 | 2023-09-18 |  |  | Sewing Running(SHA)
9 | 1042721 - light weight jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16044 - 100%PL, HB20AB261, | Sunflower | 9 | 2023-09-18 |  |  | Cutting done
10 | 1042204 - casual vest | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-18 |  |  | Cutting done
11 | 1042205 -herrington jacket | MCA | Proto | Availabe |  |  | 3 | 2023-09-20 |  |  | Pattern
12 | 1042206 - padded jacket | MCA | Proto | 10668 - sky captain blue | FB- WOV- 20798 - TJ- 230132 | Taiji | 3 | 2023-09-20 |  |  | Cutting Running
13 | 1042207 - sporty puffer jacket | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-20 |  |  | Cutting done
14 | 1042208 - casual puffer jacket with | MCA | 2nd Proto | 29999 - Black | FB- WOV- 20746 - TJ- 230138 100% Nylon,r | Taiji | 3 | 2023-09-20 |  |  | Cutting done
15 | 1041774 - fleece jacket | TTDM | Proto | 10668 - sky captain blue | FB- CKN- 17957 - Bonded Teddy |  | 3 | 2023-09-21 |  |  | Cutting pending
16 | 1041776 - stand- up puffer jacket | TTDM | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-21 |  |  | Cutting pending
17 | 1041319 - cord overshirt | MCA | Proto | Available | FB- - 19520 - WOVEN - MY32569， |  | 3 | 2023-09-21 |  |  | Cutting pending
18 | 1041324 - hybrid puffer jacket | MCA | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F | Sunflower | 3 | 2023-09-21 |  |  | Cutting pending
19 | 1042924 - college jacket | Mini Boys | Proto | 10668 - sky captain blue | FB- WOV- 12428 - 100PL Tafetta | Hiuibo | 3 | 2023-09-21 |  |  | Cutting Running
20 | 1032427 - light padded bomber jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16527 - Semi dull taslan, SFT20190825 |  | 9 | 2023-09-23 |  |  | Requisition done
21 | 1043011 - puffer vest | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Requisition done
22 | 1043017 - bomber jacket | Boys | Proto | Available | FB- WOV- 16527 - Semi dull taslan, | Sunflower | 3 | 2023-09-24 |  |  | Requisition done
23 | 1042922 - puffer vest | Mini Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Requisition done
24 | 1042121 - corduroy shirt jacket | TTDM | Proto | Available | FB- WOV- 13526 - 8W corduroy, |  | 3 | 2023-09-25 |  |  | Requisition done
25 | 1042661 - padded checked overshirt | MCA | Proto | Available | FB- WOV- 20842 - Woven, 100% Co | paramount | 3 | 2023-09-25 |  |  | Requisition done
26 | 1043035 - heavy puffer jacket | Boys | Proto | Paving stone | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-25 |  |  | Requisition done
27 | 1043380 - cropped padded vest | Girls | Proto | Available | FB- WOV- 12428 - 100PL Tafetta, | Xinli | 3 | 2023-09-25 |  |  | Requisition done
28 | 1043383 - cropped padded bomber jacket | girls | Proto | Available | FB- WOV- 20880 - Dummy - Sunflower | Sunflower | 3 | 2023-09-25 |  |  | Requisition done
29 | 1038522 - Tom Tailor Alexa skinny | WCA | Proto | 29999 - Black |  |  | 3 | 2023-09-15 |  |  | Sewing Done
30 | Camo Design | MCA | Proto | Avaiable |  |  | 3 | 2023-09-15 |  |  | Sewing Running
31 | 1042926 - colorblock puffer jacket | Mini Boys | Proto | Available |  |  | 3 | 2023-09-25 |  |  | Requisition done
32 | 1042887 -hooded puffer jacke | TTDF | Proto
33 | 1042905 - winterly raincoat | WCA | Proto
34 | 1042906 - artic parka | WCA | Proto
35 | 1042913 - lightweigt winter coat | WCA | Proto
36 | 1042916 - long puffer coat | WCA | Proto
37 | 1041348 -trans- seasonal blouson | TTDM | Proto
38 | 1043036 -arctic parka | Boys | Proto
39 | 1043037 -reversible quilted jacket | Boys | Proto
40 | 1042928 - parka jacket | Mini Boys | Proto
41 | 1043388 -cropped lightweight jacket | Girls | Proto
42 | 1043396 -cropped puffer jacket w. hood | Girls | Proto
43 | 1043398 -puffer jacket | Girls | Proto
44 | 1043399 -long puffer jacket | Girls | Proto
45 | 1042874 -Light weight puffer vest | Mini Girls | Proto
46 | 1042875 -Quilted light weight jacket | Mini Girls | Proto
47 | 1042876 -Peached puffer jacket | Mini Girls | Proto
48 | 1042877 -Puffer coat with belt | Mini Girls | Proto
49 | 1042878 -Modern puffer jacket | Mini Girls | Proto
50 | 1043514 -hooded lightweight jacket | WCA | Fit Sample |  |  |  | 9 | 2023-10-03 |  |  | Requisition done
51 | 1043548 -hooded lightweight jacket | WCA | Fit Sample |  |  |  | 9
52 | 1043550 -casual softshell coat | WCA | Fit Sample |  |  |  | 9
53 | 1043577 -hooded lightweight coat | WCA | Fit Sample |  |  |  | 6 | 2023-10-05 |  |  | Requisition done
54 | 1043579 -long hooded vest | WCA | Fit Sample |  |  |  | 6 | 2023-10-05 |  |  | Requisition done
[7 empty] | 3 | 2023-10-01 |  |  | Sewing-SHA
[7 empty] | 3 | 2023-10-01 |  |  | Sewing-SHA

## Sep Month Running Sample (2 (3)
Tom Tailor, Running sample status, 23
SL No. | Style | Department | Sample types | Colorway | Fabric code | Shell supplier | Sample qty | Req. Date | Tentative ready date | Submission date | Running Status
1 | 1042208 -casual puffer jacket with hood | MCA | Proto | Available | FB- WOV-04964 -'TJ-230138 | Taiji | 3 | 2023-08-17 | 2023-08-21 | 2023-09-04 | Done
2 | 1041315 -softshell jacket | MCA | Proto | Available | FB- WOV- 16452, SFT20230706H | Sunflower | 2 | 2023-08-21 | 2023-08-25 | 2023-09-03 | Done
3 | 1041779 -softshell wind breaker | TTDM | Proto | Available | FB- WOV-16452, SFT20230706J | Sunflower | 2 | 2023-08-21 | 2023-08-25 | 2023-09-03 | Done
4 | 1041348 -trans- seasonal blouson | TTDM | 2nd Proto | Available | FB- WOV- 20362, HB23AB064 | Huibo Tex | 3 | 2023-08-22 | 2023-08-26 | 2023-09-04 | Done
5 | 1040683 - short summer jacket | TTDF | Fit Sample | 34880 - faded leaf green | FB- WOV- 16866 - SD210221 | ShiduTex | 6 | 2023-08-17 | 2023-08-21 | 2023-09-06 | Done
6 | 1041280 - stand- up collar blouson | TTDM | Fit Sample | 29999 - Black | FB- WOV- 11739, HB19AB076100D | Huibo | 9 | 2023-08-26 | 2023-08-30 | 2023-09-08 | Done
7 | 1040930 - oversized bomber jacket | Kids Girls | Fit Sample | 22201 - cream toffee | FB- WOV- 20168 -SFT20230324G | Sunflower | 6 | 2023-08-22 | 2023-08-26 | 2023-09-15 | Done
8 | 1041002 - softshell printed jacket | Mini Girls | Fit Sample | 35033 - dark blue butterfly | FB- CKN- 19263, SFT170828A | Sunflower | 6 | 2023-08-26 | 2023-08-30 | 2023-08-28 | Done
9 | 1041779 -softshell wind breaker | TTDM | Hood Mockup | N/A |  | Huibo Tex | 3 | 2023-08-26 | 2023-08-30 | 2023-08-31 | Sewing done
10 | 1041001 -light weight puffer vest | Mini Girls | Fit Sample | 35247 - fresh summertime pink | FB- WOV- 12428, XLAS-19091604 | Wujiang Xinli | 9 | 2023-08-28 |  | 2023-09-22 | Done
11 | 1041004 -quilted flower jacket | Mini Girls | Fit Sample | 10668 - sky captain blue | FB- WOV- 12428, XLAS-19091604 | Wujiang Xinli | 12 | 2023-08-28 |  | 2023-09-15 | Done
12 | 1040974 -stretch swim shorts | MCA | Fit Sample | 35028 - teal navy summer design | FB- WOV-20086, SFT20220819B | Sunflower | 6 | 2023-08-30 |  |  | Cutting done
13 | 1040975 -color block swim shorts | MCA | Fit Sample | 34921 -caribbean turquoise | FB- WOV- 20086, SFT20220819B | Sunflower | 6 | 2023-08-29 |  | 2023-09-08 | Done
14 | 1042265 -swim shorts | MCA | Fit Sample | 34921 -caribbean turquoise | FB- WOV-20057, SFT20220111B | Sunflower | 9 | 2023-08-29 |  | 2023-09-08 | Done
15 | 1040891 -swim shorts | TTDM | Fit Sample | 28420 -cadmium bright orange | FB- WOV- 20057, SFT20220111B | Sunflower | 6 | 2023-08-30 |  | 2023-09-13 | Done
16 | 1042280 -allover printed swimshorts | TTDM | Fit Sample | 35679 - navy leaves print | FB- WOV- 20613, SFT20220111B | Sunflower | 9 | 2023-08-29 |  | 2023-09-13 | Done
17 | 1040969 -quilted vest | Mini Boys | Fit Sample | 16945 -light fern green | FB- WOV- 20167, SFT20230330A | Sunflower | 6 | 2023-09-03 |  | 2023-09-18 | Done
18 | 1040973 - swim shorts | MCA | Fit Sample | 12642 -Hazy Coral Rose | FB- WOV- 20057, SFT20220111B | Sunflower | 6 | 2023-09-03 |  | 2023-09-08 | Done
19 | 1040976 -quilted vest | Boys | Fit Sample | 29476 - coal grey | FB- WOV- 20167, SFT20230330A | Sunflower | 6 | 2023-09-06 |  | 2023-09-15 | Done
20 | 1039271 - hooded lightweight coat | WCA | 1st Bulk Sample | 16348 -pink velvet, 35768 -dark sage | FB- WOV- 18918 - HRT82384; 41gsm 100%PA |  | 4 | 2023-08-30 |  | 45174 | Done
21 | 1039271 - hooded lightweight coat | WCA | Mock up | 16348 -pink velvet, 35768 -dark sage | FB- WOV- 18918 - HRT82384; 41gsm 100%PA |  | 4 | 2023-09-04 | 2023-09-05 | 45175
22 | 1042208 -casual puffer jacket with hood | MCA | Mock up | Available | FB- WOV-04964 -'TJ-230138 | Taiji | 3 | 2023-09-06 |  | 2023-09-13 | Done
23 | 1042923 - softshell jacket | Mini Boys | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
24 | 1042871 - Printed softshell jacket | Mini Girls | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
25 | 1039214 - light weight jacket with hood | TTDM | Fit Sample | 29999 - Black | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-16 |  |  | Done
26 | 1042631 - hybrid vest | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-17 |  |  | Sewing running (Hassan)
27 | 1041347 - stand- up collared jacket | TTDM | 2nd Proto | Available | FB- WOV- 19527- Ribstop SD220807- U2 | ShiduTex | 3 | 2023-09-17 |  |  | Sewing running (Hassan)
28 | 1042632 - padded jacket | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 19307 - 100%PL |  | 9 | 2023-09-17 |  |  | Sewing pending
29 | 1041775 - hooded puffer jacket | TTDM | 2nd Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-18 |  |  | Sewing running (Azhar)
30 | 1042722 - softshell jacket | TTDM | Fit Sample | 10362 - Dark Gable Green | FB- WOV- 16452 - softshell | Sunflower | 9 | 2023-09-18 |  |  | Sewing Running(SHA)
31 | 1042721 - light weight jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16044 - 100%PL, HB20AB261, | Sunflower | 9 | 2023-09-18 |  |  | Sewing pending
32 | 1042204 - casual vest | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-18 |  |  | Sewing pending
33 | 1042206 - padded jacket | MCA | Proto | 10668 - sky captain blue | FB- WOV- 20798 - TJ- 230132 | Taiji | 3 | 2023-09-20 |  |  | 1 pcs test sample running(SHA)
34 | 1042207 - sporty puffer jacket | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-20 |  |  | Sewing pending
35 | 1042208 - casual puffer jacket with | MCA | 2nd Proto | 29999 - Black | FB- WOV- 20746 - TJ- 230138 100% Nylon,r | Taiji | 3 | 2023-09-20 |  |  | Sewing pending
36 | 1041774 - fleece jacket | TTDM | Proto | 10668 - sky captain blue | FB- CKN- 17957 - Bonded Teddy |  | 3 | 2023-09-21 |  |  | Cutting pending
37 | 1042205 - herrington jacket | MCA | Proto | 29999 - Black |  |  | 3 | 2023-09-21 |  |  | Cutting Pending
38 | 1041776 - stand- up puffer jacket | TTDM | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-21 |  |  | Cutting Done
39 | 1041319 - cord overshirt | MCA | Proto | Available | FB- - 19520 - WOVEN - MY32569， |  | 3 | 2023-09-21 |  |  | Cutting pending
40 | 1041324 - hybrid puffer jacket | MCA | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F | Sunflower | 3 | 2023-09-21 |  |  | Cutting done
41 | 1042924 - college jacket | Mini Boys | Proto | 10668 - sky captain blue | FB- WOV- 12428 - 100PL Tafetta | Hiuibo | 3 | 2023-09-21 |  |  | Sewing Running(SHA)
42 | 1032427 - light padded bomber jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16527 - Semi dull taslan, SFT20190825 |  | 9 | 2023-09-23 |  |  | Cutting Running
43 | 1043011 - puffer vest | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Cutting Done
44 | 1043017 - bomber jacket | Boys | Proto | Available | FB- WOV- 16527 - Semi dull taslan, | Sunflower | 3 | 2023-09-24 |  |  | Cutting Pending
45 | 1042922 - puffer vest | Mini Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Cutting Pending
46 | 1042121 - corduroy shirt jacket | TTDM | Proto | Available | FB- WOV- 13526 - 8W corduroy, |  | 3 | 2023-09-25 |  |  | Requisition done
47 | 1042661 - padded checked overshirt | MCA | Proto | Available | FB- WOV- 20842 - Woven, 100% Co | paramount | 3 | 2023-09-25 |  |  | Requisition done
48 | 1043035 - heavy puffer jacket | Boys | Proto | Paving stone | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-25 |  |  | Requisition done
49 | 1043380 - cropped padded vest | Girls | Proto | Available | FB- WOV- 12428 - 100PL Tafetta, | Xinli | 3 | 2023-09-25 |  |  | Requisition done
| 1043383 - cropped padded bomber jacket(OP-1) | girls | Proto | Available | FB- WOV- 20880 - Dummy - Sunflower | Sunflower | 3 | 2023-09-25 |  |  | Cutting Running
50 | 1043383 - cropped padded bomber jacket(OP-2) | girls | Proto | Available | FB- WOV- 20880 - Dummy - Sunflower | Sunflower | 3 | 2023-09-25 |  |  | Cutting Running
51 | 1038522 - Tom Tailor Alexa skinny | WCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Running
52 | Camo Design | MCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Hold(Hasan)
53 | 1042926 - colorblock puffer jacket | Mini Boys | Proto | Available | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-21 |  |  | Requisition done
54 | 1043036 - arctic parka | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Requisition done
55 | 1042928 - parka jacket | Mini Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Requisition done
56 | 1043398 - puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
57 | 1043399 - long puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
| 1042874 - Light weight puffer vest | Mini Girls | Proto | 29999 - Black |  |  | 3 | 2023-09-26 |  |  | Requisition done
54 | 1043037 - reversible quilted jacket | Boys | Proto | 29999 - Black |  |  | 3 | 2023-09-27 |  |  | Requisition done
55 | 1042876 - Peached puffer jacket | Mini Girls | Proto | Available |  |  | 3 | 2023-09-27 |  |  | Requisition done
56 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
57 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
58 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
59 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
60 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
61 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
62 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
63 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
64 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
65 |  | Mini Girls | Proto | Available | [6 empty] | Requisition done
66 | 1042878 - Modern puffer jacket | Mini Girls | Proto | Available |  |  | 3 | 2023-09-27 |  |  | Requisition done
Formulas:
Tentative ready date = [Req. Date]+4

## 30- Sep Month Running Sample
Tom Tailor, Running sample status, 23
SL No. | Style | Department | Sample types | Colorway | Fabric code | Shell supplier | Sample qty | Req. Date | Tentative ready date | Submission date | Running Status | Remarks
1 | 1042923 - softshell jacket | Mini Boys | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
2 | 1042871 - Printed softshell jacket | Mini Girls | Proto | Available | FB- CKN- 19263- SFT170828A, | Sunflower | 3 | 2023-09-15 |  |  | Done
3 | 1039214 - light weight jacket with hood | TTDM | Fit Sample | 29999 - Black | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-16 |  |  | Done
4 | 1042631 - hybrid vest | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 05190 - SPB- 160923- 07 | Sunflower | 9 | 2023-09-17 |  |  | Done
5 | 1041347 - stand- up collared jacket | TTDM | 2nd Proto | Available | FB- WOV- 19527- Ribstop SD220807- U2 | ShiduTex | 3 | 2023-09-17 |  |  | Done
6 | 1042632 - padded jacket | MCA | Fit Sample | 10668 - sky captain blue | FB- WOV- 19307 - 100%PL |  | 9 | 2023-09-17 |  |  | Cutting Done
7 | 1041775 - hooded puffer jacket | TTDM | 2nd Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-18 |  |  | Done
8 | 1042722 - softshell jacket | TTDM | Fit Sample | 10362 - Dark Gable Green | FB- WOV- 16452 - softshell | Sunflower | 9 | 2023-09-18 |  |  | Done
9 | 1042721 - light weight jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16044 - 100%PL, HB20AB261, | Sunflower | 9 | 2023-09-18 |  |  | Sewing Running(Azhar)
10 | 1042204 - casual vest | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-18 |  |  | Sewing Done
11 | 1042206 - padded jacket | MCA | Proto | 10668 - sky captain blue | FB- WOV- 20798 - TJ- 230132 | Taiji | 3 | 2023-09-20 |  |  | 1 pcs test sample Done
12 | 1042207 - sporty puffer jacket | MCA | 2nd Proto | 29999 - Black | FB- WOV- 15784 - Tafetta Full Dull | Taiji | 3 | 2023-09-20 |  |  | Sewing Running(Azhar)
13 | 1042208 - casual puffer jacket with | MCA | 2nd Proto | 29999 - Black | FB- WOV- 20746 - TJ- 230138 100% Nylon,r | Taiji | 3 | 2023-09-20 |  |  | Cutting Done
14 | 1041774 - fleece jacket | TTDM | Proto | 10668 - sky captain blue | FB- CKN- 17957 - Bonded Teddy |  | 3 | 2023-09-21 |  |  | Cutting pending
15 | 1041776 - stand- up puffer jacket | TTDM | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F High | Sunflower | 3 | 2023-09-21 |  |  | Sewing Running(Azhar)
16 | 1041319 - cord overshirt | MCA | Proto | Available | FB- - 19520 - WOVEN - MY32569， |  | 3 | 2023-09-21 |  |  | Sewing Done
17 | 1041324 - hybrid puffer jacket | MCA | Proto | 29999 - Black | FB- WOV- 19119 - SFT20201024F | Sunflower | 3 | 2023-09-21 |  |  | Sewing Running(Hasan)
18 | 1042924 - college jacket | Mini Boys | Proto | 10668 - sky captain blue | FB- WOV- 12428 - 100PL Tafetta | Hiuibo | 3 | 2023-09-21 |  |  | Sewing Done
19 | 1032427 - light padded bomber jacket | TTDM | Fit Sample | 29999 - Black | FB- WOV- 16527 - Semi dull taslan, SFT20190825 |  | 9 | 2023-09-23 |  |  | Cutting done
20 | 1043011 - puffer vest | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Sewing Running(SHA)
21 | 1043017 - bomber jacket | Boys | Proto | Available | FB- WOV- 16527 - Semi dull taslan, | Sunflower | 3 | 2023-09-24 |  |  | Cutting Done
22 | 1042922 - puffer vest | Mini Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-24 |  |  | Cutting Done
23 | 1042121 - corduroy shirt jacket | TTDM | Proto | Available | FB- WOV- 13526 - 8W corduroy, |  | 3 | 2023-09-25 |  |  | Cutting Pending
24 | 1042661 - padded checked overshirt | MCA | Proto | Available | FB- WOV- 20842 - Woven, 100% Co | paramount | 3 | 2023-09-25 |  |  | Sewing Running(SHA)
25 | 1043035 - heavy puffer jacket | Boys | Proto | Paving stone | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-25 |  |  | Cutting Done
26 | 1043380 - cropped padded vest | Girls | Proto | Available | FB- WOV- 12428 - 100PL Tafetta, | Xinli | 3 | 2023-09-25 |  |  | Cutting Pending
27 | 1043383 - cropped padded bomber jacket(OP-1) | girls | Proto | Available | Available | Sunflower | 3 | 2023-09-25 |  |  | Cutting Done
28 | 1043383 - cropped padded bomber jacket(OP-2) | girls | Proto | Available | FB- WOV- 20880 - Dummy - Sunflower | Sunflower | 3 | 2023-09-25 |  |  | Sewing Running(SHA)
29 | 1038522 - Tom Tailor Alexa skinny | WCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Wash Done
30 | Camo Design | MCA | Proto | 29999 - Black |  |  | 3 |  |  |  | Sewing Hold
31 | 1042926 - colorblock puffer jacket | Mini Boys | Proto | Available | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-21 |  |  | Cutting Done
32 | 1043036 - arctic parka | Boys | Proto | 29999 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Cutting Pending
33 | 1042928 - parka jacket | Mini Boys | Proto | 30000 - Black | FB- WOV- 17532 - Recycle Ribstop | Taiji | 3 | 2023-09-26 |  |  | Cutting Pending
34 | 1043398 - puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
35 | 1043399 - long puffer jacket | girls | Proto | Available |  |  | 3 | 2023-09-26 |  |  | Requisition done
36 | 1042874 - Light weight puffer vest | Mini Girls | Proto | 29999 - Black |  |  | 3 | 2023-09-26 |  |  | Cutting Done
37 | 1043037 - reversible quilted jacket | Boys | Proto | 29999 - Black |  |  | 3 | 2023-09-27 |  |  | Requisition done
38 | 1042876 - Peached puffer jacket | Mini Girls | Proto | Available |  |  | 3 | 2023-09-27 |  |  | Requisition done
39 | 1042916 - long puffer coat | WCA | Proto | Available |  |  | 3 | 2023-09-28 |  |  | Requisition done
40 | 1042875 - Quilted light weight jacket | Mini Girls | Proto | 29999 - Black | FB- WOV- 12428 - 100%PL | Xinli | 3 | 2023-09-28 |  |  | Requisition done
41 | 1043388 - cropped lightweight jacket | Girls | Proto | 30000 - Black | FB- WOV- 12428 - 100%PL | Xinli | 3 | 2023-09-28 |  |  | Requisition done
42 | 1042878 - Modern puffer jacket | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-27 |  |  | Requisition done
43 | 1043396 - cropped puffer jacket w. hood | Girls | Proto | Available | FB- WOV- 20813 - Dummy 85% Recycle Polyester ,15% polyamide |  | 3 | 2023-09-28 |  |  | Requisition done
44 | 1042905 - winterly raincoat | WCA | Proto | Available | FB- CKN- 16887 - TLL- 150(A) |  | 3 | 2023-09-28 |  |  | Requisition done
45 | 1042913 - stand- up collar puffer coat | WCA | Proto | Available | FB- WOV- 19073 - Leadwon “LW- 220917- 1”/ |  | 3 | 2023-09-28 |  |  | Requisition done
46 | 1042906 - arctic parka | WCA | Proto | Available | FB- WOV- 04671 - 100PL; 240gsm |  | 3 | 2023-09-28 |  |  | Requisition done
47 | 1042887 - hooded puffer jacket | TTDF | Proto | Available | FB- WOV- 20758 - 100%PL Ribstop |  | 3 | 2023-09-30 |  |  | Requisition done
48 | 1041348 - hooded technical jacket | TTDM | 3rd Proto | Available | FB- WOV- 19527 - Shidutex strech Ribstop | Shidutex | 3 | 2023-09-30 |  |  | Requisition done
49 | 1042877 - Puffer coat with belt(Op-1) | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-30 |  |  | Requisition done
50 | 1042877 - Puffer coat with belt(Op-2) | Mini Girls | Proto | Available | FB- WOV- 12428 - 100PL | Xinli | 3 | 2023-09-30 |  |  | Requisition done
51 | 1043514 - hooded lightweight jacket | WCA | Fit Sample |  |  |  | 9 | 2023-10-03 |  |  | Requisition done
52 | 1043548 - hooded lightweight jacket | WCA | Fit Sample |  |  |  | 9
53 | 1043550 - casual softshell coat | WCA | Fit Sample |  |  |  | 9
54 | 1043579 - long hooded vest | WCA TT Plus | Fit Sample |  |  |  | 6 | 2023-10-05 |  |  | Requisition done
55 | 1043577 - hooded lightweight coat | WCA TT Plus | Fit Sample |  |  |  | 6 | 2023-10-05 |  |  | Requisition done
56 | 1038910 - casual blouson | MCA | Proto |  |  |  | 3 | 2023-10-01 |  |  | Sewing-SHA
57 | 1038910 - casual blouson | MCA | Proto |  |  |  | 3 | 2023-10-01 |  |  | Sewing-SHA

## 30-Ocb Month Running Fit Sample
SL No. | Style | Department | Sample types | Fabric Color | Fabric Supplier | Sample qty | Req. Date | Running Status | Sent date | Remarks
1 | 1039214 - light weight jacket with hood | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-16 | Done | 2023-09-26
2 | 1042631 - hybrid vest | Outlet- MCA | Fit Sample |  |  | 9 | 2023-09-17 | Done | 2023-09-26
3 | 1042632 - padded jacket | Outlet- MCA | Fit Sample |  |  | 9 | 2023-09-17 | Done | 2023-10-20
4 | 1042722 - softshell jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-18 | Done | 2023-09-26
5 | 1042721 - light weight jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-18 | Done | 2023-10-04 | Style move to VN
6 | 1032427 - light padded bomber jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-09-23 | Done | 2023-10-20
7 | 1043514 - hooded lightweight jacket | Outlet- WCA | Fit Sample |  |  | 9 | 2023-10-03 | Done | 2023-10-20
8 | 1043548 - hooded lightweight jacket | Outlet- WCA | Fit Sample |  |  | 9 | 2023-10-14 | Done | 2023-10-25
9 | 1043550 - casual softshell coat | Outlet- WCA | Fit Sample |  |  | 9 | 2023-10-19 | Done | 2023-10-26
10 | 1043579 - long hooded vest | WCA TT Plus | Fit Sample |  |  | 6 | 2023-10-05 | Done | 2023-10-20
11 | 1043577 - hooded lightweight coat | WCA TT Plus | Fit Sample |  |  | 6 | 2023-10-05 | Done | 2023-10-20
12 | 1042484 -swim shorts | Boys | Fit Sample |  |  | 9 | 2023-10-16 | Done | 2023-10-24
13 | 1042485 -swim shorts | Mini Boys | Fit Sample |  |  | 9 | 2023-10-16 | Done | 2023-10-24
14 | 1042294 -printed swim shorts | TTDM | [7 empty] | Fabric PSO not approved
15 | 1042306 -printed swim shorts | MCA | [7 empty] | Fabric PSO not approved
17 | 1042101 -short puffer jacket | TTDF | Fit Sample |  |  | 6 | 2023-10-11 | Done | 2023-10-29
| 1042101 -short puffer jacket | TTDF | Sleeve Mockup |  |  | 5 | 2023-10-11 | Done | 2023-10-29
18 | 1039271 -hooded lightweight coat | WCA | Mock up |  |  | 15 | 2023-10-08 | DONE
20 | 1041346 -hybrid jacket | TTDM | Fit Sample
21 | 1041310 -lightweight vest | MCA | Mock up
22 | 1041311 -lightweight jacket | MCA | Mock up |  |  | 12 | 2023-10-29 | Cutting Done
23 | 1041312 -lighweight jacket aop print | MCA | [7 empty] | Same as 1041311
24 | 1041314 -transeasonal jacket | MCA | Mock up |  |  | 12 | 2023-10-29 | Done
25 | 1041315 -softshell jacket | MCA | Fit Sample
26 | 1041343 -hybrid vest | TTDM | Fit Sample
27 | 1041779 -softshell wind breaker | TTDM | Fit Sample
28 | 1042201 -plus transeasonal jacket | MCA Plus | Fit Sample |  |  | 6 | 2023-10-28 | Done
29 | 1042820 -long puffer vest | Outlet- TTDF | Fit Sample |  |  | 9
30 | 1042265 |  | Mockup |  |  | 5 | 2023-10-16 | Done | 2023-10-26
31 | 1040972 - college jacket | Kids | Size Set Sample |  |  | 3 | 2023-10-22 | Done | 2023-10-29
32 | 1039271 - hooded lightweight coat | Wca | Production Sample |  |  | 4 | 2023-10-22 | Done
33 | 1043514 - hooded lightweight jacket | Outlet- WCA | Fit Sample |  |  | 3 | 2023-10-24 | Done | 2023-10-30
34 | 1032427 - light padded bomber jacket | Outlet- TTDM | Hood Mockup |  |  | 3 | 2023-10-22 | Done | 2023-10-25
35 | 1042722 - softshell jacket | Outlet- TTDM | Fit Sample |  |  | 9 | 2023-10-28 | Done
29 | 1042820 -long puffer vest | Outlet- TTDF | Test Sample |  |  | 1 | 2023-11-06 | Req done
| 1043514 - hooded lightweight jacket | Outlet- WCA | Mockup |  |  | 5 | 2023-11-12 | Req done
| 1042101 -short puffer jacket | TTDF | Mockup |  |  | 10 | 2023-11-12 | Req done

## Rugh
SL No. | Style | Department | Sample types | Fabric Color | Fabric Supplier | Sample qty | Req. Date | Running Status | Sent date | Remarks
1 | 1042913 - stand- up collar puffer coat | WCA | Button Mockup |  |  | 3 Pcs | 2023-10-10 | Sewing Pending
2 | 1042887 - hooded puffer jacket | TTDF | Front Panel Mockup |  |  | 3 Pcs | 2023-10-14 | Cutting Done
3 | 1041348 - hooded technical jacket | TTDM | Front and Back Panel Mockup (OP-1) |  |  | 2 Pcs | 2023-10-15 | Requisition Done
4 | 1041348 - hooded technical jacket | TTDM | Front and Back Panel Mockup (OP-2) |  |  | 2 Pcs | 2023-10-15 | Requisition Done
5 | 1042204 - casual vest | MCA | Front Panel Mockup |  |  | 3 Pcs | 2023-10-05 | Cutting Pending
5 | Camo Design |  | Proto Sample |  |  | 3 |  | Sewing Hold
6 | 1041779 - softshell wind breaker | TTDM | Development sample for fabric checking purpose |  |  | 2 Pcs | 2023-10-10 | Sewing Running
7 | 1043018 - puffer jacket | Boys | Proto Sample |  |  | 3 Pcs | 2023-10-09 | Sewing Running