## TBL F24 TNA (hidden)
SL | Buyer | Buy Rec.Date | Style/ Buy CO | Item | O/Qty | Sewing Line | Production Start Date | Production End Date | Production | Poly Booking | Poly Inhouse Status | Balance Qty | Running Style | Top Production | SMV | Base FOB | Total FOB | CM | PO FOB | P UC | PPS | Fabric ETA+ Inhouse Details( Rony) | Sewing & Finishing Trims Inhouse Details( Taslim) | E. Size Set H/O Date | Final TNA/BPCD | ERP/Planning Offer CRD (Style 1st CRD) | PPS REQ. 6/26 | Style Details | Trims issue | GB PO | GB Test Status. | Merchand Comments | Bulk Issue | Solution | PO STATUS 2/10 | LT | TNA Remarks | GARMENTS TR NUMBER. | GARMENTS TEST STATUS
1 | Timberland | 2023-12-21 | TB0A22W2 | PARKA | 6530 | LY-10 | 2024-05-07 | 2024-06-05 | 6530 | Inhoused | Inhoused | 0 | OK | 260 | 122 | 65.38 | 426931.4 | 18.13 |  |  | TBA |  |  | GIVEN | 2024-05-10 | 2024-06-25 | PASS | [8 empty] | Improve input Required | Improve input Required
2 | Timberland | 2024-01-25 | TB0A22W2 | PARKA | 2102 | LY10 | 2024-07-16 | 2024-07-18 | 2102 |  |  | 0 | OK |  | 122 | 65.38 | 137428.76 | 18.13 | 65.38 | 0 | TBA |  |  | Assort Need to send today | 2024-06-13 | 2024-07-30 | PASS | [7 empty] | OK | Tight TNA | Tight TNA
3 | Timberland-AE-Collab-SMU | 2024-02-26 | TB0A27SG- Wash | MENS BOTTOMS | 2264 | SF 13 | 2024-07-03 | 2024-07-13 | 2264 |  |  | 0 | ok |  |  | 14.34 | 32465.76 | [6 empty] | Given 6/11 | 2024-06-06 | 2024-07-09 | PASS | [5 empty] | 2024-07-10 |  | 1 Day improved CRD | 135 | 130 Pcs PO Missing against Buy Report informed VF.
4 | Timberland-AE-Collab-SMU | 2024-01-25 | TB0A27VW | Anorak Jacket | 2023 | LY-01 | 2024-07-09 | 2024-07-18 | 2023 |  |  | 0 | OK |  | 50 | 23 | 46529 | 5.47 | 23 | 0 |  |  |  | Given 6/11 | 2024-06-11 | 2024-07-17 | PASS | [7 empty] | 2024-07-17
5 | Timberland-AE-Collab-SMU | 2024-02-26 | TB0A27ZB- DPQSL | MENS JKT | 2169 | RS-08 | 2024-07-15 | 2024-07-18 | 2169 |  |  | 0 | OK |  |  | 34.92 | 75741.48 | [6 empty] | Need to HO Assort 6/26 | 2024-06-25 | 2024-08-01 | PASS |  |  | NO |  |  | 2024-08-04 |  | 3 Day Improved CRD | 160 | 100 Pcs PO Missing against Buy Report informed VF.
6 | Timberland-AE-Collab-SMU | 2024-01-25 | TB0A283T | Vest | 2028 | LS 04 | 2024-07-09 | 2024-07-27 | 2028 |  |  | 0 | OK |  | 61 | 24 | 48672 | 6.68 | 24 | 0 |  |  |  | Given 6/11 | 2024-06-11 | 2024-07-16 | PASS |  |  |  | 94 Pcs Improved CRD 3th July, Costs seaving . VSl Allignment |  |  |  | OK
7 | Timberland | 2023-11-23 | TB0A29PQ | Insulation Jkt | 5906 | LY-10 | 2024-02-08 | 2024-06-06 | 5906 | Inhoused | Inhoused | 0 | OK | 340 | 83 | 35.53 | 209840.18 | 13.83 |  |  | Approved | 3 Plt 85 Bales ( MONOTX) 173 Rolls- (Jibo)-20 PKG,8 Rolls( Huamua)- Inhouseed |  | 2024-01-24 | 2024-02-05 | 2024-03-27 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO)
8 | Timberland | 2024-01-25 | TB0A29PQ | Insulation Jkt | 2617 | LY - 9 | 2024-06-04 | 2024-06-30 | 2617 |  |  | 0 | OK |  | 83 | 34.84 | 91176.28 | 13.83 | 34.84 | 0 |  |  |  | GIVEN | 2024-05-07 | 2024-06-21 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) | OK
9 | Timberland | 2024-02-22 | TB0A29PQ | Insulation Jkt | 5181 |  | 2024-08-04 | 2024-08-10 | 5181 |  |  | 0 | OK |  | 83 | 34.84 | 180506.04 | [6 empty] | GIVEN | 2024-05-25 | 2024-07-02 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) |  | 130
10 | Timberland-AE-Collab-SMU | 2024-02-26 | TB0A29TH- Wash | MENS BOTTOMS | 3780 | Ly01 | 2024-07-18 | 2024-08-03 | 3780 |  |  | 0 | OK |  |  | 13.76 | 52012.8 | [6 empty] | Need to HO Assort 6/26 | 2024-06-25 | 2024-08-01 | PASS |  |  |  |  | 22 Pcs Misisng in Infor PO after 5% + Adjust 2 Color | Decrease 8 units from size 32/34. And redistribute those 8 units to other sizes. Date.4/20 |  |  | 145 | 232 Pcs PO PO Missing against Buy Report informed VF.
11 | Timberland | 2023-11-23 | TB0A2AZ3 | Insulation Vest | 3674 | LY-10 | 2024-02-27 | 2024-03-10 | 3674 | Inhoused |  | 0 | OK | 400 | 63 | 25.52 | 93760.48 | 11.2 |  |  | Approved | 3 Plt 85 Bales ( MONOTX) 173 Rolls- (Jibo)-20 PKG,8 Rolls( Huamua)- Inhouseed |  | 2024-01-24 | 2024-02-05 | 2024-03-27 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) |  |  | ALL qty except EIC GMT SKU Qty
12 | Timberland | 2023-11-23 | TB0A2AZ3 | Insulation Vest | 1627 | LY-10 | 2024-03-10 | 2024-03-17 | 1627 | Inhoused |  | 0 | OK |  | 63 | 25.52 | 41521.04 | 11.2 |  |  | Approved | 11 Roll Eta will be 27th Feb. ( MONOTX) 173 Rolls- (Jibo)-20 PKG,8 Rolls( Huamua)- Inhouseed |  | 2024-01-24 | 2024-03-10 | 2024-05-07 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) |  |  | EIC SKU Qty
13 | Timberland | 2023-12-21 | TB0A2AZ3 | Insulation Vest | 4780 | LY-14 | 2024-07-16 | 2024-08-08 | 4780 |  |  | 0 | OK | 265 | 63 | 25.52 | 121985.6 | 11.2 | 4.48 |  | Approved |  |  | GIVEN | 2024-04-20 | 2024-08-01 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) |  |  | 42 pcs first shipment
14 | Timberland | 2024-01-25 | TB0A2AZ3 | Insulation Vest | 4970 | LY10 | 2024-07-16 | 2024-08-03 | 4970 |  |  | 0 |  |  | 63 | 25.52 | 126834.4 | 11.2 | 25.52 | 0 |  |  |  | GIVEN | 2024-05-08 | 2024-06-22 | PASS | [5 empty] | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) | OK
15 | Timberland | 2024-03-21 | TB0A2AZ3 | Insulation Vest | 400 | Need all Materils by 1st June, to continue Line plan. |  | 2024-07-30 | 400 |  |  | 0 | OK |  | 63 | 45.05 | 18020 | 11.2 | 44.08 |  | Approved | 11 Roll Eta will be 27th Feb. ( MONOTX) 173 Rolls- (Jibo)-20 PKG,8 Rolls( Huamua)- Inhouseed |  | Need to HO Assort today. 6/10 | 2024-06-01 | 2024-10-18 | C/O | 2024-10-18 |  |  |  |  | AD provided Wrong MSRP ( Buyer side Incorrect Data issue)price tag | Make MSRP Sticker to re- pesting on the Price tag( NA.CA PO) |  | 205 | EIC SKU Qty
16 | Timberland-AE-Collab-SMU | 2024-01-25 | TB0A2D1D- Wash | Anorak Jacket | 2047 | SF 03 | 2024-07-07 | 2024-07-15 | 2047 |  |  | 0 | OK |  | 55 | 26.14 | 53508.58 | 6.026 | 26.14 | 0 |  |  |  | Given 6/11 | 2024-06-11 | 2024-07-17 | PASS | [5 empty] | Care Label Re-Purces. |  | 104 Pcs 10 th July rest of 28th July
17 | Timberland | 2024-02-22 | TB0A2H9M-GB | 3 in 1 Jkt | 6335 | LY-14 | 2024-06-14 | 2024-07-14 | 6335 |  |  | 0 | OK |  |  | 52.77 | 334297.95 | [6 empty] | GIVEN | 2024-05-25 | 2024-07-06 | C/O |  |  | Y | China CRD 7/17 |  | QCC TAG RE- ORDER |  |  | 115 | ok
18 | Timberland | 2024-02-22 | TB0A2J5B | 3 in 1 Jkt | 2680 | LY-12 | 2024-08-08 | 2024-08-11 | 2680 |  |  | 0 | OK |  |  | 52.4 | 140432 | [6 empty] | GIVEN | 2024-06-10 | 2024-08-10 | CO | [5 empty] | 2024-07-06 |  |  | 135 | 34 Days + From LT
19 | Timberland | 2024-01-25 | TB0A44BF | JKT-DPQSL Quilting | 5525 | RS-11 | 2024-06-06 | 2024-07-07 | 5525 |  |  | 0 | OK |  | 85 | 31.33 | 173098.25 | 11.63 | 31.33 | 0 |  |  |  | GIVEN | 2024-05-08 | 2024-06-22 | PASS | 2024-07-06 |  | 7/17- CRD 2987 Pcs |  |  | GUACAMOLE: Eyelet Problem, will be inhouse 16th May. |  | 2024-07-06 | Actual Ship Date July 06, 2024 | Actual Ship Date July 06, 2024
20 | Timberland | 2023-12-21 | TB0A44UA-GB- DK Sheper, Casel Earth 2 PCs for GB AD S=Counter | Bomber | 3263 | LY-10 | 2024-06-10 | 2024-06-30 | 3263 |  |  | 0 | OK |  | 57.02 | 22.85 | 74559.55 | 8.47 | [5 empty] | GIVEN | 2024-05-16 | 2024-06-23 | PASS |  |  |  | China PO CRD 6/21 Qty. 370 Pcs |  |  |  |  | Revised CRD June 21 | Revised CRD June 21
21 | Timberland | 2024-01-25 | TB0A5M2X- GB | 3 in 1 Jkt | 2870 | LY-7 | 2024-07-07 | 2024-07-18 | 2870 |  |  | 0 | ok |  | 99.52 | 41.94 | 120367.8 | 15.68 | 41.94 | 0 |  |  |  | GIVEN | 2024-05-23 | 2024-07-03 | PASS | 2024-07-17 |  |  | China CRD 7/17/2024 | Pass | QCC TAG RE- ORDER |  | 2024-07-17 | Actual CRD 17 July | Actual CRD 17 July
22 | Timberland | 2024-02-22 | TB0A5M46 | Shirt | 3221 | RS-10 | 2024-07-08 | 2024-07-18 | 3221 |  |  | 0 | OK |  |  | 22.51 | 72504.71 | [6 empty] | Given 6/11. | 2024-06-10 | 2024-07-17 | PASS | [5 empty] | Pls check and confirm HO or not ? |  |  | 110 | 35 Day + from LT
23 | Timberland | 2024-01-25 | TB0A5M5E | JKT | 3671 | LY-12 | 2024-07-06 | 2024-07-15 | 3671 | Partial inhoused | Partial in housed. | 0 | OK | 260 | 77 | 49.15 | 180429.65 | 11.41 | 49.15 | 0 |  |  |  | Given 6/13 | 2024-05-22 | 2024-07-03 | PASS | 2024-07-10 |  |  |  |  | One item of Sealon MJVX as Shell 2 has been in risk as per Mill feedback "We are informed that pillar raw material has a problem and it would take at least 1.5 month to solve. At this moment it is unclear to figure out the production schedule"Alauddin: Just to correct, we are talking about code MJVX which is not seam tape but overlay film. | VF Romen Working on it togeter by Email Sub: Debonair // VF Timberland // F24 // Bulk PO // January Buy // Sealon | 2024-07-10 | Actual CRD 10 Jul | Actual CRD 10 Jul
24 | Timberland | 2023-12-21 | TB0A5M9T-GB | Bomber | 3660 | SF-04 | 2024-05-29 | 2024-06-14 | 3660 |  | Inhoused | 0 | OK |  | 48.52 | 26.52 | 97063.2 | 7.64 |  |  | 0.12 |  |  | GIVEN | 2024-04-27 | 2024-06-06 | PASS |  |  |  | Pass CFRD 6/23
25 | Timberland | 2024-01-25 | TB0A5MB2-GB | Shirt | 5657 | SF-8 | 2024-05-28 | 2024-06-14 | 5657 | 2024-06-02 | Not Yet | 0 | OK |  | 50 | 21.02 | 118910.14 | 7.47 | 21.02 | 0 | 2024-04-03 |  |  | GIVEN | 2024-05-12 | 2024-06-21 | PASS |  |  |  | China CRD 6/21; 4678 Pcs |  | Cordura HT Wrong should AP H Tag |  | OK
26 | Timberland | 2023-12-21 | TB0A5MCM- GB WAX Finished | JKT | 1615 | RS-14 | 2024-06-06 | 2024-06-14 | 1615 |  |  | 0 | OK |  | 87.72 | 40.53 | 65455.95 | 13.03 | [5 empty] | GIVEN | 2024-05-14 | 2024-06-23 | PASS |  |  |  | Pass, CRD 6/23 |  | Wast brand Drosting length 3'' + from requird. | Working with supplier get MA approval form VF |  | Revised CRD June 21 | Revised CRD June 21
27 | Timberland | 2023-11-23 | TB0A5UVW | Insulated Jacket | 5657 | RS- 11 | 2024-05-12 | 2024-05-29 | 5657 |  | Inhoused | 0 | OK | 400 | 85 | 31.55 | 178478.35 | 11.63 |  |  | req. 3/4 | MI: 44 Bel. Inhouse 19th Feb. |  | GIVEN | 2024-04-03 | 2024-05-21 | PASS
28 | Timberland | 2023-12-21 | TB0A5UVW | Insulated Jacket | 2403 | RS- 11 | 2024-05-30 | 2024-06-06 | 2403 |  |  | 0 | OK |  | 85 | 31.55 | 75814.65 | 11.63 |  |  | Approved |  |  | GIVEN | 2024-05-07 | 2024-06-06 | PASS
29 | Timberland | 2023-12-21 | TB0A5XFF- GB | Pant | 9776 | SF 8 | 2024-04-21 | 2024-05-19 | 9776 |  |  | 0 | OK |  | 26.32 | 13.08 | 127870.08 | 3.91 | [5 empty] | 2024-03-23 | 2024-04-02 | 2024-05-10 | PASS |  |  | YES; CRD 15th MAY | Pass CRD 5/12 |  |  |  |  | 178 Pcs Frist CRD on May 07, 2024 | 178 Pcs Frist CRD on May 07, 2024
30 | Timberland | 2023-11-23 | TB0A5ZRK- WAAP-DPQSL Quilting | 2in One Parka- AP (353 Pcs) +NA+EU PO | 3412 | LY-13 | 2024-03-20 | 2024-04-20 | 3412 | Inhoused |  | 0 | OK | 280 | 100 | 63.73 | 217446.76 | 14.25 |  |  | Approved | Z&Z: 31,56,6 Roll. Inhoused. Mono Kr. 6 Bale. Inhouse. MKR. 82 Bel ETA Mar 05. (Waiting for DPQSL Quiltung. Sample going on) |  | plan to 10th Mar- | 2024-03-20 | 2024-05-02 | PASS |  |  | Yes: TR202403055048 |  |  | Outer CF Zipper Slider Finish tone Wrong, as per BOM Mention V3; Need Replace or VF MA Approval. | YKK People invistigating the issue 3/18 |  | First CRD 82 Pcs on 27 Mar/At least One color need to improve 1 wk, Otherwise take 500 yds shell fabric by air | First CRD 82 Pcs on 27 Mar/At least One color need to improve 1 wk, Otherwise take 500 yds shell fabric by air
31 | Timberland | 2023-11-23 | TB0A6137- WAAP | Puffer Jacket-NO AP PO | 908 | SF-7 | 2024-03-16 | 2024-03-22 | 908 | Inhoused | N/Y | 0 | OK | 90 | 73 | 31.59 | 28683.72 | 11.5 |  |  | Approved | Jibo: 609 Roll: Inhouse 2/20. Inhoused |  | Ok | 2024-03-15 | 2024-03-27 | PASS | [5 empty] | Pls go back to TNA
32 | Timberland | 2023-11-23 | TB0A6137- WAAP | Puffer Jacket-NO AP PO | 4418 | SF-7 | 2024-03-22 | 2024-04-22 | 4418 | Inhoused | N/Y | 0 | OK |  | 73 | 31.59 | 139564.62 | 11.5 |  |  | Approved | Jibo: 609 Roll: Inhouse 2/20. Inhoused |  | Ok | 2024-03-20 | 2024-04-23 | PASS | [5 empty] | Pls go back to TNA |  |  | Must Need to get Fabric before CNY | Must Need to get Fabric before CNY
33 | Timberland | 2023-11-23 | TB0A613U-WAAP | Puffer Parka | 2105 | SF-7 | 2024-04-23 | 2024-05-04 | 2105 |  |  | 0 | OK |  | 94.52 | 37.48 | 78895.4 | 14.9 |  |  | Approved | Jibo: 609 Roll: Inhouse 2/20. Inhoused |  | OK | 2024-03-28 | 2024-05-07 | PASS
34 | Timberland | 2023-12-21 | TB0A613U-WAAP | Puffer Parka- NO AP PO | 1030 | SF7 |  | 2024-05-07 | 1030 |  |  | 0 | OK |  |  | 37.48 | 38604.4 |  |  |  | Approved |  |  | 2024-04-07 | 2024-04-27 | 2024-05-28 | PASS | [8 empty] | A strategy Fabric need to collect by air | A strategy Fabric need to collect by air
35 | Timberland | 2023-11-23 | TB0A6153 -WAAP | Anorak Jacket | 6438 | SF-5 | 2024-03-11 | 2024-04-05 | 6438 | Inhoused |  | 0 | OK | 400 | 63 | 24.84 | 159919.92 | 9.927 |  |  | Approved | Jibo: Ist ship 173 Rolls /2nd ship 35 rolls/(Inhoused) 3rd Ship 609 Rolls> 2/22 |  | 2024-02-15 | 2024-02-26 | 2024-03-27 | PASS | [5 empty] | Accepted |  |  | Due to EID Cut off offer LT 30 days | Due to EID Cut off offer LT 30 days
36 | Timberland | 2023-11-23 | TB0A62CF | JKT | 8015 | LS-08 | 2024-03-19 | 2024-03-23 | 8015 | Inhoused |  | 0 | OK | 480 | 60 | 29.68 | 237885.2 | 9.45 |  |  | Approved | 114 Roll- Xinhua- E. Inhouse Day. 16th Feb.; lining 14th Feb. Balance Lining col. Folkstone Gray -, will be 2/20 |  | 2024-02-07 | 2024-02-22 | 2024-04-17 | PASS | Finished |  |  | 530007723600100 & 530007727300100= 2k request to improve 1 wk fro Red Sea criscess |  |  |  |  | huge Qty shipment after eid | huge Qty shipment after eid
37 | Timberland | 2023-12-21 | TB0A62CF | JKT | 6252 | LS10 | 2024-04-28 | 2024-05-15 | 6252 |  |  | 0 | OK |  | 60 | 29.68 | 185559.36 | 9.45 | [5 empty] | OK | 2024-04-20 | 2024-05-21 | PASS | Ontime.
38 | Timberland | 2024-01-25 | TB0A62CF | JKT | 2681 | LS10 | 2024-05-15 | 2024-05-29 | 2681 |  | Inhoused | 0 | OK |  | 60 | 29.68 | 79572.08 | 9.45 | [5 empty] | GIVEN | 2024-05-18 | 2024-06-25 | PASS | Auto Connect if input plan after 18th May. | [6 empty] | OK
39 | Timberland | 2024-02-22 | TB0A62CF | JKT | 1679 | BR-4 | 2024-07-01 | 2024-07-13 | 1679 |  |  | 0 | ok |  | 60 | 29.95 | 50286.05 | 9.45 | [5 empty] | Need to HO Assort today. 6/10 | 2024-06-01 | 2024-07-09 | PASS | Auto Connect if input Plan after 1 st June. Line close will be 25th Mayu/ need input 22 May. |  |  |  |  | 2024-07-06 |  |  | 135 | Decrease PO yet to Update in INFO
40 | Timberland | 2023-12-21 | TB0A62N7-GB | Pant | 3939 | Need Ad Dark Olive + Black color for GB test. | 2024-05-17 | 2024-06-29 | 2610 |  | Inhoused | 1329 | OK |  | 27.32 | 21.01 | 82758.39 | 3.84 |  |  | Re. 3/18 |  |  | GIVEN | 2024-04-25 | 2024-06-03 | PASS | [8 empty] | Second TNA | Second TNA
41 | Timberland | 2023-12-21 | TB0A62N7-GB- DK Oliv- Need GB Sample for AD Color. | Pant | 284 | SF-8 | 2024-05-11 | 2024-05-15 | 284 |  |  | 0 | OK |  | 27.32 | 21.01 | 5966.84 | 3.84 |  |  | Re. 3/18 | CHIA HER: 03 BALES. Inhouse: 13 Th Mar. |  | GIVEN | 2024-04-20 | 2024-05-02 | PASS |  |  | Yet to for fabric delay. | China PO CRD 6/23 |  |  |  |  | CRD Revised to June 06, 2024 | CRD Revised to June 06, 2024
42 | Timberland | 2024-02-22 | TB0A62VQ | JKT- Collubs | 304 | BR-2 | 2024-07-30 | 2024-08-03 | 304 |  |  | 0 | OK |  |  | 48.46 | 14731.84 | [6 empty] | GIVEN | 2024-07-03 | 2024-07-30 | PASS | [5 empty] | H. Tag Wrong. Finding 4/7. supplier will replace |  |  | 155 | ok
43 | Timberland | 2023-11-23 | TB0A62WB- WAAP | Vest- All NA PO | 674 | RS-3 | 2024-03-16 | 2024-03-23 | 674 | Inhoused |  | 0 | OK | 360 | 53.62 | 20.75 | 13985.5 | 8.45 |  |  | Approved | Jibo: Ist ship 173 Rolls /2nd ship 35 rolls/(Inhoused) 3rd Ship 609 Rolls> 2/22.Inhoused |  | 2024-03-02 | 2024-03-17 | 2024-03-27 | PASS | [5 empty] | Accepted
44 | Timberland | 2023-11-23 | TB0A62WB- WAAP | Vest- All NA PO | 1784 | RS-3 | 2024-03-21 | 2024-03-28 | 1784 | Inhoused |  | 0 | OK |  | 53.62 | 20.75 | 37018 | 8.45 |  |  | Approved | Jibo: Ist ship 173 Rolls /2nd ship 35 rolls/(Inhoused) 3rd Ship 609 Rolls> 2/22.Inhoused |  | 2024-03-02 | 2024-03-20 | 2024-05-06 | PASS | [5 empty] | Pls go back to TNA |  |  | Shell M4NM, Need to get 1 sku before CNY | Shell M4NM, Need to get 1 sku before CNY
45 | Timberland | 2023-12-21 | TB0A62YU | Short Pant | 2000 | RS-3 | 2024-05-26 | 2024-06-05 | 2000 |  |  | 0 | OK |  | 27 | 17.21 | 34420 | 4.25 |  |  | Re. 3/18 |  |  | GIVEN | 2024-04-25 | 2024-06-04 | PASS | [8 empty] | PO Stil not created | PO Stil not created
46 | Timberland Pro | 2023-12-21 | TB0A6363 | JKT | 2000 | RS-14 | 2024-06-25 | 2024-07-14 | 2000 |  |  | 0 | OK | 250 | 120 | 47.43 | 94860 | 7.8 | [5 empty] | Given | 2024-06-11 | 2024-07-11 | PASS |  |  |  |  | Will Try to Manage. | PPE test brand hold everything on certification samples. & Materials might be change to re- purchase – TNA & CRD will be Uncertain.( RE- send SMS Sample 3/2) waiting for further Test Report)
47 | Timberland Pro | 2023-12-21 | TB0A637B | Bib | 2000 | LY-7 | 2024-06-15 | 2024-07-03 | 2000 |  |  | 0 | OK |  | 78 | 37.81 | 75620 | 11.27 | [5 empty] | Given | 2024-06-11 | 2024-07-11 | PASS |  |  |  |  | TNA will be change for snap / Eyelet- Wing hing supplier | PPE test brand hold everything on certification samples. & Materials might be change to re- purchase – TNA & CRD will be Uncertain.( Re- send SMS Sample 3/2) waiting for further Test Report)
48 | Timberland | 2023-12-21 | TB0A645W | Pant | 2016 |  | 2024-05-07 | 2024-05-15 | 2016 |  |  | 0 | OK |  | 37 | 26.06 | 52536.96 | 6.01 |  |  | Req. Given. 3/6 |  |  | GIVEN | 2024-04-25 | 2024-06-04 | PASS | [5 empty] | Placket Zipper mms Update 7th Jan, Zipeer Bookied OLD MMS 0.5'' Short from Update MMS. PPS Req. Hold
49 | Timberland | 2024-02-22 | TB0A645W | Pant | 2434 |  | 2024-07-04 | 2024-07-18 | 2434 |  |  | 0 | OK |  | 37 | 26.06 | 63430.04 |  |  |  | Req. Given. 3/6 |  |  | Need to HO Assort today. 6/14 | 2024-06-25 | 2024-07-23 | C/O | [8 empty] | 147 | ok
50 | Timberland | 2023-12-21 | TB0A655U | Vest | 1920 | SF 3 | 2024-04-28 | 2024-05-12 | 1920 |  |  | 0 | OK |  | 59.4 | 24.01 | 46099.2 | 9.36 |  |  | Req. Given. 3/6 |  |  | 2024-03-27 | 2024-04-06 | 2024-05-14 | PASS
51 | Timberland | 2024-01-25 | TB0A655U | Vest | 1123 |  | SP | 2024-05-29 | 1123 |  |  | 0 | OK |  | 59.4 | 24.02 | 26974.46 | 9.36 | 24.02 | 0 |  |  |  | GIVEN | 2024-05-10 | 2024-06-21 | PASS |  |  |  | 185 Pc Requesting to get CRD Before Eid cut off. 6/6 |  |  |  | 520044697400100 PO Pending. 185 Pcs: As per LT File CRD 6/18 | Tight TNA/! Wk fabric improvement required to connect line | Tight TNA/! Wk fabric improvement required to connect line
52 | Timberland | 2023-11-23 | TB0A656F | Pant | 5485 | SF-11 | 2024-02-23 | 2024-03-11 | 5485 | Inhoused |  | 0 | OK | 900 | 32.12 | 15.645 | 85812.825 | 5.06 |  |  | Approved | Vardhaman: Inhouse 2nd Feb.Shell: 116 Roll, |  | 2024-02-15 | 2024-03-05 | 2024-04-24 | PASS | [5 empty] | Input Plan 2/25: Accepted.
53 | Timberland | 2024-02-22 | TB0A65QY | Pant- Colubs | 319 | BR-2 |  |  | 319 |  |  | 0 | OK |  |  | 22 | 7018 | [6 empty] | NOT YET | 2024-07-03 | 2024-07-23 | PASS |  | H. TAG Wrong. 7/4 findings. |  |  |  | 2024-07-26 |  | 3 Day Improved CRD | 155 | ok
54 | Timberland | 2024-01-25 | TB0A668U | JKT | 1595 | LS-4 | 2024-07-30 | 2024-08-11 | 1595 |  |  | 0 | OK |  | 73 | 42.37 | 67580.15 | 10.77 | 42.37 | 4.308 |  |  |  | GIVEN | 2024-05-20 | 2024-07-17 | PASS |  |  |  | NOT Yet Send |  | TB0A668U243-868 Pcs. Brand asking to change the Color to Black 001, creat NEW PO |  | 2024-07-17 | Actual CRD July 17 | Actual CRD July 17
55 | Timberland | 2024-01-25 | TB0A68ZB | Parka | 1358 | RS-1 | 2024-07-03 | 2024-07-14 | 1358 |  |  | 0 | ok |  | 100 | 50.35 | 68375.3 | 14.85 | 50.35 | 0 | 2024-04-03 |  |  | GIVEN | 2024-06-02 | 2024-07-10 | PASS | 2024-07-10 |  | YES; CRD 17th July |  |  |  |  | 2024-07-17 | Actual CRD July 10, 2024 | Actual CRD July 10, 2024
56 | Timberland | 2023-12-21 | TB0A6927- Real Down | 3 in 1 Bomber | 7172 | LS-13 | 2024-06-29 | 2024-07-18 | 7172 |  |  | 0 | OK | 500 | 61.91 | 65.7 | 471200.4 | 9.75 | [5 empty] | GIVEN 6/9 | 2024-06-07 | 2024-07-17 | PASS |  |  |  |  | If materials come early then, pl skeep eye on materils inhouse Staus. | TP down hangtag has been updated by add M7YZ | Need strongly Follow up to Update BOM
57 | Timberland | 2023-11-23 | TB0A6DE7 | Bib | 2121 | SF-4 | 2024-03-16 | 2024-03-28 | 2121 | Inhoused | N/Y | 0 | OK | 220 | 80 | 38.26 | 81149.46 | 11.4 |  |  | Approved | Jibo. 609 Roll: Inhouse 2/20 |  | 2024-02-24 | 2024-03-05 | 2024-04-16 | PASS | [9 empty] | PPM Hold due to PPS Comments Pending!
58 | Timberland | 2024-01-25 | TB0A6GTF | Pant | 2378 | BR-2 | 2024-05-28 | 2024-05-06 | 2378 |  | Inhoused | 0 | OK |  | 24 | 13.25 | 31508.5 | 3.28 | 13.25 | 0 |  |  |  | GIVEN | 2024-05-05 | 2024-06-04 | PASS |  |  |  | 2179 Pcs Will Requesting to get CRD 6/6 |  |  |  | As per LT File CRD 6/13 | 77 Pcs QTY Added | CRD Revised to June 06, 2024, tna ALSO WILL BE IMPROVE
95 | Timberland- JD Program | 2024-04-05 | TB0A6GVB | Insulated Jacket | 250 |  |  | 2024-08-10 | 250 |  |  | 0 | OK |  |  | 53.89 | 13472.5 | 17.5 | [5 empty] | GIVEN | 2024-07-28 | 2024-09-05 | PASS | [8 empty] | 170 | Considered Shain han fabric Air Frieight
60 | Timberland | 2023-12-21 | TB0A6NYD | 3 in One Parka | 2814 | LY-14 | 2024-04-29 | 2024-05-19 | 2814 |  | Inhoused | 0 | OK |  | 40 | 14.94 | 42041.16 | 5.56 |  |  |  | Jonstit. 109 Roll IH. 7th Mar |  | GIVEN | 2024-04-20 | 2024-05-22 | PASS
61 | Timberland | 2024-01-25 | TB0A6P19- DPQSL | 3 in 1 Jkt | 6135 | LY-3 | 2024-05-22 | 2024-06-14 | 6135 |  | Inhoused | 0 | OK | 360 | 140 | 54.66 | 335339.1 | 19.81 | 54.66 | 0 |  |  |  | GIVEN | 2024-05-16 | 2024-06-21 | C/O | New Color added in BK0 CHOCOLATE CHIP. Carry Over Color in 433 DARK SAPPHIRE 308 Roll Shell: ETA 9 May. Not Yet Inhouse. | All Inhoused. Leather Patch change to Embro |  |  |  | CP asking for TNA Improved or CRD Extention |  | OK
62 | Timberland | 2024-01-25 | TB0A6RXD | Parka | 5370 | Ly-1 | 2024-05-20 | 2024-06-14 | 5370 |  | Inhoused | 0 | OK | 280 | 148 | 49.21 | 264257.7 | 21.34 | 49.21 | 0 |  |  |  | 1. BLACK. C/O Color.1st Input Plan. 2. DARK OLIVE- New Color. 3. FOLKSTONE GRAY- New Color. Shell Fabirc 308 Roll Fabric Inhoused Today. NB: Inhouse Quilting. | 2024-05-16 | 2024-06-21 | Carry Over | [5 empty] | CP asking for TNA Improved or CRD Extention |  | OK
63 | Timberland | 2023-12-21 | TB0A6USP | parka | 3903 | RS-14 | 2024-05-23 | 2024-06-30 | 3903 |  |  | 0 | OK | 220 | 100 | 51.08 | 199365.24 | 14.85 |  |  | 2024-03-24 |  |  | GIVEN | 2024-05-14 | 2024-06-25 | PASS | [8 empty] | Connected | Connected
64 | Timberland | 2024-01-25 | TB0A6USP | parka | 2241 | RS-1 | 2024-07-01 | 2024-07-09 | 2241 |  |  | 0 | OK |  | 100 | 51.08 | 114470.28 | 14.85 | 51.08 | 0 |  |  |  | Need to HO Assort today. 6/10 | 2024-06-21 | 2024-07-30 | PASS | [7 empty] | OK | Connected | Connected
65 | Timberland | 2023-11-23 | TB0A6UX2 | Shirt | 3315 | RS-3 | 2024-04-03 | 2024-04-29 | 3315 | Booked | Inhoused | 0 | OK |  | 46.62 | 26.86 | 89040.9 | 7.35 |  |  | Approved | Shang hai TH. 176 Roll: Inhoused, Arthanari: 113 Roll. Inhouse |  | 2024-02-23 | 2024-03-05 | 2024-04-17 | PASS
66 | Timberland | 2023-12-21 | TB0A6UX2 | Shirt | 5069 | RS-3 |  | 2024-05-07 | 5069 |  |  | 0 | OK |  | 46.62 | 26.86 | 136153.34 | 7.35 | [5 empty] | OK | 2024-04-20 | 2024-05-14 | PASS |  |  |  |  | If materials come early then, pl skeep eye on materils inhouse Staus. | Fabric defect with slabs & hand feel issue 540 Yds. Item: M4IX Dark Wheat Boot Working with mill for replacement |  |  | 528 Pcs 14 May, Balace QTY 28th May | 528 Pcs 14 May, Balace QTY 28th May
67 | Timberland | 2024-01-25 | TB0A6UX2 | Shirt | 4063 | RS-3 |  | 2024-05-19 | 4063 |  |  | 0 | OK |  | 46.62 | 26.87 | 109172.81 | 7.35 | 26.87 | 0 |  |  |  | GIVEN | 2024-05-16 | 2024-06-21 | PASS |  |  |  | 461 pcs Requesting to get CRD 6/4/2024 |  |  |  | As per LT File CRD 6/18 | Connected, 2 PC 4TH JUNE | Connected
68 | Timberland | 2023-11-23 | TB0A6UYX | JKT | 2254 | Sf-03 | 2024-03-27 | 2024-04-04 | 2254 | NY |  | 0 | OK | 335 | 50.32 | 21.57 | 48618.78 | 7.48 |  |  | Approved | Jonstit: 109 Roll; Vardoman: 116 Roll. IH. 7th Mar. |  | 2024-02-27 | 2024-03-10 | 2024-04-30 | PASS
69 | Timberland | 2023-12-21 | TB0A6UYX | JKT | 3079 | SF-03 | 2024-05-22 | 2024-06-06 | 3079 |  | Inhoused | 0 | OK | 700 | 50.32 | 21.57 | 66414.03 | 7.48 | [5 empty] | GIVEN | 2024-04-20 | 2024-05-29 | PASS |  |  |  |  | If materials come early then, pl skeep eye on materils inhouse Staus.
70 | Timberland | 2023-12-21 | TB0A6VT6 | Shirt | 7452 | RS-14 | 2024-05-04 | 2024-05-29 | 7452 |  |  | 0 | OK | 600 | 48.82 | 25.22 | 187939.44 | 7.25 |  |  | Waiting for Approved Dye lot |  |  | GIVEN | 2024-04-20 | 2024-05-14 | PASS | [8 empty] | 14th May 678 Pcs/23 May 4502 Pcs/28th May 2272 Pcs) | 14th May 678 Pcs/23 May 4502 Pcs/28th May 2272 Pcs)
71 | Timberland | 2024-01-25 | TB0A6VT6 | Shirt | 2984 | RS-14 | 2024-05-30 | 2024-06-06 | 2984 |  |  | 0 | OK |  | 48.82 | 24.16 | 72093.44 | 7.25 | 24.16 | 0 | Waiting for Approved Dye lot |  |  | GIVEN | 2024-05-15 | 2024-06-21 | PASS |  |  |  | 2984 Pcs Requesting to get CRD 4/6/2024; 3rd April Fabric Ex- mill; Arthanari- India. |  |  |  | As per LT File CRD 6/18
72 | Timberland | 2023-12-21 | TB0A6WRT | JKT | 9537 | SF11 | 2024-05-04 | 2024-05-29 | 9537 |  |  | 0 | OK |  | 69.55 | 32.21 | 307186.77 | 10.04 |  |  | Requsition has given. 3/7 |  |  | 2024-03-27 | 2024-04-06 | 2024-05-14 | PASS | [5 empty] | DK Shapahir Color Sewing Thread problem- need to input aty last |  |  | 204 QTY Increase
73 | Timberland | 2024-03-05 | TB0A6WRT | JKT | 1210 | SF11 | 2024-06-02 | 2024-06-04 | 1210 |  |  | 0 | OK |  | 69.55 | 32.21 | 38974.1 | 10.04 |  |  | Requsition has given. 3/7 |  |  | GIVEN | 2024-06-10 | 2024-07-18 | PASS | [5 empty] | 2024-07-13 |  |  | 130 | ok
74 | Timberland | 2024-04-03 | TB0A6WRT | JKT | 523 | SF11 | 2024-06-05 | 2024-06-08 | 523 |  |  | 0 | OK |  | 69.55 | 32.21 | 16845.83 | 10.04 |  |  | Requsition has given. 3/7 |  |  | GIVEN | 2024-07-08 | 2024-08-22 | PASS | [5 empty] | 2024-08-11 |  |  | 130 | ok
75 | Timberland | 2024-01-25 | TB0A6WZX | Pant | 800 | ETA Delay- 21 May.- Inhoused. 142 Roll Jonstit Issue. Will be inhouse 21th May. | 2024-06-02 | 2024-06-13 | 800 |  |  | 0 | OK |  | 46 | 28.1 | 22480 | 6.82 | 27.5 | -0.6 |  |  |  | GIVEN | 2024-05-15 | 2024-06-21 | PASS |  |  |  | 441 Pes Request to getcRD 6/5 /2024 |  |  |  | 520044750200100 PO Pending. 69 PC; As per LT File CRD 6/18
76 | Timberland | 2024-02-22 | TB0A6X1J | Pant | 2291 | LY-1 | 2024-07-10 | 2024-07-18 | 2291 |  |  | 0 | OK | 350 |  | 17.37 | 39794.67 | [6 empty] | Given | 2024-06-10 | 2024-07-17 | PASS | [5 empty] | 2024-06-16 |  |  | 115 | ok
77 | Timberland | 2023-11-23 | TB0A6X5A | Reversible Vest | 2310 | SF-10 | 2024-03-19 | 2024-03-31 | 2310 | Inhoused |  | 0 | OK | 350 | 72.57 | 30.02 | 69346.2 | 10.48 |  |  | Approved | 109 Roll, 31 Roll: ETA 29 FEB |  | 2024-03-02 | 2024-03-15 | 2024-04-30 | PASS | [5 empty] | 395 Pcs CRD 27 Mar 2024;' 1st shipment is tight to meet the CRD!! |  |  | 395 Pcs CRD 27 Mar 2024 | 395 Pcs CRD 27 Mar 2024
78 | Timberland | 2024-01-25 | TB0A6X5A | Reversible Vest | 778 | BR-4 | 2024-06-14 | 2024-08-02 | 778 |  |  | 0 | OK |  | 72.57 | 30.02 | 23355.56 | 10.48 | 29.59 | -0.43 |  |  |  | GIVEN | 2024-05-20 | 2024-07-04 | PASS | [7 empty] | 420037963200100 PO Pending. 449 Pcs | Disconnected | Disconnected
79 | Timberland | 2024-03-21 | TB0A6X6J-A. Real Down | Jkt | 1761 | Sf14 | 2024-08-20 | 2024-08-25 | 1761 |  |  | 0 | OK |  | 26 | 60.541 | 106612.701 | 10.73 | 106612.701 |  |  |  |  | GIVEN | 2024-08-01 | 2024-08-18 | PASS | [5 empty] | TP down hangtag has been updated by add M7YZ | Need strongly Followup to Update BOM |  | 145
80 | Timberland | 2023-11-23 | TB0A6XCT- Wash | Hoodie Jkt | 1817 | BR-2 | 2024-03-19 | 2024-03-23 | 1817 | Inhoused |  | 0 | OK |  | 32.77 | 23 | 41791 | 4.29 |  |  | Approved | Huagin: 39 Beal: Inhouse. 28th Feb. Inventory report Pending. |  | 2024-03-02 | 2024-03-13 | 2024-04-17 | PASS | [5 empty] | 1. Buy PR Has't CHINA PO, but Updated QCC File 3/7 has China PO. 2. Style: A6XCT, As per BOM & approved trims card attached Zipper Puller/Slider color is Metal plated black. But bulk inhouse zipper Puller/Slider color is Metal Silver. Please check & confirm the which one is correct. | Checking With VF. F24 Timberland Apparel China order-20240307 |  | Tight TNA | Tight TNA
81 | Timberland | 2023-12-21 | TB0A6XE2 | Over Shirt- Foot Locker | 1210 | SF-9 | 2024-05-20 | 2024-05-29 | 1210 |  | Inhoused | 0 | OK |  | 56 | 25.93 | 31375.3 | 7.28 |  |  | 0.14286 |  |  | GIVEN | 2024-05-02 | 2024-06-06 | PASS | [5 empty] | 540 Yds M4IX Dark Wheat Boot working for replacement for defect with slabs & hand feel issue . BR Approved.
82 | Timberland- Collab-Off Cyl | 2023-12-07 | TB0A6XFX | Pant | 2422 | SF-14 | 2024-04-04 | 2024-05-02 | 2422 |  |  | 0 | OK |  | 40.12 | 16.35 | 39599.7 | 5.21 |  |  | Approved | MI: 44 Bel: Inhouse 19 th Feb. Dyalot Problem, Missing. |  | OK | 2024-03-30 | 2024-05-09 | PASS |  |  |  | China Po CRD 5/15 ; Qty. 6741 Pcs | Line Plan Yet to !!
83 | Timberland | 2024-02-22 | TB0A6XJE | JKT | 2211 | BR-3 | 2024-06-14 | 2024-07-14 | 2211 |  |  | 0 | OK | 330 |  | 32.78 | 72476.58 | [6 empty] | 2024-05-28 | 2024-05-27 | 2024-07-03 | PASS | [5 empty] | 2024-07-04 |  | 1 Day improved CRD | 133 | ok
84 | Timberland | 2023-11-23 | TB0A6Y72-GB | Pant | 4091 | 2024-04-03 | 2024-04-22 | 2024-04-28 | 4091 | Booked | Inhoused | 0 | OK |  | 31.37 | 24.18 | 98920.38 | 4.3 |  |  | Approved | YOONIA TEX : 31 Bales. Inh. 10 th Mar |  | 2024-03-24 | 2024-04-03 | 2024-05-06 | PASS |  |  | Yez: TR202403048908-R01 | GB Test Fail 3/7: for Sprey Test. TR: Pass due to this styel fabric is not DWR- Not applicable. Sprey test. Pass report Pending. Pass. CRD 7/14 |  | GB Test Fail 3/7: for Sprey Test. TR: Pass due to this styel fabric is not DWR- Not applicable. Sprey test. | VF Confirm Not applicable Prey Test in this Style. Pass: 3/19 : TR: TR202403048908 |  |  | 700 Pcs CRD On 6th may Balance qty Later on Jun
85 | Timberland | 2024-01-25 | TB0A6Y7P-GB | Pant | 2810 | BR-3 | 2024-05-22 | 2024-05-29 | 2810 |  | Inhoused | 0 | OK | 350 | 26 | 15.08 | 42374.8 | 4 | 15.08 | 0 | 0.096774 |  |  | GIVEN | 2024-05-02 | 2024-06-06 | PASS |  |  |  | China CRD 6/21; Qty. 1616 Pcs |  |  |  | OK
86 | Timberland | 2024-02-22 | TB0A6Y8A | Pant | 5434 | SF-8 | 2024-05-30 | 2024-07-03 | 5434 |  |  | 0 | OK |  |  | 18.46 | 100311.64 | [6 empty] | GIVEN | 2024-06-02 | 2024-07-02 | C/O |  |  | 7/17 CRD |  |  | 2024-07-01 |  |  | 130 | Decrease PO yet to Update in INFO
87 | Timberland | 2024-03-21 | TB0A6Y8X-A | Pant | 4247 | BR-2 | 2024-08-08 |  |  |  |  | 4247 | OK |  | 26 | 17.42 | 73982.74 | 3.65 | 73982.74 |  |  |  | Tape rearrange qty. being delay. | GIVEN | 2024-07-20 | 2024-08-17 | PASS | [8 empty] | 150 | Infor has mention 3rd August
88 | Timberland | 2023-12-21 | TB0A6Y9J | Short Pant | 3490 | SF-04 | 2024-03-06 | 2024-03-16 | 3490 | Inhoused |  | 0 | OK | 780 | 35.54 | 15.305 | 53414.45 | 5.285 |  |  | Approved | MI: 44 Belt: Inhoused 19th Feb, Inspection Report Pending |  | Plan 20 Feb | 2024-03-02 | 2024-03-27 | PASS | [5 empty] | Style: A6Y9J, As per BOM & trims card Zipper puller Color is Cassel Earth - Grape Leaf YD. But Finishing section received Cord color is Mix-up(Cassel Earth-Grape Leaf, Cassel Earth) from MCD. Only Cassel earth color cord is not acceptable. Please check & replace the wrong cord |  |  | Disconnected | Disconnected
89 | Timberland | 2024-01-25 | TB0A6Y9J | Short Pant | 3792 |  | 2024-05-04 | 2024-05-12 | 3792 |  |  | 0 | OK |  | 35.54 | 15 | 56880 | 5 | 14.92 | -0.08 |  | MI:ETD: 3/10 |  | OK | 2024-04-20 | 2024-05-15 | PASS |  |  |  | 215 Pcs CRD Improved by 11th May to Vsl cut off Alignment. |  |  |  | OK | Disconnected | Disconnected
90 | Timberland | 2023-12-21 | TB0A6YA6 | Short Pant | 2611 | SF-14 | 2024-04-21 | 2024-05-05 | 2611 | 2024-04-21 |  | 0 | OK |  | 26.42 | 12.47 | 32559.17 | 3.93 | [5 empty] | 2024-03-22 | 2024-04-01 | 2024-05-10 | PASS | [5 empty] | 1. Buy PR Has't CHINA PO, but Updated QCC File 3/7 has China PO. | checking with VF.RE: F24 Timberland Apparel China order-20240307
91 | Timberland | 2023-11-23 | TB1A237T | JKT | 6219 | LS-5 | 2024-03-31 | 2024-05-05 | 6219 | Booked | Inhoused | 0 | OK |  | 120 | 47.44 | 295029.36 | 7.8 |  |  | C/O | Singtex: ETD: 3/6: ETA: 3/17. partial Shipment for Early Line feeding 300 Yds,9 Roll .Inhouse. 78 Roll ETD 3rd march. 168 Roll, Huafung. ETA: 3rd Mar.IH: 10th Mar. |  | C/O | 2024-03-21 | 2024-05-07 | PASS | [5 empty] | Shell 1: Spry Test Fail. Inhouse Lab. 3/24
92 | Timberland | 2023-11-23 | TB1A55RS | Bib | 2000 | Ly-10 | 2024-04-06 | 2024-04-26 | 2000 | Inhoused |  | 0 | OK |  |  | 34.62 | 69240 | 8 |  |  | C/O | Huafung: 2 March ETA: 168 Pakage. IH: 10th Mar. QST: 13 Roll Inhouse |  | C/O | 2024-03-20 | 2024-04-30 | PASS
93 | Timberland | 2023-11-23 | TB1A55RT | Bib | 3207 | Ly-07 | 2024-03-19 | 2024-04-07 | 3207 | Inhoused |  | 0 | OK | 300 | 74 | 37.828 | 121314.396 | 10.75 |  |  | Approved | All Inhoused. Z&Z. 5 Roll, 22 Roll, 37 Roll. |  | OK | 2024-03-17 | 2024-04-23 | PASS | [5 empty] | TB1A55RT # Short + Tall range = 1026 Pcs. Size Label Inhouse Missing- Regular 2010 Pcs Start to sewing. AD promised to delivery within 3/20.. pls note. | Need strong Followup AD
94 | Timberland | 2023-11-23 | TB1A6D9T | Pant | 2000 | LS-12 | 2024-04-20 | 2024-05-04 | 2000 |  |  | 0 | OK |  | 38 | 23.1 | 46200 | 9 |  |  | C/O | Monotex. KR. 82 Bl. 5th Mar ETA. Apex. 10 Roll - Inhouse. |  | C/O | 2024-03-25 | 2024-05-07 | PASS
95 | Timberland | 2024-02-22 | TB1A6D9T | Pant | 3244 | SF-09 | 2024-07-10 | 2024-07-18 | 3244 |  |  | 0 | OK | 400 | 38 | 23.1 | 74936.4 | 9 | [5 empty] | Need to HO Assort today. 6/14 | 2024-06-25 | 2024-07-23 | C/O | NO CONNECTING PLAN |  |  |  |  | 2024-07-18 |  |  | 147 | ok
|  |  |  | G. TOTAL as per buy report | 305219 |  |  |  | 299643 |  |  | 4247 |  |  | 317.5 |  | 9525923.522 | 44.415 | 73997.66 | -0.08
332 Pcs Misisng Infor PO
3000
|  | Shipped |  |  |  |  | 1.2
|  | TBL F24- 8/12 |  |  |  |  | 3490
|  | Total TNA | BULK SUMMARY | 95 | TNA Closed | TNA Finished Balance | 2500
|  | Total PO Qty. | 305219 | Running 02 line/ 02 TNA of 95 | 90 | 5
|  | Total Production | 299643 | Waiting for Run | 6 Style
|  | Total Shipment | 213778 | Till 8/12
|  | Ready to ship | 85865 |  | AUG. CRD PLAN | 80775
|  | Production Balance | 5576
|  | PPS Approved | 60/62
|  | PPS Req | 60 Style Given of 62
|  | GB TEST | 16 Style
Eid ul-Fitr – 9th April-24 to 19th Apr-24;Total 11day’s
Eid al-Adha-16th Jun-24 to 23th Jun-24; Total-08 day’s
| F24 BUY SUMMARY | TBL | NAPA | Total Qty.
| Total Style | 62 | 28
| TOTAL TNA | 93 | 33
| TOTAL QTY. | 305219 | 139557 | 444776 | Pcs
| TOTAL BUY | 8 | 5
| 1st CRD | 26th Mar | 7th May
| 1st TNA | 5th Feb. | 27th Mar
| Top Qty Style:TB0A62CF | 18627 Pcs | YUPIK FZH 3= 10007 Pcs
| Average TNA Qty. | 3295 | 4190
| Style Below 1k Qty | 7 Style | 0
| Style Below 2k Qty | 12 | 1
| Style Below 3k Qty | 27 | 10
| Style Below 4K Qty. | 24 | 11
| Avarage FOB | 31.4 | 24.19
| Total FOB till Feb.+ SMU Mar Buy | 9422593.34 | 3465395.92
| Total. ML | 9.4226 | 3.4654 | 12.888 | G.ML
| Forecast buy Mar. F24=6k | 186346 | 0.18635 | 13.0743 | G.ML
| Delivery | 18th July
| Production Month | Confirm Order | Projection |  | Monthly Total
| Feb'2024 | 10000 | 0 |  | 10000
| Mar'2024 | 35000 | 0 |  | 35000
| April'2024 | 65000 | 0 |  | 83000
| May'2024 | 85000 | 5000 |  | 90000
| June'2022 | 56000 | 29000 |  | 85000
| July'2024 | 2000 | 8000 |  | 10000
| Aug'2024 | 2000 | 5000 |  | 7000
TBL + NAPA Monthly Production based on CRD
| 2024-03-01 | 10K | 0
| 2024-04-10 | 19K | 10K
| 2024-05-01 | 103K | 40K
| 2024-06-01 | 75K | 61K
| 2024-08-01 | 72K | 26K
| 2024-09-01 | 11K | 1K
| 2024-10-01 | 1K | 0
| Total | 298K | 138K
EiD Cut-off: For all destination (EU, US, CANADA, MEXICO & APAC)
| BOOKING CUT-OFF |  | Last DAY of Goods Receiving before EID
| Time | Date | Time | Date
| 15:00 | 26th May 2024 | 15:00 | Sunday – 6th June 2024
Special Instructions :
A. All goods must be sent within cutoff date.
B. No late cargo will be accepted.
C. If we find any issue (such as incorrect or damaged label/sticker, damaged CTN or cargo, short or excess qty, unsorted cargo etc.) cargo will be directly rejected.
D. No rework will be allowed at our CFS during Eid Cut off.
E. Any documents issue must be resolved within cargo delivery.
F. BL Draft/Invoice/packing list/Factory File must be given on timely manner as per requirement.
G. Cargo will be unloaded on priority basis.
H. Regular operation of CFS will resume from one day after the EID day (19th June’24).
I. Above mentioned dates can be changed according to the Moon sight.
Formulas:
Final TNA/BPCD = [ERP/Planning Offer CRD (Style 1st CRD)]-46
Bulk Issue = [Buy Rec.Date]+[LT]
Bulk Issue = [LT]+[Buy Rec.Date]
E. Size Set H/O Date = [Final TNA/BPCD]-10
Note on F4: Author: 130 Pcs Reduced 12th Mar. 46 Pcs Top up 3/12 separate email= total 2264 pcs
Note on F6: Author: 44 PCS ADD TOP UP TO TOTAL= 2169
Note on F11: Author: 235 PCS po STILL MISISNG IN INFOR. Qty. Adjusted by VF advice 5% added to 92 pcs new PO: 3602 Pcs.
Note on F40: Author: Qty. 626 pcs Drop 4th Mar.
Note on Z40: Author: Improved TNA. 5th June to 1st June, but depands on fabric inhouse
Note on F43: Author: 4 Pcs TOP UP 4th mar
Note on Z47: Apurba:1st TNA was 14th May - Revised TNA 4th June.
Note on AA47: Author: CRD & TNA Has Reviksd due to Materials Late change.
Note on Z48: Apurba:1st TNA was 14th May - Revised TNA 4th June.
Note on AA48: Author: TNA/ CRD Revised Due Materils Late change
Note on AA55: Author: CRD Push out from 23 June.
Note on AA56: Author: CRD Push Out fron 23 June.
Note on Y69: Author: 109 Roll pending to make size set
Note on Z84: Author: Improved TNA 5/27 from 1st June.,Date.3/14; depends on Fabric inhouse
Note on F87: Author: Qty Drop 323 Pcs 3rd mar

## TBL S25 (hidden)
SL | Brand | Buy Rec. Date | Style/ Buy CO | Styling | O/Qty | Sewing Line | Production Start Date/ Materils Status. | Total Production 3/4 | Balance Qty | Production Status: 3/04 | Top Production | PPS Requsition Date 12/10 | PPS Status 1/2 (Challenge) | Size set file E. HO Date. | E.TNA/BPCD | Vendor Revised Last CRD (Style 1st CRD) | Lead Time | Trims issue | Bulk Issue: 1/20 | Solution | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | TIMBERLAND | 2024-05-24 | TB0A656F | C/O. 1 New Color Added | 3143 | RS-9 | Inhoused. | 3143 | O | OK | 300 | CO | CO- Pass | 2024-08-29 | 2024-09-10 | 2024-10-16 | 145 |  |  |  | 28 | 5.691 | 14 | 88004 | 17886.813 | 44002
2 | TIMBERLAND | 2024-05-24 | TB0A429N - WAAP | New | 985 | LY-2 | Inhoused. | 985 | 0 | OK | 300 | 2024-08-01 | Pass | 2024-08-16 | 2024-08-28 | 2024-10-01 | 125 |  |  |  | 55 | 7.481 | 27.8 | 54175 | 7368.785 | 27383
3 | TIMBERLAND | 2024-05-24 | TB0A68CB | New | 4205 | LY-2 | Inhoused. | 4205 | 0 | OK | 500 | 2024-08-01 | Pass | 2024-08-17 | 2024-08-24 | 2024-09-23 | 125 |  |  |  | 56.5 | 7.1247 | 23.6139 | 237582.5 | 29959.3635 | 99296.4495
4 | TIMBERLAND | 2024-05-24 | TB0A6EY1 | New | 2622 | LS-1 | Inhoused. | 2622 | 0 | OK |  | 2024-08-22 | Pass | 2024-09-09 | 2024-09-20 | 2024-11-08 | 150 |  |  |  | 19 | 2.7999 | 8.27 | 49818 | 7341.3378 | 21683.94
5 | TIMBERLAND | 2024-05-24 | TB0A6FA9 | New | 1409 | RS-9 | Inhoused. | 1409 | 0 | OK |  | 2024-08-01 | Pass | 2024-08-29 | 2024-09-10 | 2024-10-22 | 150 |  |  |  | 32 | 7.0003 | 17.44 | 45088 | 9863.4227 | 24572.96
6 | TIMBERLAND | 2024-06-21 | TB0A4235 | New | 7119 | SF-9 | Inhoused. | 7119 | 0 | OK |  |  | CO- Pass- Need to Make GB Sample. Req geive 09/22- will strat 10/24 | 2024-09-25 | 2024-10-06 | 11/10/2024( 3250 Pcs) | 123 |  |  |  | 35.5 | 6.0683 | 19.29 | 252724.5 | 43200.2277 | 137325.51
7 | TIMBERLAND | 2024-06-21 | TB0A44PP | New | 1535 | LS-13 | Inhoused. | 1535 | 0 | OK |  | Plan review 9/17. | Pass | 2024-09-14 | 2024-09-24 | 2024-10-22 | 130 |  |  |  | 56.5 | 11.7001 | 29.98 | 86727.5 | 17959.6535 | 46019.3
8 | TIMBERLAND | 2024-06-21 | TB0A5QUJ | New | 3155 | SF-2 | Inhoused. | 3155 | 0 | OK |  | PPS Done. 8/30 | Pass/ With GB Sample - balance - need to colelct from Bulk. | 2024-09-21 | 2024-09-29 | 2024-10-29 | 130 |  |  |  | 24.5 | 4.261 | 12.04 | 77297.5 | 13443.455 | 37986.2
9 | TIMBERLAND | 2024-06-21 | TB0A5WWB | New | 10869 | LY-3 | Inhoused. | 10869 | 0 | OK | 550 | Pass | Pass | 2024-09-14 | 2024-09-24 | 2024-10-29 | 130 |  |  |  | 55.5 | 9.5821 | 26.3312 | 603229.5 | 104147.8449 | 286193.8128
10 | TIMBERLAND | 2024-06-21 | TB0A5YEQ | New | 8327 | SF-9 | Inhoused. | 8327 | 0 | OK |  | CO | CO Pass | 2024-09-25 | 2024-10-15 | 2024-11-19 | 142 |  |  |  | 35.5 | 6.0801 | 19.56 | 295608.5 | 50628.9927 | 162876.12
11 | TIMBERLAND | 2024-06-21 | TB0A656F | New | 416 | RS-9 | Inhoused. | 416 | 0 | Ok | 300 | CO | Pass Buy CO | 2024-09-26 | 2024-10-08 | 2024-11-13 | 145 |  |  |  | 28 | 6.1882 | 18.6 | 11648 | 2574.2912 | 7737.6
12 | TIMBERLAND | 2024-06-21 | TB0A66XQ | New | 439 | LY-12 | Inhoused. | 439 | 0 | OK |  | PASS | Comments Pending. | 2024-10-24 | 2024-10-24 | 2024-11-18 | 150 |  |  |  | 46 | 6.081 | 22.54 | 20194 | 2669.559 | 9895.06
13 | TIMBERLAND | 2024-06-21 | TB0A6767 | New | 1077 | SF-8 | Inhoused. | 1077 | 0 | OK |  | GIVEN 9/22 | Pass | 2024-10-14 | 2024-10-19 | 2024-11-18 | 150 |  |  |  | 30 | 4.9435 | 18.99 | 32310 | 5324.1495 | 20452.23
14 | TIMBERLAND | 2024-06-21 | TB0A67GU- WAAP | New | 1492 |  | Inhoused. | 1492 | 0 | OK |  | Running 9/12 | Pass | Given | 2024-10-16 | 2024-11-15 |  |  |  |  | 41.5 | 19.04 | 19.04 | 61918 | 28407.68 | 28407.68
15 | TIMBERLAND | 2024-06-21 | TB0A67GU- WAAP | New | 339 |  | Inhoused. | 339 | 0 | OK |  | Running 9/16 | Pass | 2024-09-22 | 2024-10-01 | 2024-10-22 | 123 |  |  |  | 41.5 | 19.04 | 19.04 | 14068.5 | 6454.56 | 6454.56
16 | TIMBERLAND | 2024-06-21 | TB0A689U | New | 1651 | LY-12 | Inhoused. | 1651 | 0 | OK |  | Cutting Done. 9/1. Embo | Pass | 2024-09-18 | 2024-09-18 | 2024-10-22 | 125 for B'' ( 67 Pcs) 215 for A''( 1584 Pcs) |  |  |  | 68 | 9.4199 | 31.18 | 112268 | 15552.2549 | 51478.18
17 | TIMBERLAND | 2024-06-21 | TB0A68CB | New | 4371 | LY-2 | Inhoused. | 4371 | 0 | Ok | 500 | CO | Pass | CO | 2024-09-15 | 2024-10-15 | 115 for B'' ( 410 Pcs) 130 for A''( 2550 Pcs) |  |  |  | 56.5 | 7.7592 | 23.62 | 246961.5 | 33915.4632 | 103243.02
18 | TIMBERLAND | 2024-06-21 | TB0A68QK- Black + Dk Saphire | New | 4721 | RS-9 | Inhoused. | 4721 | 0 | OK |  | PPS Cutting Pending for !! | Pass | 2024-09-18 | 2024-09-17 | 2024-10-22 | 110 for B'' ( 4741 Pcs) 130 for A''( 2172 Pcs) |  |  |  | 31 | 5.1272 | 13.72 | 146351 | 24205.5112 | 64772.12
19 | TIMBERLAND | 2024-06-21 | TB0A68QK- Black | New | 2172 | RS-9 | Inhoused. | 2172 | 0 | OK |  |  | Pass | 2024-09-18 | 2024-10-02 | 2024-10-22 | 110 for B'' ( 4741 Pcs) 130 for A''( 2172 Pcs) |  |  |  | 31 | 5.1272 | 13.72 | 67332 | 11136.2784 | 29799.84
20 | TIMBERLAND | 2024-06-21 | TB0A69PU | New | 3505 | LY-2 | Inhoused. | 3505 | 0 | OK |  | PPS send to VF Chain PD 9/18 will review- 9/26 | Pass | Given | 2024-10-06 | 2024-11-10 | 115 |  |  |  | 56.5 | 7.9413 | 23.24 | 198032.5 | 27834.2565 | 81456.2
21 | TIMBERLAND | 2024-06-21 | TB0A6GHQ- WAAP | New | 1476 | LS-1 | Inhoused. | 1476 | 0 | OK |  | Plan 9/2 | Pass | Given | 2024-10-11 | 2024-11-17 | 105 for B'' ( 389 Pcs) 155 for A''( 1087 Pcs) |  |  |  | 27 | 3.1065 | 13.11 | 39852 | 4585.194 | 19350.36
22 | TIMBERLAND | 2024-07-26 | TB0A5QUJ | New | 2220 | SF-8 | Inhoused. | 2220 | 0 | OK |  | 2024-09-21 | Pass | CO | 2024-10-19 | 2024-12-08 | 115 & 130 |  |  |  | 24.5 | 4.5629 | 12.04 | 54390 | 10129.638 | 26728.8
23 | TIMBERLAND | 2024-07-26 | TB0A5T23 | New | 510 | BR-2 | Inhoused. | 510 | 0 | OK |  | Review Pending | Pass |  | 11/25 > Revise 12/5/2024 | 2025-01-05 | 135 |  |  |  | 58 | 29.1008 | 48.18 | 29580 | 14841.408 | 24571.8
24 | TIMBERLAND | 2024-07-26 | TB0A5T57 | New | 450 | BR-2 | Inhoused. | 450 | 0 | OK |  | Pass | Pass |  | 2024-11-15 | 2025-01-05 | 125 |  |  |  | 43 | 15.3118 | 30.53 | 19350 | 6890.31 | 13738.5
25 | TIMBERLAND | 2024-07-26 | TB0A5XFF | CO | 4154 |  | Inhoused. | 4154 | 0 | OK |  | 2024-09-30 | Pass | 2024-10-20 | 2024-11-01 | 2024-12-01 | 123 |  |  |  | 26 | 5.6177 | 13.72 | 108004 | 23335.9258 | 56992.88
26 | TIMBERLAND | 2024-07-26 | TB0A5YEQ | New | 1284 | SF-9 | Inhoused. | 1284 | 0 | OK |  | C/O | Pass | 2024-10-29 | 2024-11-10 | 2024-12-15 | 142 |  |  |  | 35.5 | 8.3577 | 22.83 | 45582 | 10731.2868 | 29313.72
27 | TIMBERLAND | 2024-07-26 | TB0A66XQ | New | 4332 | LY-12 | Inhoused. | 4332 | 0 | OK |  | C/O | Pass | 2024-10-21 | 2024-11-02 | 12/2/2024 & 12/16/2024 | 105 & 150 |  |  |  | 46 | 6.5926 | 19.7 | 199272 | 28559.1432 | 85340.4
28 | TIMBERLAND | 2024-07-26 | TB0A673Q | New | 4604 | LY-7 | Inhoused. | 4604 | 0 | OK |  | Pass | Pass |  | 2024-11-22 | 2025-01-10 | 150 |  |  |  | 29 | 5.0306 | 14.77 | 133516 | 23160.8824 | 68001.08
29 | TIMBERLAND | 2024-07-26 | TB0A6767 | New | 860 | Sf-8 | Inhoused. | 860 | 0 | OK |  | C/O | Pass | 2024-10-29 | 2024-11-10 | 2025-01-12 | 150 |  |  |  | 30 | 10.8494 | 24.98 | 25800 | 9330.484 | 21482.8
30 | TIMBERLAND | 2024-07-26 | TB0A677F | New | 8874 | LS-8 | Inhoused. | 8874 | 0 | OK |  | Pass | Pass | 2024-10-15 | 10/11& 11/25/2024 | 2024-12-23 | 150 |  |  |  | 21 | 3.3696 | 10.5 | 186354 | 29901.8304 | 93177
31 | TIMBERLAND | 2024-07-26 | TB0A689U | New | 2004 | PPS Approved | Inhoused. | 2004 | 0 | OK |  | CO | Pass | 2024-12-20 | 2025-01-01 | 2025-02-26 | 215 |  |  |  | 68 | 10.8266 | 31.18 | 136272 | 21696.5064 | 62484.72
32 | TIMBERLAND | 2024-07-26 | TB0A68CB | New | 3625 | LY-2 | Inhoused. | 3625 | 0 | OK |  | CO | pass | CO | 2024-10-18 | 11/18/2024 & 12/14/2024 | 115 & 130 |  |  |  | 56.5 | 7.9087 | 23.62 | 204812.5 | 28669.0375 | 85622.5
33 | TIMBERLAND | 2024-07-26 | TB0A68KU | New | 2088 | BR-4 | 1 COLOR 50% Inhoused. | 2088 | 0 | OK |  | Pass | Pass | Given 11/26 Black color inhoused. | 12/04/2024 > Revised 12/10/2024 | 2025-01-05 | 155 |  | Arvinva Item.MEER. Black color. 450 Yds Short - 210 Yds. Sending will be inhosed 12/14. |  | 38 | 8.5158 | 19.8 | 79344 | 17780.9904 | 41342.4
34 | TIMBERLAND | 2024-07-26 | TB0A68SF | New | 2233 | LY-13 | Inhoused. | 2233 | 0 | OK |  | Pass | Pass |  | 2024-12-05 | 2025-01-12 | 150 |  |  |  | 27 | 4.7563 | 15.75 | 60291 | 10620.8179 | 35169.75
35 | TIMBERLAND | 2024-07-26 | TB0A69QF | New | 2272 | LY-13 | Inhoused. | 2272 | 0 | OK |  | PASS | Pass | 2024-11-03 | 2024-11-15 | 2024-12-15 | 120 |  |  |  | 39 | 5.7945 | 15.61 | 88608 | 13165.104 | 35465.92
36 | TIMBERLAND | 2024-07-26 | TB0A6FE2 | New | 1675 | SF-7 | Inhoused. | 1675 | 0 | OK |  | 2024-10-04 | Pass | 2024-10-24 | 2024-11-02 | 2024-12-02 | 120 |  |  |  | 37.5 | 8.9961 | 20.1581 | 62812.5 | 15068.4675 | 33764.8175
37 | TIMBERLAND | 2024-07-26 | TB0A6FEZ | New | 3425 | RS-8 | Inhoused. | 3425 | 0 | OK |  | Pass | Pass | 2024-10-24 | 2024-11-02 | 2024-12-02 | 125 |  |  |  | 36 | 5.2307 | 14.95 | 123300 | 17915.1475 | 51203.75
38 | TIMBERLAND | 2024-07-26 | TB0A6V8P | New | 3776 | LS11 | Inhoused. | 3776 | 0 | OK |  | PPS Running | Pass |  | 11/22/2024 Revise TNA: 12/20 | 12/22/2024 > 12/29/2024 | 125 |  |  |  | 28 | 6.7515 | 18.8864 | 105728 | 25493.664 | 71315.0464
39 | TIMBERLAND | 2024-07-26 | TB0A6V9A | New | 2943 | LY-8 | Inhoused. | 2943 | 0 | OK |  | PPS Running | Pass |  | 11/22/2024 Revise TNA: 12/20 | 2025-01-10 | 125 |  |  |  | 26.5 | 5.5532 | 15.1077 | 77989.5 | 16343.0676 | 44461.9611
40 | TIMBERLAND | 2024-08-22 | TB0A677F | New | 2001 | LY-04 | Inhoused. | 2001 | 0 | OK |  | C/O | pass | 2024-10-15 | 2024-12-10 | 2025-01-20 |  |  | Buy Disconnect due to Fabric Balance Black Color balance. |  | 21 | 2.5229 | 10.6 | 42021 | 5048.3229 | 21210.6
41 | TIMBERLAND | 2024-08-22 | TB0A68CB | New | 600 | BR-2 | Inhoused. | 600 | 0 | OK |  | CO | pass | CO | 2024-10-10 | 2024-12-16 | 130 |  |  |  | 56.5 | 10.7503 | 28.51 | 33900 | 6450.18 | 17106
42 | TIMBERLAND | 2024-08-22 | TB0A6EY1 | New | 2216 | RS-8 | Inhoused. | 2216 | 0 | OK |  | C/O | pass | 2024-10-21 | 2024-11-02 | 2024-12-31 |  |  |  |  | 19 | 3.0506 | 8.15 | 42104 | 6760.1296 | 18060.4
43 | TIMBERLAND | 2024-08-22 | TB0A6FA9 | New | 602 | SF-10 | Inhoused. | 602 | 0 | OK |  | C/O | pass |  | 2024-12-01 | 2025-01-27 |  |  |  |  | 32 | 10.6565 | 21.95 | 19264 | 6415.213 | 13213.9
44 | TIMBERLAND | 2024-08-22 | TB0A6Y7P | CO | 4166 | SF-9 | Inhoused. | 4166 | 0 | OK |  | C/O: Size set not required. | pass; GB Pass |  | 2024-11-29 | 2024-12-29 |  |  |  |  | 26 | 5.1492 | 13.9 | 108316 | 21451.5672 | 57907.4
47 | TIMBERLAND | 2024-09-19 | TB0A6H6B | New | 191 | BR-2 | Inhoused. | 191 | 0 | OK |  | Plan to 12/10 | Pass |  | 2025-01-08 | 2025-02-12 |  |  |  |  | 40 | 16.1497 | 56.93 | 7640 | 3084.5927 | 10873.63
48 | TIMBERLAND | 2024-10-04 | A6H5Q | New | 189 | BR-3 | Inhoused. | 189 | 0 | OK |  | Plan to 12/10 | Pass |  | 2025-01-12 | 2025-02-11 |  |  |  |  | 73.5 | 39.8196 | 93.92 | 13891.5 | 7525.9044 | 17750.88
49 | TIMBERLAND- PRO | 2024-10-24 | TB0A645W | CO | 3627 | SF - 12 | Shell Fabric ETD: 1/08 from Korea. ETA 2/4: Consgment: 54 Beal | 3627 | 2603 | OK |  | CO- F24 | C/O | CO | 2024-02-13 | 2024-03-19 |  |  |  |  | 34.5 | 7.6131 | 25.64 | 125131.5 | 27612.7137 | 92996.28
[5 empty] | 129949 |  |  | 129949 | [15 empty] | 4874464 | 872441.4286 | 2439683.0773 | 0.17898
| TBL S25 | BULK SUMMARY: 2/17 | [23 empty] | 2.4397 | M
| Total TNA | 49
| Total PO Qty. | 129949 | Running: 0
| Total Production | 129949 | TNA Closed: 49
| Total Shipment | 124275 | OK
| Ready to ship | 5674
| Production Balance | 0
Formulas:
Size set file E. HO Date. = [E.TNA/BPCD]-12
Vendor Revised Last CRD (Style 1st CRD) = [Buy Rec. Date]+[Lead Time]
Vendor Revised Last CRD (Style 1st CRD) = [Buy Rec. Date]+150
PPS Requsition Date 12/10 = [Size set file E. HO Date.]-20
E.TNA/BPCD = [Vendor Revised Last CRD (Style 1st CRD)]-35
Note on F13: Author: 348 pcs drop EAMA PO.

## NAPA F24- TNA (hidden)
Brand: NAPAPIJRI Season-FW24 & SS25: Upate: 8th July. | [28 empty] | Date | 2024-03-04
SL | Season | Buyer | Buy Date | Style | O/Qty | Sewing Line. | P.star Date | Carton/ Poly Booking | P. End Date | Production | Production Balance | Production/ Size Set File HO | PPS Status | PPS requisition date | Final TNA | Actual CRD Should as per LT | 1st Offer CRD | Day Production | CRD Comments | Final CRD | Actual LT | Remarks | CRD As per LT | CRD Variation(+) | FOB | Total FOB | CM | SMV | Total CM | Total Min | Total Value | Issue | Solution
1 | FW24 | NAPAPIJRI | 2023-11-23 | A-WILDHORN-NP0A4I22 | 3751 | RS-8 | 2024-03-27 |  | 2024-04-30 | 3751 | 0 | OK | Approved | 2024-02-26 | 2024-03-27 |  | 2024-05-07 |  |  |  |  | ETA 3/3 |  |  | 30.92 | 115980.92 | 7.9695 | 43 |  | 161293 | 115980.92 | Fabric Delay Ship Technial Trouble during Trafic | TNA 6 Days Push out
2 | FW24 | NAPAPIJRI | 2023-11-23 | A-BUNZ FZH-NP0A4I1G- Print | 2661 | RS-10 | 2024-04-30 |  |  | 2661 | 0 | OK | Approved | 2024-02-29 | 2024-03-30 |  | 2024-05-14 |  |  |  |  | ETA 3/3 |  |  | 21.3 | 56679.3 | 4.1084 | 26 |  | 69186 | 56679.3
3 | FW24 | NAPAPIJRI | 2023-12-07 | TURNAGE 4-NP0A4IIU | 5198 | SF 9 | 2024-07-27 |  | 2024-08-11 | 5198 | 0 | OK | Approved | 2024-06-04 | 2024-07-04 | 2024-08-13 | 2024-08-13 | [7 empty] | 27 | 140346 | 6.1581 | 33.5 |  | 174133 | 140346
4 | FW24 | NAPAPIJRI | 2023-12-07 | ALTHER SHELL-NP0A4IIG | 4768 | RS-10 | 2024-04-07 |  |  | 4768 | 0 | Ok | Approved | 2024-03-05 | 2024-04-04 |  | 2024-05-14 | [7 empty] | 23.59 | 112477.12 | 6.3652 | 36 |  | 171648 | 112477.12
5 | FW24 | NAPAPIJRI | 2023-12-07 | K T-BURGEE HZH 1- NP0A4I6L | 2456 | RS-12 | 2024-05-06 | 2024-05-11 | 2024-05-12 | 2456 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | [7 empty] | 16.13 | 39615.28 | 4.8951 | 28 |  | 68768 | 39615.28 | Mill : Nice Gain , color Red Goji color which garments already made and ready to ship but test report rejected due to severe pilling at back. 500 Pcs PO will be short close. Bu getting FOB DN from Mill.
6 | FW24 | NAPAPIJRI | 2023-12-07 | K T-GONZEN H-NP0A4I5N | 1665 | RS-03 | 2024-05-19 |  | 2024-05-29 | 1665 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | [7 empty] | 14.26 | 23742.9 | 3.788 | 21.5 |  | 35797.5 | 23742.9
7 | FW24 | NAPAPIJRI | 2023-12-07 | K YUPIK FZH 3-NP0A4HG1 | 2523 | RS-13 | 2024-05-22 | 2024-05-23 |  | 2523 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | 650 | [6 empty] | 20.15 | 50838.45 | 7.2848 | 41.5 |  | 104704.5 | 50838.45
8 | FW24 | NAPAPIJRI | 2023-12-07 | T-TYNIK FZ-NP0A4IA9 | 3639 | SF-5 | 2024-05-18 |  | 2024-06-05 | 3639 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 |  |  | SF- Input START TODAY. |  |  |  |  | 19.96 | 72634.44 | 5.818 | 33 |  | 120087 | 72634.44 | The po: 520043355500100 will be 50 % Short shipemnt with PO close- QA Fabric Rejected.
9 | FW24 | NAPAPIJRI | 2023-12-07 | T-TYNIK FZH-NP0A4IA8 | 3892 | SF-5 | 2024-05-12 |  | 2024-06-05 | 3892 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | [7 empty] | 22.06 | 85857.52 | 6.35 | 36 |  | 140112 | 85857.52
10 | FW24 | NAPAPIJRI | 2023-12-07 | YUPIK FZ 3- NP0A4GNT | 5628 | RS-12 | 2024-06-06 |  | 2024-06-06 | 5628 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | [7 empty] | 25 | 140700 | 6.9474 | 39.5 |  | 222306 | 140700
11 | FW24 | NAPAPIJRI | 2023-12-07 | YUPIK FZH 3=NP0A4GNS | 10007 | RS-8 | 2024-05-22 | 2024-05-23 | 2024-06-12 | 10007 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | 650 | [6 empty] | 25.61 | 256279.27 | 7.3805 | 42 |  | 420294 | 256279.27
12 | FW24 | NAPAPIJRI | 2023-12-07 | YUPIK V-NP0A4HZK | 3010 | RS-10 | 2024-05-25 | 2024-05-26 | 2024-06-05 | 3010 | 0 | OK | Approved | 2024-03-28 | 2024-04-27 |  | 2024-06-06 | [7 empty] | 21.94 | 66039.4 | 4.9078 | 28 |  | 84280 | 66039.4
13 | FW24 | NAPAPIJRI | 2023-12-07 | T-BURGEE CURLY-NP0A4I5D | 3609 | SF-6 | 2024-06-10 |  | 2024-07-09 | 3609 | 0 | OK | Approved | 2024-04-30 | 2024-05-30 |  | 2024-07-09 | [7 empty] | 22 | 79398 | 6.1502 | 35 |  | 126315 | 79398
14 | FW24 | NAPAPIJRI | 2024-01-12 | A-MOESA PUF-NA4I1R | 6255 | LY-11 | 2024-05-08 | Inhoused | 2024-06-12 | 6255 | 0 | OK | Approved | 2024-04-02 | 2024-05-02 |  | 2024-06-06 | 1900-10-16 |  |  | 127 |  |  |  | 44.09 | 275782.95 | 11.06 | 83 |  | 519165 | 275782.95
15 | FW24 | NAPAPIJRI | 2024-02-23 | A-BUNZ FZH-NP0A4I1G- Print | 2156 | BR-04 | 2024-07-11 |  | 2024-07-15 | 2156 | 0 | OK | Approved |  | 2024-06-24 | 2024-07-23 | 2024-07-23 |  |  |  | 142 | With GR,Insufficient LT | 2024-07-14 | #REF! | 21.3 | 45922.8 | 4.1084 | 26 |  | 56056 | 45922.8
16 | FW24 | NAPAPIJRI | 2024-02-23 | A-WILDHORN-NP0A4I22 | 2440 | SF-07 | 2024-07-11 |  | 2024-07-18 | 2440 | 0 | OK | Approved |  | 2024-06-24 | 2024-07-23 | 2024-07-23 |  |  |  | 142 | With GR,Insufficient LT | 2024-07-14 | #REF! | 30.92 | 75444.8 | 7.9695 | 43 |  | 104920 | 75444.8
17 | FW24 | NAPAPIJRI | 2024-02-23 | T-BURGEE CURLY -NP0A4I5D | 2480 |  |  |  | 2024-07-13 | 2480 | 0 | ok | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 134 | Without GR | 2024-07-06 | #REF! | 22 | 54560 | 5.06 | 37 |  | 91760 | 54560
18 | FW24 | NAPAPIJRI | 2024-02-23 | YUPIK FZ 3-NP0A4GNT | 5558 | RS-3 | 2024-07-02 |  | 2024-07-13 | 5558 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 127 | Without GR | 2024-06-29 | #REF! | 25 | 138950 | 5.86 | 44 |  | 244552 | 138950
19 | FW24 | NAPAPIJRI | 2024-02-23 | T-SELINE HZH W-NP0A4HYO | 3505 | SF-13 | 2024-06-27 |  | 2024-07-09 | 3505 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 117 | Without GR | 2024-06-19 | 20 | 24 | 84120 | 5.4 | 40 |  | 140200 | 84120 |  | In-housed. 6/23
20 | FW24 | NAPAPIJRI | 2024-02-23 | T-ARGIENT-NP0A4HZJF | 3982 | SF-7 | 2024-06-14 |  | 2024-07-03 | 3982 | 0 | OK | Approved |  | 2024-05-28 | 2024-07-02 | 2024-07-02 |  |  | PPS req. GIVEN 5/12 | 127 | Without GR,Insufficient LT | 2024-06-29 | #REF! | 23.16 | 92223.12 | 4.19 | 29 |  | 115478 | 92223.12
21 | FW24 | NAPAPIJRI | 2024-02-23 | YUPIK W 2.0 1-NP0A4I55W | 4581 | RS 13 | 2024-06-08 |  | 2024-07-06 | 4581 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-02 | 2024-07-02 |  | CRD Improved | 2024-07-09 | 127 | Without GR,Insufficient LT | 2024-06-29 | #REF! | 23.84 | 109211.04 | 6.38 | 47 |  | 215307 | 109211.04
22 | FW24 | NAPAPIJRI | 2024-02-23 | T-DOLENT FZ-NP0A4HZP | 5070 | Sf-14 | 2024-06-26 |  | 2024-07-06 | 5070 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 | 800 |  |  | 133 | Without GR,Insufficient LT | 2024-07-05 | #REF! | 21.28 | 107889.6 | 3.96 | 29 |  | 147030 | 107889.6
23 | FW24 | NAPAPIJRI | 2024-02-23 | T-DOLENT HZ-NP0A4HZO | 3840 | SF-14 | 2024-07-07 |  | 2024-07-13 | 3840 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  | POLY + CTN REQ. NOT YET. Given 76/6 |  | 133 | Without GR,Insufficient LT | 2024-07-05 | #REF! | 19 | 72960 | 3.7 | 27 |  | 103680 | 72960
24 | FW24 | NAPAPIJRI | 2024-02-23 | YUPIK OG H W-NP0A4I542 | 5459 | RS-13 | 2024-06-08 | 2024-06-10 | 2024-06-12 | 5459 | 0 | OK | Approved |  | 2024-05-28 | 2024-07-02 | 2024-07-02 |  |  | PPS Req. given 5/13 | 114 | With GR | 2024-06-16 | #REF! | 26.5 | 144663.5 | 6.5 | 50 |  | 272950 | 144663.5
25 | FW24 | NAPAPIJRI | 2024-02-23 | A-MOESA PUF-NA4I1R | 2596 | LY-11 | 2024-06-26 |  | 2024-07-07 | 2596 | 0 | OK | Approved |  | 2024-06-24 | 2024-07-23 | 2024-07-23 |  | MOLINA DOWN DELAY EXTENTION Ready Date by 5/13; Revise CRD proposed 7/23. TNA will be revised. waiting for VF final feedback | 2024-08-09 | 127 | Without GR,Insufficient LT | 2024-06-29 | #REF! | 44.09 | 114457.64 | 11.06 | 83 |  | 215468 | 114457.64 | MOLINA DOWN DELIDY EXTENTION by 5/13; Revise CRD proposed 8/13. TNA will be revised. waiting for VF final feedback | Inhoused- Issue solved.
26 | FW24 | NAPAPIJRI | 2024-02-23 | T-TYNIK FZ-NP0A4IA | 3268 | SF-5 | 2024-07-03 |  | 2024-07-13 | 3268 | 0 | ok | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  | Line Connected Sewing plan with Dec Buy. need input by 1st June. | 127 | Without GR | 2024-06-29 | #REF! | 19.96 | 65229.28 | 4.79 | 35 |  | 114380 | 65229.28 | Fabric Quality Issue. Might Be short shipment.
27 | FW24 | NAPAPIJRI | 2024-02-23 | YUPIK FZH 3-NP0A4GN | 7424 | RS-8 | 2024-06-26 |  | 2024-07-13 | 7424 | 0 | ok | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 127 | Without GR | 2024-06-29 | #REF! | 25.6 | 190054.4 | 6.07 | 43 |  | 319232 | 190054.4
28 | FW24 | NAPAPIJRI | 2024-02-23 | YUPIK V-NP0A4HZK | 2555 | RS-10 | 2024-07-01 |  | 2024-07-13 | 2555 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 127 | Without GR | 2024-06-29 | #REF! | 21.94 | 56056.7 | 4.9078 | 28 |  | 71540 | 56056.7
29 | FW24 | NAPAPIJRI | 2024-02-23 | T-TYNIK FZH-NP0A4IA8 | 3108 | SF-7 | 2024-07-01 |  | 2024-07-06 | 3108 | 0 | OK | Approved |  | 2024-06-04 | 2024-07-09 | 2024-07-09 |  |  |  | 134 | Without GR | 2024-07-06 | #REF! | 22.06 | 68562.48 | 6.35 | 36 |  | 111888 | 68562.48
30 | FW24 | NAPAPIJRI | 2024-03-01 | TALIA W-NP0A4IIV | 2394 | BR-02 | 2024-08-08 |  | 2024-08-11 | 2394 | 0 | OK | Approved | Sample ready for review. 6/25 | 2024-06-22 | 2024-08-06 | 2024-08-06 |  |  |  | 127 | Without GR | 1931-07-30 |  | 23.83 | 57049.02 | 5.56 | 45 |  | 107730 | 57049.02
31 | FW24 | NAPAPIJRI | 2024-03-01 | TARALGA FZ 1-NP0A4IKV | 6317 |  | 1000 Pcs Added by VF |  | 2024-08-11 | 6317 | 0 | OK | Approved | Sample ready for review. 6/25 | 2024-06-25 | 2024-08-06 | 2024-08-06 |  | 1000 Pcs Added by VF |  | 130 | Without GR | 1931-07-30 |  | 26.56 | 167779.52 | 5.67 | 46 |  | 290582 | 167779.52
32 | FW24 | NAPAPIJRI | 2024-03-01 | THEOS V-NP0A4IHW | 3541 | BR-5 | CRD/ TNA Revised |  | 2024-08-11 | 3541 | 0 | OK | Approved | Sample ready for review. 6/25 | 2024-07-02 | 2024-06-20 | 2024-08-13 | 300 | 280 Pcs Short ship for Fabric Quality Issue. | 2024-08-06 | 140 | Without GR | 1931-07-30 |  | 14.01 | 49609.41 | 4.06 | 33 |  | 116853 | 49609.41 | LT File has wrong LT. singtex Lt should 85 Days i/o 60 Days CRD will be 6th Aug. TNA wil be Revised
33 | FW24 | NAPAPIJRI | 2024-03-01 | TARALGA 4 -NP0A4IHU | 9936 | SF-12 | 2024-07-11 |  | 2024-07-30 | 9936 | 0 | OK | Approved | Sample ready for review. 6/25 | 2024-06-25 | 2024-08-06 | 2024-08-06 |  |  |  | 130 | Without GR | 1931-07-30 |  | 29.31 | 291224.16 | 6.13 | 50 |  | 496800 | 291224.16
[5 empty] | 139272 |  |  |  |  | 139272 | 0
| NAPA F24; 8/12 | BULK SUMMARY
| Total TNA | 33 | Running 04 Line/ 04 TNA of 33
| Total PO Qty. | 139272 | Waiting for Run | 0
| Total Production | 139272 | TNA Closed: | 33 |  |  | S24 |  | 43 | style
| Total Shipment | 110470 | TNA Balance | 0
| Ready to ship | 28802 | Aug. Balance CRD PO | 18072
| Production Balance | 0 |  |  | Fabric QC Rejected to replace Partial Production & Ship plan Qty.( T-TYNIK FZH GREEN URBAN & K T-BURGEE HZH 1 RED GOJI) 5200433532 & 5200433553 | 780 Pcs
efore Eid Cut Off Shipemnt Status. 6/6/2024.
| 1 | TBL – 5 HQ Container, 4 Cont. BK Approved, Pending 1 Cont.
| 2 | NAPA 6 HQ Container. No BK Approved, Pending All. 6 Cont.
Total 7 Cont. BK Approval pending for Forwarder, due to Container/ Spec Issue. Since, VF Logistic/ SP team working together on this issue.
Formulas:
PPS requisition date = [Final TNA]-30
CRD As per LT = [Actual LT]+[Buy Date]
CRD As per LT = [Buy Date]+[Actual LT]
Note on P3: Author: AS PHNOE DISCUSED WITH IQBAIL PCD
Note on R3: Author: CRD Improved.
Note on F18: Author: 80 Pcs Top Up. 3/3 infor tiger
Note on F21: Author: File 1 + 2
Note on F22: Author: file 1+2
Note on F23: Author: file 1+2
Note on Q23: Author: Brand Frequest CRD Improived 3/17
Note on R23: Author: Brand Frequest CRD Improived by 7/2 on date of 3/17
Note on F25: Author: file1 + 2
Note on F28: Author: File 1 +2
Note on F31: Author: 190 pcs Top Up 3/3 in infor
Note on F33: Author: Late Add 6317 Pcs. Mar buy was 5317 Pcs
Note on U34: Author: Fabric lead time 85 Days

## TBL S26
Brand: TIMBERLAND Season: S26
SL | Season | Buyer | Buy Date | Style | Buy Staus | Item Details | Fabric Mill | Styling | O/Qty | PO Status. | Production St: 7/28 | Production Balance | PPS/HO Status: 7/27 | E.TNA | CRD | Long LT Fabric Ex- Mill | Merchandising update | Fabric Delivery Details | Trims Delivery Date | production Start Date. | Production Finished date. | Closing Reprt received Date. | Shipment Status | TNA Remarks for Materils | Materials Status. | Issue | Fabric EX- Mill ( Long LT Items) | UC Item wise | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | S26 | TIMBERLAND | 2025-05-21 | TB0A4495 | Open | DWR Stratham Cotton Bomber |  | NEW, Buy CO June. | 455 |  |  | 455 | 2025-08-07 | 2025-09-06 | 2025-10-20 |  | B= LT: 140 Days | Shell 1 Monotex ETD 7/14, Lining 1 Square Local, Lining-2 : Jibo ETD. 7/6 | Long lead time Trims deady date 6/30. | [5 empty] | Red House Fabric Ex-Mill Date. 6/05 | [5 empty] | 34.5
2 | S26 | TIMBERLAND | 2025-05-21 | TB0A66XQ | Open | QUICK-DRY CONVERTIBLE PANTS |  | CO-S25 | 467 |  |  | 467 | 2025-08-11 | 2025-09-10 | 2025-10-05 |  | A= LT: 135 days | Shell 1: Apex; 8/5, Wu luen. 7/14. | Long lead time Trims deady date 6/30. | [5 empty] | Fabric Ex- Mill: 5/30. Long Lead time Trims Need to Air collect_ VF Will Pay | [5 empty] | 39.6
3 | S26 | TIMBERLAND | 2025-05-21 | TB0A6N4K | Open | AF Waterproof Cotton Barn Coat |  | CO-F25 | 3615 |  |  | 3615 | 2025-08-31 | 2025-09-30 | 2025-11-10 |  | A= LT: 160 days | Shell 1 Monotex- ETD 8/6; Jibo ETD 8/25; | Long lead time Trims deady date 6/30. | [5 empty] | Fabric Ex- Mill: 5/30. Long Lead time Trims Need to Air collect_ VF Will Pay | [5 empty] | 42.02
4 | S26 | TIMBERLAND | 2025-05-21 | TB0A6VSJ | Open | Lightweight Puffer Vest |  | CO-F25 | 2715 |  |  | 2715 | 2025-07-26 | 2025-08-25 | 2025-10-03 |  | B= LT: 120 Days | Shell 1 Jibo ETD 7/16, Lining Jibo ETD 7/6 | Long lead time Trims deady date 6/30.
5 | S26 | TIMBERLAND | 2025-05-21 | TBC0YH32 | Open | Chore Canvas Jacket- wash |  | Buy CO June | 2886 |  |  | 2886 | Send for Log in - 7/26 | 2025-08-16 | 2025-09-15 |  | A+ LT: 108 Day(Z&Z FABRIC) | Shell 1 Local ETD 8/4 | Long lead time Trims deady date 6/30.
6 | S26 | TIMBERLAND | 2025-06-19 | TB0A2PE2 | Buy File Updated. | Men's Pant | Z&Z | CO F25, Need to clarify Shetch at WB throw insde constraction wihout cut &Sew to witho C&S. as per F25 | 3919 |  |  |  |  | 2025-09-03 | 2025-10-03 | [15 empty] | 12
7 | S26 | TIMBERLAND | 2025-06-19 | TB0A2QPD | Buy File Updated. | Womens Lining Jackt | Monotex Fab: B: 125 LT | CO F25, CO color Safari, but New Color DK Olive 302 Col. Added. | 2319 |  |  |  |  | 2025-09-23 | 2025-10-23 | [15 empty] | 34.51
8 | S26 | TIMBERLAND | 2025-06-19 | TB0A4235 | Buy File Updated. | Men's Jacket | Monotex Fab | CO F25- Need to Checkif New color Added. | 3355 |  |  |  |  | 2025-09-27 | 2025-10-27 | [15 empty] | 19.18
9 | S26 | TIMBERLAND | 2025-06-19 | TB0A42BF | TP Measurment Delay- buy File update. Ack Pending. Ok | Womens Parka | Monotex Fab | New | 2000 |  |  |  |  | 2025-09-18 | 2025-10-18 | [15 empty] | 39.32
10 | S26 | TIMBERLAND | 2025-06-19 | TB0A447F AF of TB0A5SHA | TP Delay- Ack Pending. Solved. |  | Monotex Fab | New | 2589 |  |  |  |  | 2025-09-20 | 2025-10-18 |  | Ex mill 9/8: Shell Fabric Air Collect by VF cost. AF $ 1800 has been Approved. Need to Inhoused 9/18 | [13 empty] | 24.54
11 | S26 | TIMBERLAND | 2025-06-19 | TB0A4495 | Buy File Updated. | Mens Bomber Jacket | Monotex Fab | Buy CO May- Connecting TNA | 2917 |  |  |  |  | 2025-10-08 | 2025-11-17 | [15 empty] | 20.95
12 |  | TIMBERLAND | 2025-06-19 | TB0A4495 | Buy File Updated. | Mens Bomber Jacket | Monotex Fab | Buy CO May- Connecting TNA | 4572 |  |  |  |  | 2025-09-18 | 2025-10-18
13 | S26 | TIMBERLAND | 2025-06-19 | TB0A44GB | Buy File Updated. | Seam Sealing- Waterproof Barn Coat | Monotex Fab | CO F25, 2 color CO, New color Leaf Green A58 | 2448 |  |  |  |  | 2025-09-23 | 2025-10-23 | [15 empty] | 38.48
14 | S26 | TIMBERLAND | 2025-06-19 | TB0A5SHA GF of TB0A447F | TP Delay. Buy File Updated. Infor Updated. Solved. |  | Monotex Fab | New, AF Style of GF Style A447F | 1104 |  |  |  |  | 2025-10-25 | 2025-11-24 | [15 empty] | 24.25
15 | S26 | TIMBERLAND | 2025-06-19 | TB0A5SHY GF A4487. | Buy File Updated. |  | Monotex Fab |  | 2484 |  |  |  |  | 2025-09-25 | 2025-10-27 | [15 empty] | 16.54
16 | S26 | TIMBERLAND | 2025-06-19 | TB0A5WNU | Buy File Updated. |  | HYOSUNG: Will Come Materials UC/ MOQ/MCQ 3K/1K |  | 947 |  |  |  |  | 2025-09-18 | 2025-10-23 | [15 empty] | 27.14
17 | S26 | TIMBERLAND | 2025-06-19 | TB0A68CB | Buy File Updated. |  | XINGHUA |  | 5528 |  |  |  |  | 2025-09-20 | 2025-10-28 | [15 empty] | 23.5
18 | S26 | TIMBERLAND | 2025-06-19 | TB0A68XF | Buy File Updated. |  | XINGHUA |  | 4870 |  |  |  |  | 2025-09-25 | 2025-11-03 | [15 empty] | 33.03
19 | S26 | TIMBERLAND | 2025-06-19 | TB0A69PU | Buy File Updated. |  | XINGHUA | CO F25 | 3981 |  |  |  |  | 2025-09-20 | 2025-10-27 | [15 empty] | 23.25
20 | S26 | TIMBERLAND | 2025-06-19 | TB0A6KTQ | Buy File Updated. |  | Z&Z |  | 2658 |  |  |  |  | 2025-09-03 | 2025-10-03 | [15 empty] | 13.65
21 | S26 | TIMBERLAND | 2025-06-19 | TBC0YH32 | Buy File Updated. |  | Z&Z | Buy CO May, Connecting TNA | 3175 |  |  |  |  | 2025-09-01 | 2025-10-13 | [15 empty] | 17.8
22 | S26 | TIMBERLAND | 2025-07-23 | TB0A2PE2 |  |  |  |  | 733 | Hold PI Confirm, Untill VF Approved UC |  |  |  |  | 2025-10-31 |  | 187 Pcs 10/31, 546 pcs 11/28
23 | S26 | TIMBERLAND | 2025-07-23 | TB0A2QZA |  |  |  |  | 5547 | [5 empty] | 2025-12-12 |  | 88 pcs 12/12 , 274 pcs 12/29 rest of from 1/04/26
24 | S26 | TIMBERLAND | 2025-07-23 | TB0A42AF |  |  |  |  | 2644 | [5 empty] | 2025-11-22 |  | 1694 11/22, bal. 12/7
25 | S26 | TIMBERLAND | 2025-07-23 | TB0A447F |  |  |  |  | 3317 |  |  |  |  | 2025-10-30 | 2025-11-29 |  |  | Ex- Mill: 9/19
26 | S26 | TIMBERLAND | 2025-07-23 | TB0A4487 |  |  |  |  | 3031 |  |  |  |  | 2025-10-23 | 2025-11-22
27 | S26 | TIMBERLAND | 2025-07-23 | TB0A4495 |  | Mens Bomber Jacket | Monotex Fab | Buy CO June- Connecting !! | 3320 |  |  |  |  | 2025-10-30 | 2025-11-29 |  |  | Shafari Color 1689 Pcs 1st Ex Mill 9/12 & Col. Oceana 1631 Pcs Ex Mill: 9/19 both Color CRD 11/29.
28 | S26 | TIMBERLAND | 2025-07-23 | TB0A44GB |  |  |  |  | 3748 | [5 empty] | 2025-11-27
29 | S26 | TIMBERLAND | 2025-07-23 | TB0A5M68 |  |  |  |  | 2765 | [5 empty] | 2025-12-01
30 | S26 | TIMBERLAND | 2025-07-23 | TB0A5MB8 |  |  |  |  | 2110 | [5 empty] | 2025-10-31
31 | S26 | TIMBERLAND | 2025-07-23 | TB0A5N8M |  |  |  |  | 431 | Hold PI Confirm, Untill VF Approved UC |  |  |  |  | 2025-11-30
32 | S26 | TIMBERLAND | 2025-07-23 | TB0A5N9J |  |  |  |  | 382 | Hold PI Confirm, Untill VF Approved UC |  |  |  |  | 2025-11-30
33 | S26 | TIMBERLAND | 2025-07-23 | TB0A5SHA |  |  |  |  | 903 | Hold PI Confirm, Untill VF Approved UC |  |  |  | 2025-11-01 | 2025-12-22 |  | 1800Y/ 290 KG Need to Air Collet Connecting TNA with June buy. 134 Pcs 12/22 CRD Rest of from 12/28( Ex Mill: 10/17, TNA secured)
34 | S26 | TIMBERLAND | 2025-07-23 | TB0A5SJK |  |  |  |  | 4843 | [5 empty] | 2025-12-01
35 | S26 | TIMBERLAND | 2025-07-23 | TB0A5WNU |  |  |  |  | 600 | Hold PI Confirm, Untill VF Approved UC |  |  |  |  | 2025-11-27
36 | S26 | TIMBERLAND | 2025-07-23 | TB0A5WPF |  |  |  |  | 3352 | [5 empty] | 2025-11-27
37 | S26 | TIMBERLAND | 2025-07-23 | TB0A677F |  |  |  |  | 2211 | [5 empty] | 2025-12-07
38 | S26 | TIMBERLAND | 2025-07-23 | TB0A67J3 |  |  |  |  | 2153 | [5 empty] | 2025-11-22
39 | S26 | TIMBERLAND | 2025-07-23 | TB0A68CB |  |  |  |  | 2772 | [5 empty] | 2025-12-02
40 | S26 | TIMBERLAND | 2025-07-23 | TB0A6HNY |  |  |  |  | 1590 | [5 empty] | 2025-11-12
41 | S26 | TIMBERLAND | 2025-07-23 | TB0A6JJ3 |  |  |  |  | 590 | Hold PI Confirm, Untill VF Approved UC |  |  |  |  | 2025-12-07
42 | S26 | TIMBERLAND | 2025-07-23 | TB0A6KRU |  |  |  |  | 1517 | [5 empty] | 2025-11-15
43 | S26 | TIMBERLAND | 2025-07-23 | TB0A6KUB |  |  |  |  | 2380 | [5 empty] | 2025-11-10
44 | S26 | TIMBERLAND | 2025-07-23 | TB0A6VSJ |  |  |  |  | 2002 | [5 empty] | 2025-11-28
59737
S26 Projection
|  |  | Still May-1 Buy Recevied | 3919
|  |  | NAPA S26 | BULK SUMMARY:
|  |  | Total TNA |  |  | Running Style:
Total PO Qty.
|  |  | Total Production |  |  | TNA Closed:
Total Shipment
|  |  | Ready to ship |  |  | Closing Report Rec.
|  |  | Production Balance |  |  | Closing Report Balance
TNA Balance:
EID HOLIDAY-2026 (ESTIMATED)
Eid Start Day |  |  | End Day | Total Day
2025-03-21 |  |  | 2025-03-30 | 9
2025-05-29 |  |  | 2025-06-07 | 9
Formulas:
PPS/HO Status: 7/27 = [E.TNA]-30
E.TNA = [CRD]-30

## NAPA S26
Brand: NAPA Season: S26
SL | Season | Buyer | MER | Buy Date | Style | Item Details | Embellishment Approval status | Styling | O/Qty | Sewing Line | Production St: 7/27 | Production Balance | PPS/HO Status: 7/27 | E.TNA | CRD | Final Ex-mill | Fabric Delivery Deatails 7/21 | Merchandising update: 7/21 | production Start Date. | Production Finished date. | Closing Reprt received Date. | Shipment Status | TNA Remarks for Materils | Materials Status. | Issue | Fabric EX- Mill ( Long LT Items) | UC Item wise | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | SS26 | NAPAPIJRI | Sahed | 2025-04-29 | A-MELVILLE | Mens Jkt |  | CO- S25 | 3594 | RS-5 | 70 | 3524 | Approved | 2025-07-12 | 2025-08-12 |  | Shell 1 Red House( TW) ETD: 6/9 | All Materils inhoused. | [5 empty] | Red House Fabric Ex-Mill Date. 6/05 | [5 empty] | 34.5
2 | SS26 | NAPAPIJRI | Mehedi | 2025-05-13 | A-RAINCAPE L | Rain Coat |  | New | 1667 |  |  | 1667 | Approved | 2025-07-12 | 2025-08-12 |  | Shell 1 Jibo ETD: 6/5, Seam Tape: 6/30, Payment will be 6/25 or 6/30, Air Freight inv need to sellet Mateirls Liablity. | All Materils inhoused. Need Fabirc Inspection, inventory, Seal Seaing Test Report |  |  |  |  | Fabric payment done. FF Booking done, Bemis Tape need to air collect. | Fabric Ex- Mill: 5/30. ETD: 6/5, ETA: 6/17. .Long Lead time Trims Need to Air collect_ VF Will Pay | [5 empty] | 39.6
3 | SS26 | NAPAPIJRI | Mehedi | 2025-05-13 | A-RIVALTO FIELD | Men's Jkt |  | New | 3079 | LS-5 | 230 | 2849 | Approved | 2025-07-12 | 2025-08-12 |  | Shell 1 Jibo ETD: 6/5. Seam Tape. Ex 6/18 | All Materils inhoused. Need Fabirc Inspection, inventory, Seal Seaing Test Report |  |  |  |  | Fabric payment done. FF Booking done, Bemis Tape need to air collect. | Fabric Ex- Mill: 5/30. ETD: 6/5, ETA 6/17. Long Lead time Trims Need to Air collect_ VF Will Pay | [5 empty] | 42.02
4 | SS26 | NAPAPIJRI | Sahed | 2025-05-28 | A-TUNDRA 1 | Mens Jkt |  | Print change) Need to make PPS, since CO S25 | 2705 |  |  | 2705 | Req. Cutting done. 7/27 | 2025-08-25 | 2025-09-30 |  | Shell 1 Red House( TW) ETD: 7/10 | ETD Done. 71 Roll, ETA: 7/21 | [5 empty] | Red House Pi Mention. Delivery date 7/10.All Fabric Ready greige Booking | [5 empty] | 24.89
5 | SS26 | NAPAPIJRI | Farhan | 2025-06-13 | BALKAS FZH 5 | Mens Jkt |  | Willson Elistic, Tape will be in housed 7/29. | 2550 |  |  | 2550 | 2025-07-31 | 2025-08-30 | 2025-09-30 |  | Shell 1 Jibo EX- MIll: 7/26, Push improved Ex- Mill 7/21 to catch Cut off 7/23, | 1st Ship ETD: 7/16; 267 Roll; ETA: 2nd ship Yet to Forwerder Booking ?? | [11 empty] | 19.05 | Zipper will be change
6 | SS26 | NAPAPIJRI | Farhan | 2025-06-13 | B-LOCKROY FZH | Mens Jkt |  | HD Print. Sub. 7/25, need to follow up to geet approval. | 4950 |  |  | 4950 | 2025-07-26 | 2025-08-30 | 2025-09-30 |  | Shell- 1 Apex EX- Mill : 7/17, Should Ex- Mill 7/15 to catch 7/17 Cut off. Mill asking 23yh July Ex- Mill. On beating. | 1st Ship ETD: 7/21; 122 Roll; ETA: 8/2; 2nd ship Yet to Forwerder Booking ?? | [11 empty] | 27.52
7 | SS26 | NAPAPIJRI | Farhan | 2025-06-13 | NEZY SHORT 2 | Mens Shorts |  | Willson Elistic, Tape will be in housed 7/29. | 13940 |  |  | 13940 | 2025-08-07 | 2025-09-06 | 2025-11-18 | Jibo Item EX mill Delay. Code- 124732--JBP9668 , Color- Sharkskin 17-3914TCX & Qty.-2590 | Shell 1 Jibo EX- MIll: 7/26, Push improved Ex- Mill 7/21 to catch Cut off 7/23 | 1st Ship ETD: 7/16; 267 Roll; ETA: 2nd ship Yet to Forwerder Booking ?? | [11 empty] | 10.79
8 | SS26 | NAPAPIJRI | Farhan | 2025-06-13 | RF NEXT WB | Mens Jkt |  | Shine Ebo. Tape need to get Apparaval form VF BD | 9111 |  |  | 9111 | 2025-07-31 | 2025-08-30 | 2025-09-30 |  | Shell 1 Jibo EX-Mill: 7/08. catch cut off 7/10.Seam Tape ETD: | 1st Ship ETD: 7/16; 267 Roll; ETA: 2nd ship Yet to Forwerder Booking ?? Late add 220 Pcs Fabric will be ready 8/5- need to colelct courier, Others trims 8/5 Need Courier collect.; 4 Dark color need to input 1st priority; Velcro Whit wisper, Toppu, jepry) Will be inhused 8/30) Courier collet. | [11 empty] | 36.97
9 | SX26 | NAPAPIJRI | Mehedi | 2025-06-19 | AMIS SUM V 1 | Mens Jkt |  |  | 2777 |  |  | 2777 | 2025-08-11 | 2025-09-10 | 2025-10-14 |  | Shell1: Hyson 8/2 & Lining Jibo. Ex- Mill : 7/25 | [12 empty] | 18.54
10 | SX26 | NAPAPIJRI | Mehedi | 2025-06-19 | AMIS SUM STAND 1 | Mens Jkt |  |  | 2686 |  |  | 2686 | 2025-08-11 | 2025-09-10 | 2025-10-14 |  | Shell1: Hyson 8/2 & Lining Jibo. Ex- Mill : 7/25 | [12 empty] | 23.88
11 | SS26 | NAPAPIJRI | Sahed | 2025-06-26 | A-TRAVELER | Mens Jkt (NORMAL WASH 55 Tmp 20 Min) Hamza Wash |  | New | 2201 |  |  | 2201 | 2025-08-26 | 2025-09-25 | 2025-10-28 |  | Shell-1, Mill: Seojing- Ex- Mill: 8/7, Jibo Ex - mill 8/7 | [12 empty] | 50.03
12 | SS26 | NAPAPIJRI | Sahed | 2025-06-26 | A-TRAVELER SHORT D W | Mens Jkt( Deep Dry) wash Capacity 80 Pcs each day.( Hamza wash) Need to male sewing plan considering Wash production Capacity. |  | New | 1152 |  |  | 1152 | 2025-08-26 | 2025-09-25 | 2025-10-28 |  | Shell-1, Mill: Seojing- Ex- Mill: 8/7, Jibo Ex - mill 8/7 | [12 empty] | 57.56
13 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | A-BIOIS |  |  | CO-FW25 | 3054 |  |  | 3054 | 2025-08-29 | 2025-09-28 | 2025-10-28 | 2025-08-18 | Shell: HUAMOA- EX-Mill: 8/18 | [5 empty] | HUA MO: $2100 | [6 empty] | 24.13
14 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | A-GIOVI 1 |  |  |  | 3818 |  |  | 3818 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-20 | Shell: Red House: Ex- Mill: 8/20, Need to Ex mill 8/19 to meet 8/20 Cut off. Wu Luen Ex- Mill 8/19. , Jibo Lining Ex- mill should 8/25 | [12 empty] | 20
15 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | A-RIVALTO COT |  |  |  | 2176 |  |  | 2176 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-25 | Shell: Huajin: Ex Mill 8/20 to Catch 8/21 if not then Ex Mill 8/25 Cut off 8/28, Squar 9/6: Local , Jibo Lining Delivery Should 8/25 | [12 empty] | 37.95
16 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | A-SECRET W |  |  | CO-SS25 | 543 |  |  | 543 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-25 | Shell: Formosa- Taiwan- 8/24; Hua Jin 8/25. Need to improve Ex- Mill 8/19; Cut off 8/20 align with Wu Luen Shipment. | [5 empty] | Hua jin $ 666 | [6 empty] | 35.55
17 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | K A-ALLORI |  |  |  | 2003 |  |  | 2003 | 2025-08-29 | 2025-09-28 | 2025-10-28 | 2025-08-19 | Shell: Red House Ex- Mill: 8/20; Lining Jibo: Ex- Mill 9/8, Not Acceptable. Shell & Lining All Should Ready 8/6. | [12 empty] | 15.92
18 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | K A-DIPOLE |  |  |  | 1500 |  |  | 1500 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-25 | Shell: Huajin: Ex Mill 8/20 to Catch 8/21 if not then Ex Mill 8/25 Cut off 8/28, Jibo: 9/8. Not Accepte to be 8/6, Squear 9/6 | [12 empty] | 20.54
19 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | K RAINFOREST SUM 4 |  |  | CO-SS25 | 3126 |  |  | 3126 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-25 | Shell: Red House: Ex- Mill: 8/20, Need to Ex mill 8/19 to meet 8/20 Cut off. Wu Luen Ex- Mill 8/19. Jibo: 9/8; will be 8/6 as per Gr + Col. Booking | [12 empty] | 12.52
20 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | O-LEORAS |  |  |  | 2348 |  |  | 2348 | 2025-09-05 | 2025-10-05 | 2025-11-04 | 2025-08-25 | Shell: Huajin: Ex Mill 8/20 to Catch 8/21 if not then Ex Mill 8/25 Cut off 8/28, Squar 9/6: Local , Jibo Lining Delivery Should 8/25 | [12 empty] | 25
21 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | RF NEXT PDF |  |  |  | 396 |  |  | 396 | 2025-09-06 | 2025-10-06 | 2025-11-05 | 2025-08-30 | VINTAS PI PENDING FOR SGS TEST REPORT, Jibo Lining Delivery should 8/25. | [12 empty] | 67.27 | 16.8175 | 84.0875
22 | SS26 | NAPAPIJRI | Sahed | 2025-07-11 | SKIDOO PDF |  |  |  | 336 |  |  | 336 | 2025-09-06 | 2025-10-06 | 2025-11-05 | 2025-08-29 | VINTAS PI PENDING FOR SGS TEST REPORT, VISTAS: Ex- Mill 8/29; 1 Pcs 15th Oct. CRD need to make this with PPS | [12 empty] | 159.04 | 39.76 | 198.8
23 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | A-CLOUDY 2.0 |  |  |  | 2071 |  |  | 2071 | 2025-09-07 | 2025-10-07 | 2025-11-11 | Wu Luen 3 Sep, Yet not rcv PI from Jibo
24 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | A-MELVILLE |  |  | Buy CO | 1929 |  |  | 1929 | 2025-08-31 | 2025-09-30 | 2025-11-04 | Red House-15 Aug , Surcharge $345 | Mill Accept 5 Days Delivery improvement. To align all Ship together.
25 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | K A-MELVILLE |  |  |  | 1500 |  |  | 1500 | 2025-08-31 | 2025-09-30 | 2025-11-04 | Red House-15 Aug , Surcharge $345 | Mill Accept 5 Days Delivery improvement. To align all Ship together.
26 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | MEZY 5 |  |  |  | 2200 |  |  | 2200 | 2025-08-10 | 2025-09-09 | 2025-10-14 | Yet not rcv PI from Jibo
27 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | NEZY SHORT 2 |  |  | Buy CO | 2750 |  |  | 2750 | 2025-09-14 | 2025-10-14 | 2025-11-18 | Yet not rcv PI from Jibo
28 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | RAINFOREST M SUM 3 |  |  |  | 3514 |  |  | 3514 | 2025-09-14 | 2025-10-14 | 2025-11-18 | Red House- 3 Sep, Yet not receive PI from Jibo
29 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | RF NEXT WB |  |  | Buy CO | 9037 |  |  | 9037 | 2025-09-07 | 2025-10-07 | 2025-11-11 | Yet not rcv PI from Jibo
30 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | T-TYNIK FZH |  |  |  | 2499 |  |  | 2499 | 2025-09-21 | 2025-10-21 | 2025-11-25 | FURUI-17Sep (Wu Luen asked surcharge $200 & FURUI asked surcharge $450 | Mill Accept 10 Days Delivery improvement.
31 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | V-REFLECT |  |  |  | 3553 |  |  | 3553 | 2025-09-21 | 2025-10-21 | 2025-11-25 | WULUEN-3Sep
32 | SS26 | NAPAPIJRI | Farhan | 2025-07-25 | V-ZINC |  |  |  | 2203 |  |  | 2203 | 2025-08-31 | 2025-09-30 | 2025-11-04 | WULUEN-3Sep
[9 empty] | 71783 |  | 300
2025-07-10
|  |  |  | S26 Projection | [15 empty] | 2025-08-09
|  |  |  | Still July 2 Buy Recevied | 71783 | [10 empty] | 2025-07-28 |  |  |  | 2025-09-18
2025-09-16
|  |  |  | NAPA S26 | BULK SUMMARY: 7/27
|  |  |  | Total TNA | 32 | Running Style:2
|  |  |  | Total PO Qty. |  | 71783
|  |  |  | Total Production | 300 | TNA Closed:
Total Shipment
|  |  |  | Ready to ship |  | Closing Report Rec.
|  |  |  | Production Balance |  | Closing Report Balance
TNA Balance:
EID HOLIDAY-2026 (ESTIMATED)
Eid Start Day |  |  |  | End Day | Total Day
2025-03-21 |  |  |  | 2025-03-30 | 9
2025-05-29 |  |  |  | 2025-06-07 | 9
Formulas:
PPS/HO Status: 7/27 = [E.TNA]-30
E.TNA = [CRD]-31
Production Finished date. = [Production Finished date., row above]+40
Final Ex-mill = [Final Ex-mill, row above]+50
Note on J10: Author: XS size late added 220 Pcs

## NAPA F25
Brand: NAPAPIJRI Season: FW25
SL | Season | Buyer | Buy Date | Style | Item Details | Embellishment Approval status | Styling | O/Qty | Sewing Line | Production St 7/22 | Production Balance | PPS/HO Status 7/20 | TNA | CRD | Merchandising update 7/20 | production Start Date. | Production Finished date. | Closing Reprt. | Shipment Status | TNA Remarks for Materils | Materials Status. | Issue | Fabric EX- Mill ( Long LT Items) | UC Item wise | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | F25 | NAPAPIJRI | 2024-11-15 | D-TOSA V | Quilting Vest( Inhouse) |  | New | 2012 | SF-5 | 2012 | 0 | Approved. | 2025-01-25 | 2025-02-25 |  | 2025-02-18 | 2025-02-24 | Yes | All Ship has Done. |  | Protex RiB Issue - Replace Balance.
2 | F25 | NAPAPIJRI | 2024-11-15 | D-TOSA FZ | Quilting Jkt( Inhouse) |  | New | 3413 | SF-5 | 3413 | 0 | Approved. | 2025-01-25 | 2025-02-25 |  | 2025-02-05 | 2025-02-18 | Yes | All Ship has Done. |  | Protex RIB Issue- 3 Color Balacne.
3 | F25 | NAPAPIJRI | 2024-11-15 | O-CASIES LS | Men's Padding Jkt |  | New | 4150 | SF-5 | 4150 | 0 | Approved. | 2025-01-25 | 2025-02-25 |  | 2025-01-18 | 2025-02-02 | Yes | All Ship has Done. |  | All OK
4 | F25 | NAPAPIJRI | 2024-11-28 | K A-GESAR H | Kids Padidng H Jkt( In House Quilting) Print | PRINT OK FOR COLOR AND ARTWORK- Need to get Bulk apprpval form VF BD. | New | 2305 | RS: 14 | 2305 | 0 | Approved. | 2025-03-01 | 2025-04-08 |  | 2025-03-05 | 2025-04-09 |  |  |  | All Inhoused.
5 | F25 | NAPAPIJRI | 2024-11-28 | A-GESAR H | Mens Padidng Jkt( In House Quilting) Print | PRINT OK FOR COLOR AND ARTWORK- Need to get Bulk apprpval form VF BD. | New | 3477 | RS-14 | 3477 | 0 | Approved. | 2025-03-10 | 2025-04-22 |  | 2025-03-15 | 2025-04-23 |  |  |  | All Inhoused.
6 | F25 | NAPAPIJRI | 2024-11-28 | A-GESAR V | Mens Padidng Vest( In House Quilting) Print | PRINT OK FOR COLOR AND ARTWORK- Need to get Bulk apprpval form VF BD. | New | 2043 | RS-14 | 2043 | 0 | Approved. | 2025-03-10 | 2025-04-22 |  | 2025-04-13 | 2025-04-15 |  |  |  | All Inhoused.
7 | F25 | NAPAPIJRI | 2024-11-28 | A-SORT WINT H W | Wom Hooded Padding Jkt ( In Housed Onion Quilting) |  | New | 2617 | LY-12 | 2617 | 0 | Approved. | 2025-03-15 | 2025-04-22 |  | 2025-03-13 | 2025-04-08 |  |  |  | All Inhoused.
8 | F25 | NAPAPIJRI | 2024-11-28 | T-DERGANA HZ | Mens Fleecewear- Embo |  | New | 4065 | RS-7 | 4065 | 0 | Approved. | 2025-03-15 | 2025-04-22 |  | 2025-03-22 | 2025-03-24 |  |  | Wu Luen lycra fabric bring by air | All Inhoused.
9 | F25 | NAPAPIJRI | 2024-11-28 | A-SORT WINT L W | Wom Padding Long Jkt ( In Housed Onion Quilting) |  | New | 2029 | RS-18 | 2029 | 0 | Approved. | 2025-03-15 | 2025-04-22 |  | 2025-03-23 | 2025-04-10 |  |  |  | All Inhoused.
10 | F25 | NAPAPIJRI | 2024-11-28 | K T-ARBARI | Kids Fleecewear - Print on Woven pnl at chest | PRINT OK FOR COLOR AND ARTWORK- Need to get Bulk apprpval form VF BD. | New | 1651 | LY-13 | 1651 | 0 | Approved. | 2025-03-15 | 2025-04-22 |  | 2025-03-10 | 2025-04-17 |  |  |  | All Inhoused.
11 | F25 | NAPAPIJRI | 2024-11-28 | T-DERGANA FZ | Mens Fleecewear- Embo |  | New | 2494 | RS-8 | 2494 | 0 | Approved. | 2025-03-15 | 2025-04-22 |  | 2025-03-27 | 2025-05-11 |  |  | Wu Luen lycra fabric bring by air | All Inhoused.
12 | F25 | NAPAPIJRI | 2024-11-28 | EPOCH W S 1 | Wom Saam Sealing Jkt | SMS not make, need to follow P1 | New: NO SMS- P1 need to follow for PPS | 2009 | RS-10 | 2100 | 0 | Approved. | 2025-03-20 | 2025-05-06 |  | 2025-03-20 | 2025-04-23 |  |  |  | All Inhoused.
13 | F25 | NAPAPIJRI | 2024-12-03 | ASHERMAN |  |  | New | 14845 | BR + RS-8 | 14845 | 0 | Approved. | 2025-03-12 | 4/15/2025/4/29 |  | 2025-03-08 | 2025-04-08 |  |  | Line Stop 4/09; fabric QC issue- | All Inhoused. | Shell Fabric RED HOUSE CREISED MARK FOUND 3/24. DURING SEWING> Mill replacing fabric by air PP, since Sew line disclosed _ balance goods CRD will be revised.
14 | F25 | NAPAPIJRI | 2024-12-03 | TARALGA 4 |  |  | CO | 7133 | SF-5 | 7133 | 0 | Approved. | 2025-03-25 | 2025-04-29 |  | 2025-04-09 |  |  |  | One Sku GE4 Delivery date need to take from mill | All Inhoused. | Need to collect Madira Embo Thread by air collect from China
| F25 | NAPAPIJRI | 2024-12-03 | TURNAGE 4 |  |  | CO | 8258 | RS-7 | 8258 | 0 | Approved. | 2025-03-25 | 2025-04-29 |  | 2025-04-16 |  |  |  | Wu Luen lycra fabric bring by air Tight TNA) | All Inhoused. | Need to collect Madira Embo Thread by air collect from China
16 | F25 | NAPAPIJRI | 2024-12-03 | AGRAM |  |  | New | 4867 | LY-12 | 4867 | 0 | Approved. | 2025-03-27 | 2025-05-13 |  | 2025-04-18 |  |  |  | Sewing end Date 4 days late from CRD | All Inhoused.
17 | F25 | NAPAPIJRI | 2024-12-03 | ALTHER SHELL 1 | 2025-02-10 |  | CO, But Patch Label has Changed. | 5856 | SF-9 | 5856 | 0 | Approved. | 2025-03-27 | 2025-05-13 | Sewing completed | 2025-04-15 |  |  |  | Hinda Textile inside pkt bag fabric might be delay to TNA need to revise till 4/10 | All Inhoused.
18 | F25 | NAPAPIJRI | 2024-12-03 | ASHERMAN WINT W |  |  | New | 3700 | RS-3 | 3700 | 0 | Approved. | 2025-04-08 | 2025-05-06 | Ok | 2025-04-21 |  |  |  | Can Improved TNA 3/25- Fabric Rady b4 CNY | All Inhoused.
19 | F25 | NAPAPIJRI | 2024-12-03 | TARALGA FZ 1 |  |  | CO | 7080 | SF-5 | 7080 | 0 | Approved. | 2025-04-12 | 2025-05-20 |  | 2025-04-21 |  |  |  |  | All Inhoused. | Need to collect Madira Embo Thread by air collect from China
20 | F25 | NAPAPIJRI | 2024-12-03 | TRESER HZ |  |  | New | 4018 |  | 4018 | 0 | Approved. | 2025-04-12 | 2025-05-20 |  | 2025-05-05 |  |  |  |  | All Inhoused.
21 | F25 | NAPAPIJRI | 2024-12-03 | TRESER V |  |  | New | 3249 |  | 3249 | 0 | Approved. | 2025-04-12 | 2025-05-20 | Color N1J Sherpa fabric has change | 2025-04-21 |  | Yes |  |  | All Inhoused. | FAR ESTAN- Shell Fabric TCX Issue- Masshmall Clr.
22 | F25 | NAPAPIJRI | 2024-12-03 | ALES |  |  | New | 6916 | RS-5 | 6916 | 0 | Approved. | 2025-04-20 | 2025-05-20 |  | 2025-05-05 | Running |  |  | HUAMOA- EX- Mill 3/20 - TNA Revised. | All Inhoused.
23 | F25 | NAPAPIJRI | 2024-12-12 | A-BIOIS |  |  | CO | 3650 | RS:8,6 | 3650 | 0 | Approved. | 2025-03-09 | 2025-04-15 |  | 2025-03-13 | 2025-03-25 |  |  | Huamao- Lonely Shell ( Binding & Pkt Bag) TTL Req. 2500 Yds. Mill Prosed 2 time Ex- Mill 4th Mar. (1410 Yds.) balance Qty. Will be Air collect. Issue Solved. | All Inhoused. | Tea Leaf . Lycra 1300 Yds. Will be inhoused 3/14
24 | F25 | NAPAPIJRI | 2024-12-12 | K T-TYNIK |  |  | New | 1143 | SF-7 | 1143 | 0 | Approved. | 2025-03-15 | 2025-04-29 |  | 2025-04-10 |  | Yes |  | Tight TNA > Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28- Need Air Collect to be Inhoused. 3/15. | All Inhoused.
25 | F25 | NAPAPIJRI | 2024-12-12 | K YUPIK FZH 3 |  |  | F24-Season Carry Over | 2001 | Rs-5 | 2001 | 0 | Approved. | 2025-03-15 | 2025-04-29 |  | 2025-03-25 |  | Yes |  | Tight TNA > Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28- Need Air Collect to be Inhoused. 3/15. | All Inhoused. | Lyacra Binding delay booked, Due to CAD Missed the Portion.
26 | F25 | NAPAPIJRI | 2024-12-12 | A-BIEZ MODULAR PUF | Consider to collect Air shipment of fabric MONOMATERIAL POLY RIP TJ |  | New | 2006 | LS-4 | 2006 | 0 | Approved. | 2025-03-20 | 4/22/2025 & 4/29 | Sewing completed | 2025-04-09 |  |  |  | Taijing- Japan- Yet to share PI - as per LT, Ex. Mill should be 2/17/2025, pre- plan Air Collect to be Inhoused 03/03/2025, Others Hyosung Fabric ready 3rd Jan. OK | All Inhoused.
27 | F25 | NAPAPIJRI | 2024-12-12 | K A-TEREZ |  |  | New | 2330 | LY-12 | 2330 | 0 | Approved. | 2025-03-23 | 2025-04-29 | Sewing completed | 2025-04-09 | 2025-04-27 | Yes |  | Tight TNA > Concodia- Ex- Mill 2/20 Cut off.( Fab. Booking 9 days late from buy rec date.)Need to work with mill inprove EX mill by 2/16 to cut off 2/17. others Mill ok | All Inhoused.
28 | F25 | NAPAPIJRI | 2024-12-12 | A-EGA L W | Need to Make P3- with Actual Garment. Need to make pupy improved Sampel befre PPS. |  | New | 3119 | Ly-2 | 3119 | 0 | Approved. | 2025-04-10 | 2025-05-20 |  | 2025-05-04 | Running | Zipper Issue: CAD incorrect Mesure. Will inhoused 4/8 |  | HYOSUNG- EX- Milll 2/16. Cut off Monday- 2/17 & Jibo Ex-Mill 2/20, need 1 day improved ex-mill to cut off (Thu) alignment 2/19. | All Inhoused.
29 | F25 | NAPAPIJRI | 2024-12-12 | A-EGA SHORT W | Need to Make P3- with Actual Garment. Need to make pupy improved Sampel befre PPS. |  | New | 3943 | LY-13 | 3943 | 0 | Approved. | 2025-04-10 | 2025-05-20 |  | 2025-04-19 | 2025-05-13 |  |  | HYOSUNG- EX- Milll 2/16. Cut off Monday- 2/17 & Jibo Ex-Mill 2/20, need 1 day improved ex-mill to cut off (Thu) alignment 2/19. | All Inhoused.
30 | F25 | NAPAPIJRI | 2024-12-12 | T-FIEMME |  |  | New | 3301 | RS-11 | 3301 | 0 | Approved. | 2025-04-10 | 2025-05-20 |  | 2025-04-26 | Running |  |  | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28.Lycra by air | All Inhoused.
31 | F25 | NAPAPIJRI | 2024-12-12 | T-TYNIK FZ |  |  | F24-Season Carry Over | 2001 | SF-7 | 2001 | 0 | Approved. | 2025-04-10 | 2025-05-20 | Sewing completed | 2025-04-21 |  |  |  | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28. | All Inhoused.
32 | F25 | NAPAPIJRI | 2024-12-12 | T-TYNIK FZH |  |  | F24-Season Carry Over | 2502 |  | 2502 | 0 | CO. | 2025-04-10 | 2025-05-20 | [5 empty] | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28. | All Inhoused.
33 | F25 | NAPAPIJRI | 2024-12-12 | YUPIK FZ 3 |  |  | F24-Season Carry Over | 6454 | RS-10 | 6454 | 0 | Approved./ CO PPS made for Size Label position Only. | 2025-04-10 | 2025-05-20 |  | 2025-05-09 | Running |  |  | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28. | All Inhoused.
34 | F25 | NAPAPIJRI | 2024-12-12 | YUPIK FZH 3 |  |  | F24-Season Carry Over | 12038 | RS-10 | 12038 | 0 | Approved. | 2025-04-10 | 2025-05-20 |  | 2025-04-10 |  |  |  | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28. | All Inhoused.
35 | F25 | NAPAPIJRI | 2024-12-12 | YUPIK V |  |  | F24-Season Carry Over | 2853 | BR4 | 2853 | 0 | Approved./ CO PPS made for Size Label position Only. | 2025-04-10 | 2025-05-20 |  | 2025-04-23 |  |  |  | Nice Gain- E- Mill B4 CNY & Furi X- mill 2/17, Wu Luen X- mill 2/28. | All Inhoused.
36 | F25 | NAPAPIJRI | 2024-12-12 | T-MONTEPIANA |  |  |  | 3691 | LS-8 | 3691 | 0 | Approved. | 2025-04-12 | 2025-05-20 |  | 2025-04-30 | 2025-05-19 |  |  | Nice Gain X- Mill 2nd Mar, Cut Off 3/3. Others Ok | All Inhoused.
37 | F25 | NAPAPIJRI | 2024-12-12 | T-DELBIOS |  |  |  | 2747 |  | 2747 | 0 | Approved. | 2025-04-15 | 2025-05-20 |  | 2025-04-27 |  |  |  | Concodia- Ex- Mill 3/8 Cut off 3/10. others Mill ok | All Inhoused.
38 | F25 | NAPAPIJRI | 2024-12-12 | A-TEREZ |  |  |  | 6048 | LY-12 | 6048 | 0 | Approved. | 2025-04-17 | 2025-06-24 |  | 2025-05-06 | 2025-05-24 |  |  | Concodia- Ex- Mill 3/8 Cut off 3/10. others Mill ok | All Inhoused.
39 | F25 | NAPAPIJRI | 2024-12-12 | A-NEMES |  |  |  | 2207 | RS-7 | 2207 | 0 | Approved. | 2025-04-19 | 2025-05-27 |  | 2025-05-12 |  |  |  | Concodia- Ex- Mill 3/8 Cut off 3/10. others Mill ok | All Inhoused.
40 | F25 | NAPAPIJRI | 2024-12-12 | A-MOESA PUF |  |  | F24-Season Carry Over, but need ot make PPS for size Label position Changes and 2 New color added only. | 3561 | LY-9 | 3561 | 0 | Approved. | 2025-05-05 | 2025-06-24 |  | 2025-05-09 | 2025-06-22 |  |  | Concodia- Ex- Mill 3/8 Cut off 3/10. others Mill ok | All Inhoused.
41 | F25 | NAPAPIJRI | 2025-02-14 | ASHERMAN | UC ISSUE |  | CO | 2000 | RS-8 | 2000 | 0 | Approved. | 2025-05-31 | 2025-07-22 | 1wk Extention taken for late Production Start.
42 | F25 | NAPAPIJRI | 2025-02-14 | TARALGA FZ 1 | 4/9/2025 Ex-Mill( Nice Gain) |  | CO | 4729 | RS-10 | 4729 | 0 | Approved. | 2025-05-31 | 2025-07-15
43 | F25 | NAPAPIJRI | 2025-02-14 | A-BIOIS | UC/ CRD Issue, HUAMAO Ex- Mill 5/15 & 5/30 | Offering 7/29 (Lae GR Booking by VF) | CO | 3458 | RS-9 | 3458 | 0 | Approved. | 2025-06-25 | 2025-07-22 | [6 empty] | 2830 Pcs CRD 7/15 and 3458 Pcs 7/22( Due to Partial GR late Booking)
44 | F25 | NAPAPIJRI | 2025-02-14 | D-TOSA FZ | Quilting Jkt( Inhouse) |  | Buy CO | 1800 |  | 1800 | 0 | Approved. | 2025-04-27 | 2025-05-27 | 43 Roll; Jibo Late Inhoused to be 4/25.
45 | F25 | NAPAPIJRI | 2025-02-14 | D-TOSA V | Quilting Vest( Inhouse) |  | Buy CO | 2001 | SF-5 | 2001 | 0 | Approved. | 2025-04-27 | 2025-05-27 |  | 2025-05-10 | Running
46 | F25 | NAPAPIJRI | 2025-02-14 | TARALGA 4 | 4/9/2025 Ex-Mill( Nice Gain) |  | CO | 8283 | SF-5 | 8283 | 0 | Approved. | 2025-05-25 | 2025-07-15
47 | F25 | NAPAPIJRI | 2025-02-14 | A-BIOIS | UC/ CRD Issue, HUAMAO Ex- Mill 5/15 & 5/30 | Offering 7/29 (Lae GR Booking by VF) | CO | 2830 | RS-9 | 2830 | 0 | Approved. | 2025-06-15 | 2025-07-15 | [6 empty] | 2830 Pcs CRD 7/15 and 3458 Pcs 7/22( Due to Partial GR late Booking)
48 | F25 | NAPAPIJRI | 2025-02-27 | T-TYNIK FZ |  |  | CO | 2102 | Rs-5 | 2102 | 0 | Approved. | 2025-06-02 | 2025-07-08
49 | F25 | NAPAPIJRI | 2025-02-27 | YUPIK OG H W |  |  |  | 3719 | RS-11 | 3719 | 0 | Ready for Review | 2025-06-02 | 2025-07-08
50 | F25 | NAPAPIJRI | 2025-02-27 | YUPIK V |  |  | CO | 2000 | RS-7 | 2000 | 0 | Approved. | 2025-06-02 | 2025-07-08
51 | F25 | NAPAPIJRI | 2025-02-27 | A-GESAR H |  |  | CO | 3025 | RS-14 | 3025 | 0 | Approved. | 2025-06-02 | 2025-07-08
52 | F25 | NAPAPIJRI | 2025-02-27 | A-SORT WINT H W |  |  | CO | 2006 | LY-13 | 2006 | 0 | Approved. | 2025-06-02 | 2025-07-08
53 | F25 | NAPAPIJRI | 2025-02-27 | A-TEREZ |  |  | CO | 12568 | LY-1 | 12568 | 0 | Approved. | 2025-06-02 | 2025-07-08
54 | F25 | NAPAPIJRI | 2025-02-27 | M-ISARCO W | Full Pant. Shell Fabric from DYNAMO- TURKY |  |  | 1500 |  | 1500 | 0 | Approved. | 2025-06-02 | 2025-07-08
55 | F25 | NAPAPIJRI | 2025-02-27 | T-ASTROLABE W 1 | Mens Fleece Jacket |  |  | 682 | BR-3 | 682 | 0 | Approved. | 2025-06-02 | 2025-07-08
56 | F25 | NAPAPIJRI | 2025-02-27 | T-DERGANA FZ |  |  | CO | 5813 | RS-7 | 5813 | 0 | Approved. | 2025-06-02 | 2025-07-08
57 | F25 | NAPAPIJRI | 2025-02-27 | T-SELINE HZH W |  |  |  | 2576 | SF-9 | 2576 | 0 | Approved. | 2025-06-02 | 2025-07-08 | All Materils Inhoused. Sku, BEIGE DIMITY, Contarst panel Fall on Rock Hold till further VF confirmation.
58 | F25 | NAPAPIJRI | 2025-02-27 | T-TYNIK FZH |  |  | CO | 1400 | SF-9 | 1400 | 0 | Approved. | 2025-06-02 | 2025-07-08
59 | F25 | NAPAPIJRI | 2025-02-27 | YUPIK FZ 3 |  |  | CO | 8108 | RS-10 | 8108 | 0 | Approved. | 2025-06-02 | 2025-07-08 | All Materils Inhoused.
60 | F25 | NAPAPIJRI | 2025-02-27 | YUPIK FZH 3 |  |  | CO | 16055 | RS-8 | 16055 | 0 | Approved. | 2025-06-02 | 2025-07-08 | All Materils Inhoused. | [7 empty] | 2025-05-09
61 | F25 | NAPAPIJRI | 2025-02-27 | YUPIK W 2.0 1 |  |  |  | 2008 | SF-8 | 2008 | 0 | Approved. | 2025-06-02 | 2025-07-08 | [8 empty] | 2025-05-14
62 | F25 | NAPAPIJRI | 2025-03-12 | YUPIK FZH 3 |  | Approved. | CO | 2001 | RS-8 | 2001 | 0 | Approved. | 2025-06-19 | 2025-07-29 | Inhoused. | [6 empty] | Furui-Surcharge under MOQ $150 on POLAR RAIN SOLID(118172) REC for the col. Tea Leaf
63 | F25 | NAPAPIJRI | 2025-03-12 | A-BIOIS |  | Approved. | Buy CO | 2532 | Rs-9 | 2532 | 0 | Approved. | 2025-07-05 | 2025-08-19 | Inhoused,HUAMO; 5/29 ETA > 74 Roll. | [6 empty] | Hua Mao-Surcharge under MOQ $2100 on LONELY SHELL REC for the col Night Sky, Black Beauty& Tea Leaf. GRID SHELL 3L REC for the clo Tea Leaf of the style A BIOIS | 2025-05-14
64 | F25 | NAPAPIJRI | 2025-03-12 | T-ANSEI FZ W |  | Approved. | New | 2194 | RS-5 | 2194 | 0 | Approved. | 2025-06-04 | 2025-07-08 | Inhoused. | [6 empty] | Nice Gain-Surcharge under MOQ $600 on MICRO CURLY REC(117608) for the color Night Sky, Black Beauty & Turtledove. Jong Stit Surcharge under MOQ $737 on the UNIQUE FLEECE REC for the col Night Sky, Black Beauty & Turtledove.
65 | F25 | NAPAPIJRI | 2025-03-12 | T-FIEMME |  | Approved. | Buy CO | 4204 | RS-7 | 4204 | 0 | Approved. | 2025-06-04 | 2025-07-08 | Inoused. | [6 empty] | Wu Luen-Surcharge under MOQ $800 on Lycra Fabric M930 for the color Beige Dimity, Black Beauty, Pussywillow Gray, Brunt Orange Jibo surcharge under MOQ $120 on Lining 210T for the col Black Beauty | 2025-05-26
|  |  |  | Total |  |  | Still Mar-1 Buy PO Qty. | 263376 |  | 263467 | 0
|  |  | F25 Projection | 246444
|  |  | Still Feb-2 Buy Recevied | 263376
|  |  | NAPA F25 | BULK SUMMARY: 7/20
|  |  | Total TNA | 65 | Running Style: 2
|  |  | Total PO Qty. | 263376
|  |  | Total Production | 263467 | TNA Closed: 63
|  |  | Total Shipment | 174920
|  |  | Ready to ship | 88547 | Closing Report Rec. 3
|  |  | Production Balance | -91 | Closing Report Bal. 60
|  |  | TNA Balance: | 2
EID HOLIDAY-2025 (ESTIMATED)
Eid Start Day |  |  | End Day | Total Day
2025-03-30 |  |  | 2025-04-08 | 9
2025-06-06 |  |  | 2025-06-16 | 10
Formulas:
TNA = [CRD]-31
Note on I15: Author: 3817 Pcs 4/29 CRD
Note on N24: Apurbo: TNA Need to Revise Fabric mill Delivery. Extention.
Note on O26: Author: CRD Extended 1 wk
Note on O27: Author: CRD Extended 1 wK
Note on O29: Author: 1 WK CRD Extention approved.
Note on N42: Author: Eid-Ul Adha- 10 days LT added

## TBL F25
Brand: Timberland Season: FW25
SL | Season | Buyer | Buy Date | Style | Application | Item | Style Details | PPS/HO Status 7/27 | O/Qty | Sewing Line | Production St 7/27 | Balance | Materials Status. 7/20 | E.TNA | Style 1st CRD | Merchandising Update 7/17 | Input Plan | Finished date. | Closing Report Date | TNA Connecting & Materils Comments. 5/14 | Remarks | Trims Status. 5/14 | Issue | Solution | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | F25 | TIMBELAND | 2025-03-05 | TB0A22XM | OC Buy | Mens Waterproof Down Vest | D. BUY CO | Approved.; SS file HO 5/5 | 2000 |  |  | 2000 |  | 2025-05-25 | 2025-08-05 |  | CONNECTING
2 | F25 | TIMBELAND | 2025-02-20 | TB0A6VSJ |  |  | Buy CO | Buy CO; Approved. | 2000 |  |  | 2000 |  | 2025-06-25 | 2025-08-01 |  | RS-12; 7/21
3 | F25 | TIMBELAND | 2025-02-20 | TB0A2QE8 |  |  | New | Approved | 2626 |  |  | 2626 |  | 2025-07-15 | 2025-08-24 |  | LF-9; 7/26
4 | F25 | TIMBELAND | 2025-03-21 | TB0A6NGF |  |  |  | Approved | 4409 |  |  | 4409 |  | 2025-06-30 | 2025-08-04 |  | LY-6; 7/8
5 | F25 | TIMBELAND | 2025-02-20 | TB0A6NF7 | A6NF7- PEACOAT COLOR NEED TO SEND FOR SPRY TEST FAIL. NEED TO COLLECT SDMAPEL FIRM BULK TO SEND WITHIN 7/30; crd 8/24 |  | New | Approved | 1181 |  |  | 1181 |  | 2025-07-05 | 2025-08-04 |  | SF-11; 7/01
6 | F25 | TIMBELAND | 2025-01-23 | TB0A44A1 | Embo | Mens Down Jkt | New | Approved, HO Done. | 8104 | SF-2 | 8104 | 0 | Inhoused | 2025-05-05 | 2025-06-12 |  | SF-8; 5/31 |  | Yet to | 7924 Pcs Buyer Req. CRD 6/12, but Should 7/8 without GR LT 70 Days. Need to Check with Mill if Availabe GR in this style to mmet as buyer req. CRD.
7 | F25 | TIMBELAND | 2025-02-20 | TB0A44A1 | Embo | Mens Down Jkt | Buy CO | Approved, HO Done. | 2306 | SF-2 | 2306 | 0 | Need Materils Status. | 2025-05-25 | 2025-07-01 |  | CONNECTING |  | Yet to
8 | F25 | TIMBELAND | 2025-01-23 | TB0A5UVW | Embo 1x1 | Seam Sealing WR Jacket | N. BUY CO | Approved CO | 2000 | RS-3 | 2000 | 0 |  | 2025-06-15 | 2025-07-15 |  | RS-12; 7/2 + Sty. 44BF+ Mar buy |  | Yet to | if Possible to inhouse fabric by 5/5 to make TNA Connecting with Nov. buy.
9 | F25 | TIMBELAND | 2025-03-21 | TB0A5UVW |  |  | Buy CO | Approved. | 1213 | RS-3 |  | 1213 |  | 2025-06-25 | 2025-08-23 |  | Jan buy RS-12; 7/2 + Sty. 44BF+ Mar buy CONNECTING
10 | F25 | TIMBELAND | 2025-03-21 | TB0A6N4K | Embo |  | Buy CO | Buy CO; Approved. | 2743 | RS-11 | 230 | 2513 | Connecting Issue need cut 7/10 otherwise dis-connect.LTZE Plastic Snap Button- safari color. Will be inhsed 7/22. Must need. | 2025-07-20 | 2025-08-24 |  | CONNECTING
11 | F25 | TIMBELAND | 2025-01-23 | TB0A6927-REAL DOWN | Embo 1x2 | Mens Water Proof 3in1 Seam selaing Bomber | Season CO Shell Fabric Change. | Approved | 2229 | SF-12 | 910 | 1319 |  | 2025-06-15 | 2025-07-20 | Embo thead color Whet boot Cost to Madira. | SF-13; 6/22 |  | 2 Days Late Handover issue.
12 | F25 | TIMBELAND | 2024-12-20 | TB0A62N7 | Embo | Smart Temp Pant | CO Styling and Materils, add in Sketh. New Color Added | Approved | 3269 | SF-14 | 3269 | 0 | Delivery delay - Air PP req. Shinton | 2025-04-20 | 2025-06-10 |  | SF-1; 5/25 |  | Yet to |  |  | All Inhoused
13 | F25 | TIMBELAND | 2024-12-20 | TB0A42C1 | Embo | Mem's Reversable Jkt | New | Approved | 3465 | Br-2 | 3465 | 0 | Farestan. Delivery delay -72 Roll 4/13 ETA. | 2025-04-25 | 2025-05-27 |  | RS-11; 5/10 | 2025-05-26 | Yet to |  |  | All Inhoused
14 | F25 | TIMBELAND | 2025-01-23 | TB0A6477 | Emb 1x3 | 3in1 Jacket | D. BUY CO | Approved, SS HO DONE. | 3279 | LS-8 | 3279 | 0 | Inhoused | 2025-05-03 | 2025-06-12 |  | LS 11; 5/17 | 2025-05-30 | Yet to | Connecting with Dec+ JAN
15 | F25 | TIMBELAND | 2025-01-23 | TB0A22XM | Embo 1x2 | Mens Waterproof Down Vest | D. BUY CO | Approved.; SS file HO 5/5 | 2887 | SF-7 | 2887 | 0 |  | 2025-05-06 | 2025-06-12 |  | CONNECTING |  | Yet to | Need to Check if Greige booking if availabel to meet buyer req. CRD
16 | F25 | TIMBELAND | 2025-01-23 | TB0A22XB | Embo 1x2 | Mens Down Jkt | New | Approved.; SS file HO 5/5 | 2264 | Cutting Running. | 2264 | 0 | Materials Status. 5/5. | 2025-05-07 | 2025-06-12 |  | LY-7; 5/12 |  | Yet to | 736 Pcs. Buy Report has mention Without GR- Need to Collet all goods with GR to make single TNA. Or CDR Should Extened by 6/27
17 | F25 | TIMBELAND | 2025-02-20 | TB0A5N46 |  | Mens Padding Coach Jkt | Buy CO | Approved | 826 |  | 826 | 0 |  | 2025-05-07 | 2025-07-06 |  |  |  | Yet to
18 | F25 | TIMBELAND | 2024-12-20 | TB0A44HB | N/A | Wool Blend Shacket | J. BUY CO | Approved, HO Done. | 2383 | SF-8 | 2383 | 0 | All Inhoused. | 2025-05-08 | 2025-06-10 |  | SF-5, 5/19 |  | Yet to | Connecting with Dec+ JAN |  | All Inhoused
19 | F25 | TIMBELAND | 2024-12-20 | TB0A22XM | Embo omn chesrt+ BK Yoke | Mens Waterproof Down Vest | New | Approved.; SS file HO 5/5 | 5157 | SF-7 | 5157 | 0 |  | 2025-05-08 | 2025-06-18 |  | SF-2; 5/17- CONNICTING ALL BUY |  | Yet to |  |  | All Inhoused
20 | F25 | TIMBELAND | 2024-12-20 | TB0A6BPM | Embo | Seam Sealing Shell Jkt | New | Approved, SS HO 5/5 | 6194 | SF-13 | 6194 | 0 | All Inhoused. | 2025-05-10 | 2025-06-16 | GB SEAM SLEPAGFE FIAL- NEED TO PULL FROM BULK TO SEND 5/30., CRD 6/22. | SF13; 5/22 |  | Yet to |  |  | All Inhoused
21 | F25 | TIMBELAND | 2025-02-20 | TB0A44P6 |  |  | Buy CO | Approved | 2786 | RS-1 | 2786 | 0 |  | 2025-05-15 | 2025-06-16 | Connecting. | CONNECTING |  | Yet to
22 | F25 | TIMBELAND | 2025-02-20 | TB0A22XB |  |  | Buy CO | Approved; SS done. | 3332 | Cutting Running. | 3332 | 0 | Need Materils Status. | 2025-05-21 | 2025-06-21 |  | CONNECTING |  | Yet to
23 | F25 | TIMBELAND | 2025-02-20 | TB0A22W2 |  |  | Season CO | Approved- CO | 1500 | LY-12 | 1500 | 0 | Need Materils Status. | 2025-05-31 | 2025-06-26 | 1 Ctn; ETA 5/11; Will be inhoused 5/21 | CONNECTING, If Dec buy Input 5/19. |  | Yet to
24 | F25 | TIMBELAND | 2025-01-23 | TB0A44UA | Embo | Mens Bomber Jkt | Season CO | Approved, SS HO 5/6 | 4212 | LY-2 | 4212 | 0 |  | 2025-05-12 | 2025-06-22 | Seam sealing ( Hydrostic Tst Fail) 3 pcs send to DTC Lab, Working for Improved sample. | SF-9; 5/27 |  | Yet to
25 | F25 | TIMBELAND | 2025-01-23 | TB0A62CF | Embo | Mens seam sealing Down Bomber | D. BUY CO | Approved | 2592 | LS-12 | 2592 | 0 | Inhoused | 2025-05-07 | 2025-06-10 |  | LS 12; 5/17 |  | Yet to
26 | F25 | TIMBELAND | 2025-01-23 | TB0A6267 | Embo | Mens Down Jkt. | D. BUY CO | Approved | 11196 | RS-2 | 11196 | 0 | EX- FTY 4/7; ETD 4/15 | 2025-05-10 | 2025-06-17 |  | CONNECTING |  | Yet to
27 | F25 | TIMBELAND | 2024-12-20 | TB0A6477 | Emb 1x3 | 3in1 Jacket | J. BUY CO | Approved, SS HO DONE. | 2289 | LS-11 | 2289 | 0 | Inhoused | 2025-05-10 | 2025-06-17 |  | LS 11; 5/11 | OK | Yet to |  |  | All Inhoused
28 | F25 | TIMBELAND | 2024-12-20 | TB0A2QPD- WAAP | Embo | Womens Short Parka | New | Approved. | 4913 | SF4 | 4913 | 0 |  | 2025-05-10 | 2025-06-16 |  | SF-4; 5/10 |  | Yet to |  |  | All Inhoused
29 | F25 | TIMBELAND | 2025-01-23 | TB0A655U | N/A | Mens Down Vest | Season CO | Approved. | 3055 | LY-1 | 3055 | 0 | Need Materils Status. | 2025-05-15 | 2025-06-17 |  | LS-10; 5/29 | 2025-06-01 | Yet to
30 | F25 | TIMBELAND | 2024-12-20 | TB0A2QZ3-WAAP | Embo | Wonm Padding Jkt( Inhouse Quilting) | New | Approved | 2012 | SF-13 | 2012 | 0 | 141 Bale ETA 3/28; 315 Bl, Inhoused. | 2025-04-20 | 2025-05-27 |  | BR-1; 5/15 |  | Yet to |  |  | All Inhoused
31 | F25 | TIMBELAND | 2024-12-20 | TB0A2QS6- WAAP | EYK- 46 Add request. | Wonm Padding Jkt( DPQSL Quilting) | New | Approved | 3300 | RS-10 | 3300 | 0 | 141 Bale ETA 3/28 | 2025-04-20 | 2025-05-27 |  | RS-10; 5/17 |  | Yet to |  |  | All Inhoused
32 | F25 | TIMBELAND | 2025-01-23 | TB0A2P9F- COLLAB | Embo | Mens Fleece Lining Jkt | New | Approved. | 500 | Br-2 | 500 | 0 |  | 2025-05-24 | 6/24/2025( Air Collect) VF |  | BR-4; 5/31 |  | Yet to
33 | F25 | TIMBELAND | 2024-11-22 | TB0A68CB | EMBO on Slv, Seam sealing | Mens Jkt. | CO Styling and Materils, Adding Story telling and Icon Label, Call Out Lebel- Need to add in Sketh. New Color Added | Approved. | 5723 | Ly-2 | 5723 | 0 | Fabric + Trims; All Inhoused. | 2025-02-20 | 2025-04-08 | Sewing completed | 2025-02-28 | 2025-03-12 | Yet to | ETA: 2/2 Wuluen | 1050 pcs CRD Before eid Cut off 3/21 | All Inhoused
34 | F25 | TIMBELAND | 2024-11-22 | TB0A44PP | EMBO on SLV, Seam sealing all over | Mens Waterproof Parka | Carry Over Styling and Materils, Adding Story telling and Icon Label. | Approved. | 1109 | SF-6 | 1109 | 0 | Fabric + Trims; All Inhoused. | 2025-02-25 | 2025-04-08 | Sewing completed | OK | 2025-04-09 | Yet to |  | CRD 4/8 255 Pcs 4/15, 222 Pcs balance Qty. till June. | All Inhoused
35 | F25 | TIMBELAND | 2024-11-22 | TB0A6HNY- Wash | EMB on Chest, GARMENT WASH 15 MIN. Sewing Treat Constast. | Mens Padeding Hooded Bomber | New | Approved. | 3990 | RS-1 | 3990 | 0 | Fabric + Trims; All Inhoused. | 2025-02-25 | 2025-04-15 | Sewing completed | 2025-02-27 | 2025-03-12 | Yet to | Connecting with Dec. Buy |  | All Inhoused
36 | F25 | TIMBELAND | 2024-11-22 | TB0A62CF | EMBO on Chest, Critical Seam sealing | Mens Padding Jkt | C/O Styling and Materils. New Color Added | Approved. | 13113 | LS-10 | 13113 | 0 | Fabric + Trims; All Inhoused. | 2025-02-25 | 2025-04-08 | Sewing completed | 2025-03-08 | 2025-04-14 | Yet to |  | 548 CRD before eid cut off 3/21 | All Inhoused | WAI HING RIB ISSUE; SEA ETD 2/17, AIR ??
37 | F25 | TIMBELAND | 2024-11-22 | TB0A6VRX | Print on chest, In Houose Quilting | Mens Padding Jkt | New- PPS Req. Given | Approved. | 3669 | RS:12 | 3669 | 0 | Fabric + Trims; All Inhoused. | 2025-03-01 | 2025-04-08 | Sewing completed | 2025-03-03 | 2025-03-16 | Yet to |  |  | All Inhoused
38 | F25 | TIMBELAND | 2024-11-22 | TB0A6HQU | Silicon Badge Synthetic Insulated Puffer, Inhouse Quilting | Mens Donw Jacket | New- PPS Req. Given | Approved. | 3857 | RS-1 | 3857 | 0 | Fabric + Trims; All Inhoused. | 2025-03-05 | 2025-04-15 | Sewing completed | 2025-03-12 | 2025-04-09 | Yet to |  | This is Same as A6HQ7 | All Inhoused | POLY WRONG MEASUR BOOKING FUND 3/25. Need Revise Booking FIRE URGENT.
39 | F25 | TIMBELAND | 2024-11-22 | TB0A6VUE | EMBO on Chest. Seam Sealing | Mens Bomber Jkt | New, A44UA AF( F24) OF A6VUE GF. | Approved. | 5660 | SF-3 | 5660 | 0 | Fabric + Trims; All Inhoused. | 2025-03-05 | 2025-04-15 | Sewing completed | OK | 2025-04-09 | Yet to |  |  | All Inhoused | WAI HING RIB ISSUE; SEA ETD 2/17 AIR ?? | Issue Soved by twic payemnt Air Collect.
40 | F25 | TIMBELAND | 2024-11-22 | TB0A6HQ7 | Silicon Badge Synthetic Insulated Puffer, Inhouse Quilting | Mens Down Vest. | New- PPS Req. Given | Approved. | 2209 | RS-1 | 2209 | 0 | Fabric + Trims; All Inhoused. | 2025-03-05 | 2025-04-15 | Sewing completed | 2025-04-10 |  | Yet to |  |  | All Inhoused
41 | F25 | TIMBELAND | 2024-11-22 | TB0A5UVW | EMBO on Chest, Seam sealing, Quilting Inhouse. | Mens Padding Jkt | C/O Styling and Materils. New Color Added | Approved. | 3867 | RS-11 | 3867 | 0 | Fabric + Trims; All Inhoused. | 2025-03-10 | 2025-05-10 | Sewing completed | OK | 2025-03-20 | Yet to |  |  | All Inhoused
42 | F25 | TIMBELAND | 2024-11-22 | TB0A5WNU | Print -4 // In House Quilting | Mens Down Jkt( Packable) | New- PPS Req. Given | Approved. | 12026 | RS-12 | 12026 | 0 | Fabric + Trims; All Inhoused. | 2025-03-10 | 2025-05-10 |  | 2025-03-24 |  | Yet to |  |  | All Inhoused
43 | F25 | TIMBELAND | 2024-11-22 | TB0A5WPF | Print -4 // In House Quilting | Mens Down Vest ( Packable) | New- PPS Req. Given | Approved. | 5853 | RS-4 | 5853 | 0 | Fabric + Trims; All Inhoused. | 2025-03-10 | 2025-05-10 | Sewing Running. | 2025-04-22 |  | Yet to | Connecting plan with Jan Buy. | This vest style same as A5WNU | All Inhoused
44 | F25 | TIMBELAND | 2024-12-20 | TB0A44PP | EMBO on SLV, Seam sealing all over | Mens Waterproof Parka | N. BUY CO | Approved. | 1000 | Connecting plan | 1000 | 0 | Fabric + Trims; All Inhoused. | 2025-03-15 | 2025-05-13 | Sewing completed | OK | 2025-04-09 | Yet to | Need to bring fabric by air to connect (3600 Yds) |  | All Inhoused
45 | F25 | TIMBELAND | 2024-11-22 | TB0A6VSJ | Print on chest, In Houose Quilting | Mens Padding Vest | New- | Approved. | 7848 | RS-12 | 7848 | 0 | Fabric + Trims; All Inhoused. | 2025-03-18 | 2025-04-23 | Sewing completed | 2025-03-15 | 2025-04-17 | Yet to |  | this is same as A6VRX/487 CRD first CRD on 4/17 | All Inhoused
46 | F25 | TIMBELAND | 2024-11-22 | TB0A5UVW | EMBO on Chest, Seam sealing, Quilting Inhouse. | Mens Padding Jkt | C/O Styling and Materils. New Color Added | Approved. | 3317 | RS-11 | 3317 | 0 | Fabric + Trims; All Inhoused. | 2025-03-20 | 2025-05-10 | Sewing Running. | 2025-04-12 |  | Yet to |  |  | All Inhoused
47 | F25 | TIMBELAND | 2024-11-22 | TB0A6VRX | Print on chest, In Houose Quilting | Mens Padding Jkt | New- PPS Req. Given | Approved. | 3541 | RS:12 | 3541 | 0 | Fabric + Trims; All Inhoused. | 2025-03-20 | 2025-05-07 | Sewing completed | 2025-04-16 | 2025-04-23 | Yet to |  | 218 Pcs first CRD on 4/17 | All Inhoused
48 | F25 | TIMBELAND | 2024-12-20 | TB0A2QCS | Embo | Mens Pant | New | Approved | 6402 | SF-8 | 6402 | 0 | Fabric 18 Roll, ETA 3/22; 175 Roll ETA 3/9. 123 Roll Trycode. 4/4. Will inhoused 4/10- Black color 1st priority. | 2025-04-10 | 2025-05-10 | Sewing Running. TW, Sticker Dely. QCC Tag DK Sipphir Col. + Poly Balance. | 2025-04-16 |  | Yet to | 300 pcs First CRD 5/10, Balance 5/25 |  | All Inhoused
49 | F25 | TIMBELAND | 2024-12-20 | TB0A6HNY- Wash | EMB on Chest, GARMENT WASH 15 MIN. Sewing Treat Constast. | Mens Padeding Hooded Bomber | N. BUY CO | Approved | 4443 | RS-9 | 4443 | 0 | Fabric All Inhoused. | 2025-04-10 | 2025-05-13 | Sewing Running. | 2025-04-10 |  | Yet to | Connecting with Nov. Buy |  | All Inhoused
50 | F25 | TIMBELAND | 2024-12-20 | TB0A6HQU | Silicon Badge Synthetic Insulated Puffer, Inhouse Quilting | Mens Donw Jacket | N. BUY CO | Approved | 2841 | RS-1 | 2841 | 0 | Fabric All Inhoused. | 2025-04-10 | 2025-05-14 |  | RS-1- RUNNING |  | Yet to | Connecting with Nov. Buy, 3/22 ETA. |  | All Inhoused | Need to use Coasts EPIC i/o Asta.
51 | F25 | TIMBELAND | 2024-12-20 | TB0A5N46 | Embo | Mens Padding Coach Jkt | New | Approved | 10458 | SF-14 | 10458 | 0 | Fabric Inhoused. | 2025-04-10 | 2025-05-20 | GB Test Fail - Seam sleppage_ Fail. Send 5/29 Yet to ack - need strong fllow up. | SF-14; 5/3 |  | Yet to |  |  | All Inhoused
52 | F25 | TIMBELAND | 2024-12-20 | TB0A5WNU | Print -4 // In House Quilting | Mens Down Jkt( Packable) | N. BUY CO | Approved | 2374 | RS-4 | 2374 | 0 | 124 Roll, ETA.4/1; 123 Roll ETA 4/04 Will be 4/12 | 2025-04-13 | 2025-05-13 |  | RS-4 RUNNING 4/22 |  | Yet to | Connecting with Nov. Buy |  | All Inhoused
53 | F25 | TIMBELAND | 2024-12-20 | TB0A28EG | N/A | Mens QUICK-DRY STRETCH CARGO SHORTS | New | Approved | 6020 | SF-14 | 6020 | 0 | 175 Roll; ETA: 3/28; Inhoused | 2025-04-15 | 2025-05-17 |  | SF-3: 5/6 | 2025-05-19 | Yet to |  |  | All Inhoused
54 | F25 | TIMBELAND | 2024-12-20 | TB0A2R5M | Embo | 3in 1 - Seam sealing Jckt | New | Approved | 4133 | LY-9 | 4133 | 0 | 179 Roll; ETA 3/31, 229 Roll ETA: 3/24: Will Inhose soon. | 2025-04-15 | 2025-05-20 |  | Outer/ LS: 08 4/26; & Iner LY: 09 5/3. | 2025-05-20 | Yet to | 491 Pcs first CRD 5/13, Balance qty 5/20 and onwards |  | All Inhoused
55 | F25 | TIMBELAND | 2024-12-20 | TB0A6267 | Embo | Mens Down Jkt. | J. BUY CO | Approved | 4944 | RS-2 | 4944 | 0 | 123 Roll: ETA 4/4: Will be inhoused 4/10 | 2025-04-15 | 2025-05-20 |  | LS-4, 4/24 & RS-2, 5/3 | OK | Yet to |  |  | All Inhoused
56 | F25 | TIMBELAND | 2024-11-22 | TB0A62WB-WAAP | Print on Chest, Inhoused Quilting. | Won Down Jkt | C/O Styling and Materils. New Color Added | Approved. | 5107 | SF-2 | 5107 | 0 | Fabric + Trims; All Inhoused. | 2025-03-05 | 2025-05-05 | Sewing completed | 2025-03-10 | 2025-04-15 | Yet to | Need input 2/26 |  | All Inhoused
57 | F25 | TIMBELAND | 2024-11-22 | TB0A6137- WAAP | Print on Slv, In House Quilting | Wom Down Jkt | C/O Styling and Materils. New Color Added | Approved. | 4242 | SF-2 | 4242 | 0 | Fabric + Trims; All Inhoused. | 2025-03-10 | 2025-05-05 | Sewing Running. | 2025-04-21 |  | Yet to |  |  | All Inhoused
58 | F25 | TIMBELAND | 2024-12-20 | TB0A2PE2- Wash 15 mn gmt | Embo | Mens Pant -Washed Duck Canvas | New | Approved. | 2080 | LY-13 | 2080 | 0 | Fabric + Trims; All Inhoused. | 2025-03-15 | 2025-04-22 | Sewing completed | 2025-04-16 | 2025-04-20 | Yet to | Z&Z BD Mill | EH2 146 Pcs Late ass req. Rejected. | All Inhoused
59 | F25 | TIMBELAND | 2024-12-20 | TB0A6HPK- Wash 15 Min Gmt | Embo | Water Resistant Shell Seam sealing Jacket | New | Approved. | 2002 | SF-7 | 2002 | 0 | Fabric + Trims; All Inhoused. | 2025-03-15 | 2025-04-22 | Sewing completed | 2025-04-12 |  | Yet to | Z&Z BD Mill | MNXL Item Fabric Consumption has been save 0.25Y/Pcs Due to Measurment Changed. | All Inhoused
60 | F25 | TIMBELAND | 2024-11-22 | TB0A2KPB- WAAP | Print on Chest// In House Quilting | Wom Padding Jkt | D. BUY CO | Approved. | 3022 | SF-2 | 3022 | 0 | Fabric + Trims; All Inhoused. | 2025-03-25 | 2025-05-05 | Sewing completed | OK |  | Yet to |  |  | All Inhoused
61 | F25 | TIMBELAND | 2024-12-20 | TB0A428B- WAAP | Embo | Full Seal sealing Wom inline Parka | New | Approved | 2814 | LS-10 | 2814 | 0 | 99 Roll, ETA 3/17 | 2025-04-10 | 2025-05-06 |  | LS; 10; 4/23 | Wrong pattern 233 pcs po short- need ship by 6/10. buyer impose air PP | Yet to | 598 CRD 6 May, Balance qty 5/17 | 598 Pcs PO buyer suggest to consider Greige Booking to meet the CRD- need to re work with Mill to improved delivery , next CRD 5/17 | All Inhoused
62 | F25 | TIMBELAND | 2024-12-20 | TB0A429N- WAAP | Embo | Mens Shell Seam sealing Jacket | S.CO Styling and Materils, add in Sketh. New Color Added | Approved | 2558 | LY-2 | 2558 | 0 | 99 Roll, ETA 3/17 | 2025-04-10 | 2025-05-06 |  | LY: 2; 4/24 |  | Yet to | 821 pcs CRD on 6 May and balance 5/20 | 801 pcs PO Under Buyer View 6th May to 5/13 CRD. buyer advice to improve delivery considering greige booking. | All Inhoused
63 | F25 | TIMBELAND | 2024-12-20 | TB0A5ZEK | Quilting (Inhouse) | Wom Padding JKt | New | Approved | 601 | Br-2 | 601 | 0 | 99 Roll, ETA 3/17; 123 Roll Trycode. 4/4. Will inhoused 4/10 | 2025-04-15 | 2025-05-13 |  | BR: 4/23 |  | Yet to | 1st NTB was B" Buy Pr A'' |  | All Inhoused
64 | F25 | TIMBELAND | 2024-12-20 | TB0A2KPB-WAAP | Print on Chest// In House Quilting | Wom Padding Jkt( Inhouse Quilting) | N. BUY CO | Approved | 3105 | SF-2 | 3105 | 0 | ETA: 4/1, 123 Roll ETA 4/4: will be inhoused 4/12 | 2025-04-25 | 2025-05-27 |  | 2025-04-09 | OK | Yet to | Need to consider Connecting with Nov. Buy | 2553 Pcs PO Under buyer View> Need to work with Fabric mill To Improve delivery by using Greige booked to get delivery 2/23 to meet 5/6 CRD. | All Inhoused
65 | F25 | TIMBELAND | 2025-02-20 | TB0A2PE2 | Embo | Mens Pant -Washed Duck Canvas | New | Approved. | 927 |  | 927 | 0 |  | 2025-05-05 | 2025-05-30 | Sewing completed | 2025-04-07 | 2025-04-15 | Yet to
66 | F25 | TIMBELAND | 2025-02-20 | TB0A6VRA |  |  | New | Approved; SS done. | 2388 | SF-3 | 2388 | 0 | All Inhoused. | 2025-05-07 | 2025-06-16 | 254 Roll, ETA 4/22; BL: SFSZ2504109 | SF-7; 5/20 |  | Yet to | Need TNA revise 5/16.
67 | F25 | TIMBELAND | 2025-02-20 | TB0A5WPF |  |  | Buy CO | Approved | 600 | Br-2 | 600 | 0 |  | 2025-05-17 | 2025-07-01 |  | RS-4 RUNNING 4/22 |  | Yet to
68 | F25 | TIMBELAND | 2025-02-20 | TB0A69F2 |  |  | New | Approved | 9545 | LS-12 | 9545 | 0 |  | 2025-05-20 | 2025-07-07 |  | OUT / RS: 07& LS-4 , 5/31; & Iner-LS: 05, 6/3. |  | Yet to
69 | F25 | TIMBELAND | 2024-12-20 | TB0A44QU | Embo | Mens Padding Seam sealing Jkt | New | Approved, SS HO 5/5 | 2001 | Connecting plan | 2001 | 0 | All Inhoused. | 2025-05-08 | 2025-06-17 |  | LS-7; 5/14 |  | Yet to |  |  | All Inhoused
70 | F25 | TIMBELAND | 2024-12-20 | TB0A44GB | Embo 1x2 | Seam Sealing- Waterproof Barn Coat | J. BUY CO | Approved. SS OH. | 9340 | RS-3 | 9340 | 0 | All Inhoused. | 2025-05-10 | 2025-06-17 |  | RS-9; 5/8 |  | Yet to | Size set req. 4/26 |  | All Inhoused
71 | F25 | TIMBELAND | 2025-02-20 | TB0A6267 |  |  | Buy CO | Approved | 2250 | LS-4 | 2250 | 0 |  | 2025-05-27 | 2025-07-01 |  | CONNECTING |  | Yet to
72 | F25 | TIMBELAND | 2025-01-23 | TB0A44HB | N/A | Wool Blend Shacket | D.Buy CO | Approved, HO Done. | 2730 | SF-7 | 2730 | 0 | All Inhoused. | 2025-05-10 | 2025-06-16 |  | CONNECTING |  | Yet to | Connecting with Dec+ JAN
73 | F25 | TIMBELAND | 2025-02-20 | TB0A6HQ7 | Silicon Badge Synthetic Insulated Puffer, Inhouse Quilting | Mens Down Vest. | N Buy CO | Approved- CO | 3265 | RS-1 | 3265 | 0 | All Inhoused. | 2025-06-01 | 2025-07-11 |  | RS-1; 6/15 CONNECTING With A6HQU |  | Yet to
74 | F25 | TIMBELAND | 2025-01-23 | TB0A44GB | Embo 1x2 | Seam Sealing- Waterproof Barn Coat | D.Buy CO | Approved | 2334 | RS-11 | 2334 | 0 | Need Materils Status. | 2025-06-02 | 2025-07-21 |  | Since, Connecting Materils inhoused with Dec Buy, but not sewing dec buy together. |  | Yet to | Need to make connecting Plan with Dec buy.
75 | F25 | TIMBELAND | 2025-02-20 | TB0A6HNY | EMB on Chest, GARMENT WASH 15 MIN. Sewing Treat Constast. | Mens Padding Hooded Bom | Buy CO | Approved | 772 | Br-2 | 772 | 0 |  | 2025-05-05 | 2025-07-03 |  | BR-4; 6/23 |  | Yet to
76 | F25 | TIMBELAND | 2025-01-23 | TB0A6VUE | Embo | Mens seam sealing Bomber | Buy CO | Approved | 2117 | SF-6 | 2117 | 0 | All Inhoused. | 2025-05-13 | 2025-06-17 |  | SF-10; 5/24 |  | Yet to | Keep Connecting Plan with A44UA (AF)
77 | F25 | TIMBELAND | 2025-02-20 | TB0A68CB | EMBO on Slv, Seam sealing | Mens Jkt. | CO Styling and Materils, Adding Story telling and Icon Label, Call Out Lebel- Need to add in Sketh. New Color Added | Approved | 2267 | SF-6 | 2267 | 0 | Need Materils Status. | 2025-05-15 | 2025-06-16 |  | LY-12 5/20 |  | Yet to
78 | F25 | TIMBELAND | 2024-12-20 | TB0A6NG5 | Embo | Mens Waterproof 3in1 Seam sealing Jacket | New | Approved | 12443 | LS-11 | 12443 | 0 | All Inhoused. | 2025-05-15 | 2025-06-22 |  | INR: LS-8; 5/21 & OTR,LS-12. 5/11. |  | Yet to |  |  | All Inhoused
79 | F25 | TIMBELAND | 2025-01-23 | TB0A29PQ | Embo | Heavy Puffer Jacket | Season CO | Approved. | 4343 | LY-9 | 4343 | 0 | Need Materils Status. | 2025-05-25 | 2025-07-07 |  | LY-12; 5/30 |  | Yet to
80 | F25 | TIMBELAND | 2025-01-23 | TB0A2AZ3 | Embo | Heavy Puffer Vest | Season CO | Approved. | 3758 | LY-7 | 3758 | 0 | Inhoused. | 2025-05-31 | 2025-07-11 |  | LY-12; 6/25 |  | Yet to
81 | F25 | TIMBELAND | 2025-02-20 | TB0A6477 | Emb 1x3 | 3in1 Jacket | Buy CO | Approved | 2417 | LS-11 | 2417 | 0 |  | 2025-05-15 | 2025-06-21 |  | LS 11; 5/21 |  | Yet to
82 | F25 | TIMBELAND | 2024-12-20 | TB0A5M9T | Embo | Mens Padding Bomber | CO Styling and Materils, add in Sketh. New Color Added | Approved- CO: Need to make GB- need Req. 5/14. SS will HO Done. | 3835 | SF-10 | 3835 | 0 | Materils will be Inhoused 5/12. As per TNA OK | 2025-05-15 | 2025-06-22 |  | RS-11; 5/17 |  | Yet to |  |  | All Inhoused
83 | F25 | TIMBELAND | 2025-01-23 | TB0A69PU | Embo 1x2 | Mens Seam Sealing Shell Jacket | Season CO | Approved., CO- NEED TO MAKE GB, CRD 6/22; for new Color , Done. Production Running | 6105 | LY-7 | 6105 | 0 | Inhoused. | 2025-05-05 | 2025-06-09 |  | LY-13; 5/12 |  | Yet to
84 | F25 | TIMBELAND | 2024-12-20 | TB0A2R46-WAAP | Embo | Wom Real Down Jkt( Inhouse Quilting) | New | PPS Done. Approved. SS HO 5/5 | 2470 | LY-7 | 2470 | 0 | Inhoused- need to re- Check | 2025-05-10 | 2025-06-17 |  | LY: 1; 5/14 |  | Yet to | 60 Pcs Before Eid 5/26 CRD rest of June 17 to Aug. |  | All Inhoused
85 | F25 | TIMBELAND | 2025-01-23 | TB0A5WPF | Print | Mens Down Vest Packable. | D. BUY CO | Approved | 2001 | RS-4 | 2001 | 0 | ETD: 3/30 | 2025-04-30 | 2025-06-12 |  | CONNECTING-RS-4 RUNNING |  | Yet to | Need to connecting plan with Nov. buy. Buyer Req. CRD 6/12. Without GR LT 75 Days to Come CRD 7/10. need to check with mill if has availabe GR
86 | F25 | TIMBELAND | 2025-01-23 | TB0A5WNU | Print | Mens Down Jkt Packable. | D. BUY CO | Approved | 3087 | RS-4 | 3087 | 0 |  | 2025-05-03 | 2025-06-12 |  | RS-9 RUNNING- CONNING |  | Yet to | Connecting with Nov+ Dec + Jan 2006 Pcs CRD will be extention 6/28 from 6/12 without greige booking LT
87 | F25 | TIMBELAND | 2025-01-23 | TB0A44P6 | Embo | Waterproof Insulated Seam sealing Jacket | New | Approved. SS File HO Done. | 10666 | RS-1 | 10666 | 0 | Inhoused- need to re- Check | 2025-05-03 | 2025-06-12 | Still No Issue. | RS-14; 5/5 |  | Yet to
88 | F25 | TIMBELAND | 2025-01-23 | TB0A68XF | Embo 1x2 |  | New | Approved. | 9692 | RS-6 | 9692 | 0 | Product Name change Chinice Language. | 2025-05-05 | 2025-06-10 | Zipper Will be inhoused 5/4 | RS-5; 5/3 |  | Yet to
89 | F25 | TIMBELAND | 2025-01-23 | TB0A2QQW | Embo | Wom Waterproof seam sealing Down Parka | New | Approved | 2001 | LS-10 | 2001 | 0 | Inhoused- need to re- Check | 2025-05-07 | 2025-06-10 |  | LS-3; 5/12 |  | Yet to
90 | F25 | TIMBELAND | 2024-12-20 | TB0A5NGR | Embo | Waterproof Fleece Lined Seam Sealing Parka | New | Approved | 2002 | LS-10 | 2002 | 0 | 179 Roll; ETA 3/31, 229 Roll ETA: 3/24: Inhoused. | 2025-04-20 | 2025-05-20 |  | LS:10; 5/6 |  | Yet to |  |  | All Inhoused
91 | F25 | TIMBELAND | 2024-12-20 | TB0A22W2 | Embo omn chesrt+ BK Yoke | Mens Waterproof Down Parka | CO Styling and Materils, add in Sketh. New Color Added | Approved, New Color. | 3838 | Ly-12 | 3838 | 0 | 17( 163 Roll) Pakage - Inhoused.( Inventory & Ins Yet to!) | 2025-05-08 | 2025-06-17 | All Inhoused. | LY 5; 5/19 |  | Yet to |  |  | All Inhoused
92 | F25 | TIMBELAND | 2025-02-20 | TB0A62CF |  |  | Buy CO | Approved | 2002 | RS-1 | 2002 | 0 | Fabric 463 Roll; ETA 5/9 | 2025-05-20 | 2025-06-24 |  | LS 10; 5/20 |  | Yet to
93 | F25 | TIMBELAND | 2025-02-20 | TB0A6NHQ |  |  | New | Approved | 7227 | BR-3 | 185 | 7042 |  | 2025-06-25 | 2025-07-21 |  | LS-5; 7/12 |  |  | TNA Typo actual will be inhoused 6/17
94 | F25 | TIMBELAND | 2025-02-20 | TB0A6HQU | Silicon Badge Synthetic Insulated Puffer, Inhouse Quilting | Mens Donw Jacket | Buy CO | Approved | 2000 | Connecting Plan | 2000 | 0 |  | 2025-06-02 | 2025-07-02 |  | RS-1; 5/27 |  | Yet to
95 | F25 | TIMBELAND | 2025-02-20 | TB0A6A57 |  |  | New | Approved | 2504 | RS-1 | 255 | 2249 |  | 2025-06-21 | 2025-07-21 |  | RS-8; 7/9
96 | F25 | TIMBELAND | 2025-03-21 | TB0A69F2 |  |  | Buy CO | Buy CO; Approved. | 5366 | LS-8/LS5/LS11 | 540 | 4826 |  | 2025-06-21 | 2025-08-03 |  | CONNECTING
97 | F25 | TIMBELAND | 2025-02-20 | TB0A22W2 |  |  | Season CO | CO; Approved. | 1022 | LY-12 | 1022 | 0 |  | 2025-06-30 | 2025-07-22 | Fabric Air Collect to be inhouse 5/21 keep connecting sew. | CONNECTING |  | Yet to
98 | F25 | TIMBELAND | 2025-01-23 | TB0A44C3-REAL DOWN | Embo | Men's Vest. | New | Approved | 3640 | SF11 | 3640 | 0 |  | 2025-06-02 | 2025-07-07 |  | SF-11; 6/17 |  | Yet to
99 | F25 | TIMBELAND | 2025-01-23 | TB0A42FB-REAL DOWN | Print | Mens Down Puffer Jacket | New | Approved | 2840 | LS-9 | 2840 | 0 |  | 2025-06-15 | 2025-07-14 |  | LS-10; 6/15 |  | Yet to
100 | F25 | TIMBELAND | 2025-01-23 | TB0A44BF | Embo | Mens Padding Jkt | Season CO | Approved.S. CO; Need to Make GB, New Color Added. Req given | 1982 | RS-3 | 389 | 1593 |  | 2025-06-15 | 2025-07-21 |  | RS-12, 7/9
101 | F25 | TIMBELAND | 2024-12-20 | TB0A6N4K | Embo | Cotton Barn Seam Sealing Coat | New | Approved.. Campain sample CRD 4/29 | 4535 | RS-11 | 4535 | 0 |  | 2025-05-20 | 2025-06-30 |  | RS-9; 5/20 |  | Yet to |  |  | All Inhoused
[9 empty] | 388462 |  | 355491 | 32971
| Projection | 406670 |  | GB Test Challenge: CRD 8/03 A69F2 Umber Color Feb-Buy New Add Additional Color Test Sample Yer to send.
| Stll Jan Received | 388462 |  | A6NF7- PEACOAT COLOR NEED TO SEND FOR SPRY TEST FAIL. NEED TO COLLECT SDMAPEL FIRM BULK TO SEND WITHIN 7/30; crd 8/24
EID HOLIDAY-2025 (ESTIMATED)
Eid Start Day |  |  | End Day
2025-03-30 |  |  | 2025-04-07
2025-06-06 |  |  | 2025-06-14
TBL F25 | BULK SUMMARY: 7/20
Total TNA | 101 | Running
Total PO Qty. | 388462 | 7
Total Production | 355491 | 86
Total Shipment | 262979
Ready to ship | 92512
Production Balance | 32971
TNA Balance: | 15 | 7
CLOSING REPORT | 0 | 46
Formulas:
E.TNA = [Style 1st CRD]-40
Note on J22: Author: 1007 Pcs Drop in color TB0A6BPMEYO: 2/12 Materils Liablity $ 13242.05
Note on J28: Author: 85 pcs late add in black color- 60 pcs rejected 25 pcs accepted.

## TBL F24 Unship PO (hidden)
Season | CRD at Origin |  | PO | SHIP TERMS | PLATFORM | Style | Quantity | Customer | FOB | TotaL
F24 | 2025-01-26 | 6000767864 | 600076786400001 | FCA | INFO | TB0A5M9T001 | 61 | GMG SPORTS SEA PTE LTD (Philippines) | 26.52 | 1617.72
F24 | 2025-01-26 | 6000767864 | 600076786400002 | FCA | INFO | TB0A5M9T302 | 61 | GMG SPORTS SEA PTE LTD (Philippines) | 26.52 | 1617.72
F24 | 2025-01-26 | 6000778791 | 600077879100001 | FCA | INFO | TB0A5M5E001 | 41 | GMG SPORTS SEA PTE LTD (Philippines) | 26.52 | 1087.32
F24 | 2025-01-26 | 6000778791 | 600077879100002 | FCA | INFO | TB0A5M5EBK0 | 41 | GMG SPORTS SEA PTE LTD (Philippines) | 26.52 | 1087.32
F24 | 2025-01-26 | 6000778791 | 600077879100003 | FCA | INFO | TB0A68ZB302 | 30 | GMG SPORTS SEA PTE LTD (Philippines) | 50.35 | 1510.5
F24 | 2025-01-26 | 6000778791 | 600077879100004 | FCA | INFO | TB0A68ZB433 | 30 | GMG SPORTS SEA PTE LTD (Philippines) | 50.35 | 1510.5
F24 | 2025-01-26 | [8 empty] | 0
F24 | 2025-01-26 | 6000771590 | 600077159000001 | FCA | INFO | TB0A6XCTEFD | 44 | GMG SPORTS SEA PTE LTD (Philippines) | 23 | 1012
F24 | 2025-01-26 | 6000778788 | 600077878800001 | FCA | INFO | TB0A6Y7P433 | 34 | GMG SPORTS SEA PTE LTD (Philippines) | 15.08 | 512.72
F24 | 2025-01-26 | 6000778788 | 600077878800002 | FCA | INFO | TB0A6Y7PBK0 | 34 | GMG SPORTS SEA PTE LTD (Philippines) | 15.08 | 512.72
F24 | 2025-01-26 | 6000787110 | 600078711000001 | FCA | INFO | TB0A6Y8A302 | 34 | GMG SPORTS SEA PTE LTD (Philippines) | 18.46 | 627.64
F24 | 2025-01-26 | 6000787110 | 600078711000002 | FCA | INFO | TB0A6Y8A433 | 34 | GMG SPORTS SEA PTE LTD (Philippines) | 18.46 | 627.64
13723.8

## NAPA S25 (hidden)
Brand: NAPAPIJRI Season: SS25
SL | Season | Buyer | Buy Date | Style | PPS REQ Status: 12/25 | Size set Status- 11/05 | RQS DATA STATUS. 12/29 | MCD- Trim CARD. 11/05 | O/Qty | Production Sewing Line | Production Start | Total Production 12/29 | Balance | Upcomming Production Challenges : 12/29 | Emblishment | Size Set given | Long LT Mill:/ Cut Off | E.Final TNA | Vendor Last Revised CRD | POLY + CTN | PPS & Materials Issue: 10/29/2024 | TNA & CRD Comments | Costing File | Early Input Plan Start | Materials Upcharge | Remarks | Issue | Solution | SMV | CM | FOB | Total SMV | Total CM | Total FOB | A. CMP
1 | SS25 | NAPAPIJRI | 2024-07-25 | A-AMIATA | PASS | Given | ok | OK | 2212 | LS-7 |  | 2212 | 0 | Ok | Print | Done. | shin han-KR(FR) | 2024-10-05 | 2024-11-12 | NOT YET | PPS Running, Size set- plan to send 10/09. All Materils Inhoused. | TTL LT with GR 120 Days and without GR 175 Days | Relocation-3 |  | 0 | 1972460N: for color : MN6 CB MN6 & H62 ULTIMATE : MOQ / MCQ: 3000/ 1000 Yds |  |  | 58 | 9.2133 | 28.8982 | 128296 | 20379.8196 | 63922.8184
2 | SS25 | NAPAPIJRI | 2024-09-06 | A-AMIATA | PASS | Given | ok | OK | 1002 | BR-2 |  | 1002 | 0 | Ok |  | Done |  | 2025-01-01 | 2025-01-28 |  | EX- Mill 10th Dec. Materils Air Collect suport by VF. Unable to keep connecting with Jul buy TNA 10/28 for CRD 4th Dec. | [7 empty] | 58 | 6.2743 | 27.83 | 58116 | 6286.8486 | 27885.66
3 | SS25 | NAPAPIJRI | 2024-07-25 | A-AMIATA V | PASS | Given | ok | OK | 1609 | LS-7- Input 22th Oct. |  | 1609 | 0 | OK |  | PLAN/.10/24 | shin han-KR(FR) | 2024-10-28 | 2024-12-04 | NOT YET BOOKED. | Materials Sea Consider, Fabric inhoused. Size set will HO Today. |  | Relocation-3 | 2025-01-16 | 0 | No Materials UC |  |  | 46 | 11.2156 | 25.9071 | 74014 | 18045.9004 | 41684.5239
4 | SS25 | NAPAPIJRI | 2024-08-23 | A-BELLE V W | PASS | Given | ok | OK | 2038 | RS-6 | 2024-11-06 | 2038 | 0 | OK | DPQSL. Quilting | Plan 10/28 | Red House - TW( WE) & Wu luen ( Lining) TW(WE) | 2024-10-28 | 2024-12-03 |  | DQSL Quilting. RIB Balance- 10/28. DPQSL Quilting- will send today- 10/28, Need to size set Ho. 10/30. | [7 empty] | 41 | 6.1707 | 19 | 83558 | 12575.8866 | 38722
5 | SS25 | NAPAPIJRI | 2024-08-23 | A-BELLE W | PASS | Given | ok | OK | 1662 | RS-6 - Input plan 11/05 |  | 1662 | 0 | OK | DPQSL. Quilting | Plan 10/28 |  | 2024-10-28 | 2024-11-26 |  | DQSL Quilting. RIB Balance- 10/28. DPQSL Quilting- will send today- 10/28, Need to size set Ho. 10/30. | [7 empty] | 47 | 7.2746 | 24 | 78114 | 12090.3852 | 39888
6 | SS25 | NAPAPIJRI | 2024-08-23 | ACALMAR VEST 6 | PASS | Given | ok | OK | 1255 | LS- 13/B | 2024-11-10 | 1255 | 0 | OK |  | 2024-10-29 |  | 2024-11-05 | 2024-12-10 |  | Orang color 1 cm Gr. Tape- S/Emo. Balance- will be 10/31. PPS ruunig- Size wil be 11/02 | [7 empty] | 45 | 7.8593 | 19.03 | 56475 | 9863.4215 | 23882.65
7 | SS25 | NAPAPIJRI | 2024-07-25 | A-CLOUDY | PASS | Given | ok | OK | 1451 | Connecting. | 2024-11-04 | 1451 | 0 | Ok |  | Done. | Huamao- CN(MON/TH) Wu Luen( TW) WE | 2024-10-28 | 2024-12-04 |  | Typhon Affected. TNA, CRD being delay. Will be inhouse on-time | 4.costing on 20th Feb | 4.costing on 20th Feb |  | 400 | Lining fabric Dyeing surcharge-1951080N: MOQ/ MCQ 2000/ 800 Yds. Cons. .90 Yds |  |  | 54 | 7.4857 | 25.89 | 78354 | 10861.7507 | 37566.39
8 | SS25 | NAPAPIJRI | 2024-06-27 | A-CLOUDY | PASS | Given | ok | OK | 2369 | LY-13 | 2024-10-28 | 2369 | 0 | Ok | Print- Black color send to stabio on 8/18. need to follow up for approval Comment othesrs color will Apprved by VF ROPD: 2nd approval was to Satabio by 9/13. Need to follow up. | Done. |  | 2024-10-01 | 2024-11-19 | Inhoused. | Size set running- All Materils Inhoused. | [7 empty] | 54 | 6.8662 | 25.89 | 127926 | 16266.0278 | 61333.41
9 | SS25 | NAPAPIJRI | 2024-06-27 | A-COUBERTIN OPEN 2 | PASS | Given | ok | OK | 1502 | LS- 13 |  | 1502 | 0 | Ok | Print- Black color send to stabio on 8/18. need to follow up for approval Comment othesrs color will Apprved by VF ROPD: 2nd approval was to VF BD by 9/13. Need to follow up. | Done. |  | 2024-10-01 | 2024-11-12 |  | Size set will be 12 Oct. All Materials Inhoused. | [7 empty] | 44 | 7.3339 | 19.5 | 66088 | 11015.5178 | 29289
10 | SS25 | NAPAPIJRI | 2024-06-21 | ADA W | PASS | Given | ok | OK | 2304 | RS-09; Input Plan 11/05 | 2024-11-13 | 2304 | 0 | OK |  | Plan/.10/24- |  | 2024-10-26 | 2024-11-26 |  | Materials all inhoused. Size set plan 10/27. | [5 empty] | Inner Pkt 1 Pcs Zipper Won Sourch by YKK BD color developemnt has been going on. 7/14 |  | 44.5 | 9.2143 | 22.61 | 102528 | 21229.7472 | 52093.44
11 | SS25 | NAPAPIJRI | 2024-07-25 | A-ELSA W- Normal wash- CRD Being Challenges. | PASS | Given | ok | OK | 501 | BR:2 | 2024-11-06 | 501 | 0 | Ok | NA | Done. | Monotex KR(FR) | 2024-10-05 | 2024-11-12 |  | PPS Req given 10/6. Size set plan 10/29. |  | All Costing |  | 500 | sleeve lining Item: 1971940N: Square Apparels Ltd. Stil not Accept the Small Qty. Order |  |  | 75 | 30.9738 | 71.6686 | 37575 | 15517.8738 | 35905.9686
12 | SS25 | NAPAPIJRI | 2024-08-23 | A-GIOVI | PASS | Given | ok | OK | 6671 | PPS req. 10/15 | 2024-11-10 | 6671 | 0 | Ok | NA | Plan 10/31 |  | 2024-11-05 | 2024-12-10 |  | Lining ETA. 10/24. 25 roll/ 54 Roll. Shell Inhoused. Size set will be 10/28 | [7 empty] | 55 | 8.3202 | 20 | 366905 | 55504.0542 | 133420
13 | SS25 | NAPAPIJRI | 2024-07-25 | A-MELVILLE | PASS | Given | ok | OK | 2010 | LY-12 |  | 2010 | 0 | Ok | NA | Done. | Red House - TW( WE) | 2024-10-12 | 2024-11-12 |  | Typoon Affeted- ETD delay. | 4.costing on 20th Feb | Relocation-3 |  | 460 | 1959320N MONO MATERIAL SOFT SHELL 2L; MOQ/ MCQ: 3000/ 1000 Yds. |  |  | 48.5 | 10.2479 | 33.5 | 97485 | 20598.279 | 67335
14 | SS25 | NAPAPIJRI | 2024-04-25 | A-MELVILLE | PASS | Given | ok | OK | 1999 | LY-3 | 2024-08-12 | 1999 | 0 | Ok |  | Done. |  | 2024-07-09 | 2024-08-13 | Inhoused. | Remarks | 1 Days Improve bcz of Cut off alignment. |  |  | 111 | With GR |  |  | 48.5 | 7.5641 | 33.5 | 96951.5 | 15120.6359 | 66966.5
15 | SS25 | NAPAPIJRI | 2024-08-23 | A-MELVILLE | PASS | C/O | ok | OK | 1563 | SF-7 | 2024-11-19 | 1563 | 0 | OK |  | Done. |  | 2024-11-03 | 2024-12-10 |  | Red House. Shell; 74 Roll. ETA. 10/27- Zipper Quality issue. | [7 empty] | 48.5 | 9.0567 | 33.5 | 75805.5 | 14155.6221 | 52360.5
16 | SS25 | NAPAPIJRI | 2024-07-04 | A-MENTON W | PASS | Given | ok | OK | 448 | BR |  | 448 | 0 | Ok | Normal Wash | Done. |  | 2024-10-08 | 2024-11-12 | NOT YET | PPS Running, Size set- plan to send 10/12. All Materils Inhoused. - 1wk CRD Extention. | [5 empty] | Inner Pkt 1 Pcs Zipper Won Sourch by YKK BD color developemnt has been going on. 7/14 |  | 89 | 32.1343 | 87.42 | 39872 | 14396.1664 | 39164.16
17 | SS25 | NAPAPIJRI | 2024-06-21 | AMIS SUM STAND | PASS | Given | ok | OK | 2329 | SF-11- Input Plan : 10/18 | 2024-10-17 | 2329 | 0 | OK | Print | Done. |  | 2024-10-01 | 11/5/2024- 1155 Pcs; ( 338 Pcs 11/26) | Inhoused. | ok | [7 empty] | 56.5 | 10.2978 | 26.32 | 131588.5 | 23983.5762 | 61299.28
18 | SS25 | NAPAPIJRI | 2024-06-21 | AMIS SUM V | PASS | Given | ok | OK | 2367 | SF-11 |  | 2367 | 0 | Ok | Print | Done. |  | 2024-10-01 | 2024-11-12 |  | Size set running- All Materils Inhoused. | [7 empty] | 44 | 7.4278 | 19.97 | 104148 | 17581.6026 | 47268.99
19 | SS25 | NAPAPIJRI | 2024-07-25 | A-SECRET W | PASS | Given | ok | OK | 1051 | DPQSL QUILTING |  | 1051 | 0 | Ok | DPQSL. Quilting |  | HUAJIN-HK (TU) | 2024-11-05 | 2024-12-24 |  | Plan size set plan date. 11/03. Material sin housed. | Mill updated No GR. | All Costing |  | 3484 | MCQ 1000 Yds/ MOQ 3000 Yds. Fabric code# 1973250N REACTIVE MICRO CORDUROY(unit price USD4.35/Y X 2 = USD 8.7/y 100%upcharge and TEST CHARGE USD350 /COLOR |  |  | 50.5 | 24.064 | 42.39 | 53075.5 | 25291.264 | 44551.89
20 | SS25 | NAPAPIJRI | 2024-06-21 | ASEL | PASS | Given | ok | OK | 4665 | SF-01 | 2024-11-01 | 4665 | 0 | Ok | Print | Done. |  | 2024-10-05 | 2024-11-12 |  | Size set running- All Materils Inhoused. | [7 empty] | 40.5 | 7.8704 | 23 | 188932.5 | 36715.416 | 107295
21 | SS25 | NAPAPIJRI | 2024-07-25 | A-TUNDRA | PASS | Given | ok | OK | 4071 | LY-10- Inout Plan 15th OCT.( Connecting uncertain for typhoon ) | 2024-10-24 | 4071 | 0 | Ok | NA | Done. | Red House - TW( WE) & Wu luen ( Lining) TW(WE) | 2024-10-05 | 11/5/2024( Size set) Bulk 11/19 | Inhoused. | PPS Req given 10/07. Size set will be 10/14. Jefswin Zippe bath 10/27- 36Ctn | Lining Wthout GR- LT 50 Days | 4.costing on 20th Feb |  | 0 | No Materials UC |  |  | 70 | 8.1341 | 25.0366 | 284970 | 33113.9211 | 101923.9986
22 | SS25 | NAPAPIJRI | 2024-08-23 | A-TUNDRA | PASS | C/O | ok | OK | 2839 | LY-10- Inout Plan 15th OCT.( Connecting) |  | 2839 | 0 | OK |  | Done. |  | 2024-11-05 | 2024-12-10 |  | Lining ETA. 10/24. 25 roll/ 54 Roll. Shell. ETA 10/27- Roll: 128 | [7 empty] | 70 | 7.5684 | 24.87 | 198730 | 21486.6876 | 70605.93
23 | SS25 | NAPAPIJRI | 2024-07-11 | AVERGREEN SUM RE | PASS | Given | ok | OK | 6000 | LS-11 | 2024-10-27 | 6000 | 0 | OK |  | Done. | Red House - HK (TU)& Wu luen ( Lining) TW(TH) | 2024-10-15 | 2024-11-19 |  |  | TP shared 7/17. Server issue late downlod by 9/25. |  |  | 460 | ALL INSIDE BINDING-TPX223-QLF02 |  |  | 56 | 15.6394 | 28.01 | 336000 | 93836.4 | 168060
24 | SS25 | NAPAPIJRI | 2024-08-23 | K A-ALLORI | PASS | Given | ok | OK | 2168 | SF-3 | 2024-11-21 | 2168 | 0 | OK |  | 2024-10-28 |  | 2024-11-05 | 2024-12-10 |  | Lining ETA. 10/24. 25 roll/ 54 Roll. Shel; Jibo- 168 Roll, Inhoused. Size set file; 10/31 | [7 empty] | 41 | 5.0874 | 15.9 | 88888 | 11029.4832 | 34471.2
25 | SS25 | NAPAPIJRI | 2024-07-25 | K A-AMIATA | PASS | Given | ok | OK | 1011 | LS-7 |  | 1011 | 0 | OK | Print | Done. | shin han-KR(FR) | 2024-10-05 | 2024-11-26 | NOT YET | PPS Running, Size set- plan to send 10/15. All Materils Inhoused. | TTL LT with GR 125 Days and without GR 170 Days | Relocation-3 |  | 300 | 1972460N: MOQ / MCQ: 3000/ 1000 Yds |  |  | 55 | 11.474 | 26.5632 | 55605 | 11600.214 | 26855.3952
26 | SS25 | NAPAPIJRI | 2024-07-25 | K A-MONTALE | PASS | Given | ok | OK | 1500 | RS-8 | 2024-11-04 | 1500 | 0 | OK | NA | PLAN/.10/26- | Monotex KR(FR) | 2024-10-12 | 11/12/2024( Photo shoot) Bulk 11/19. |  | PPS ready for review- Size set given. 10/27. |  | Relocation-3 |  | 0 | NO Materials UC |  |  | 44 | 11.525 | 27.0483 | 66000 | 17287.5 | 40572.45
27 | SS25 | NAPAPIJRI | 2024-08-23 | K RAINFOREST SUM 4 | PASS | C/O | ok | OK | 499 | RS-8 |  | 499 | 0 | Ok |  | Done. |  | 2024-11-05 | 2024-12-03 |  | Lining ETA. 10/24. 25 roll/ 54 Roll. Shell; Jibo- 168 Roll, Inhoused. Read House. ETA. 10/27- Roll. 74 Roll. | [7 empty] | 61 | 5.7831 | 17.89 | 30439 | 2885.7669 | 8927.11
28 | SS25 | NAPAPIJRI | 2024-07-25 | K RAINFOREST SUM 4 | PASS | Given | ok | OK | 2507 | LS-5 | 2024-11-06 | 2507 | 0 | Ok | NA | Done. | Red House - TW( WE) & Jibo - CN( MON/TH)Wu luen ( Lining) TW(WE) | 2024-10-05 | 2024-12-03 |  | CRD Uncertain. Zipper Issue. Need to follow up next Buy. |  | 4.costing on 20th Feb |  | 0 | No Materials UC |  |  | 61 | 6.6873 | 17.89 | 152927 | 16765.0611 | 44850.23
29 | SS25 | NAPAPIJRI | 2024-06-21 | MATEY 2-NP0A4IPT | PASS | Given | ok | OK | 10300 | LY-1 | 2024-09-28 | 10300 | 0 | Ok | Print S/Off Submited 8/28, Approval Pending. Pass. | Done. |  | 2024-09-01 | 2024-10-08 | Inhoused. | 1. Leg Opening- 27 MM Elistic not yet Inhoused- will be 7th Sep. From S.EMB. Inhoused. | [7 empty] | 35 | 6.9407 | 16.12 | 360500 | 71489.21 | 166036
30 | SS25 | NAPAPIJRI | 2024-07-04 | M-MASSI CHINO | PASS | Given | ok | OK | 615 | SF-6 | 2024-10-24 | 615 | 0 | OK | Garments Dye: Black color Stabio received parcel by 19th Aug. Need to get VF approval- Approved- Phycial Apprval by Weahid . Approved. | Done. |  | 2024-10-01 | 2024-11-05 | NOT YET | Size set running- All Materils Inhoused. | [7 empty] | 28.5 | 16.7906 | 49.5 | 17527.5 | 10326.219 | 30442.5
31 | SS25 | NAPAPIJRI | 2024-07-04 | M-SENIO CARGO | PASS | Given | ok | OK | 1187 | SF-06 | 2024-10-20 | 1187 | 0 | Ok | Garments Day | Done. |  | 2024-09-22 | 2024-10-22 | NOT YET | PPM Done. Need to sedn a original Poly to supplier Unuglory- | With GR- Air Collect Fabric from Italy | [6 empty] | 41 | 8.9085 | 39.5 | 48667 | 10574.3895 | 46886.5
32 | SS25 | NAPAPIJRI | 2024-07-04 | M-TUSCO | PASS | Given | ok | OK | 299 | BR:2 |  | 299 | 0 | ok | Print | Done. |  | 2024-10-15 | 2024-11-19 |  | PPS comments pending, Size Set file 10/13; No Materials Issue. | [7 empty] | 65 | 19.7672 | 41.11 | 19435 | 5910.3928 | 12291.89
33 | SS25 | NAPAPIJRI | 2024-06-21 | NATEY SHORT 1 | PASS | Given | ok | OK | 6330 | LY-1 | 2024-10-17 | 6330 | 0 | OK | Print- Approved- as per TP Comment. | Done. |  | 2024-09-22 | 2024-11-19 | Inhoused. | No Issue. | [7 empty] | 30 | 5.0845 | 13.25 | 189900 | 32184.885 | 83872.5
34 | SS25 | NAPAPIJRI | 2024-07-25 | N-BALDI | PASS | Given | ok | OK | 531 | BR-2 |  | 531 | 0 | Ok |  | 2024-10-27 | SEOJIN -KR (FR) | 11/5/2024- Need to revse TNA 11/25 | 2024-12-24 |  | ETD Uncertian- Shell Fabric delay - qulaity issue. |  | All Costing |  | 1670 | MAIN FABRIC: 1972600N COTTON NYLON : MOQ/MCQ: 3000 /1000 Yds. |  |  | 30 | 12.337 | 38.65 | 15930 | 6550.947 | 20523.15
35 | SS25 | NAPAPIJRI | 2024-07-04 | N-SENIO | PASS | Given | ok | OK | 1777 | SF-6 | 2024-10-13 | 1777 | 0 | Ok | Garments Dye: Black color Stabio received parcel by 19th Aug. Need to get VF approval- Approved- Phycial Apprval by Weahid . Approved. | Done. |  | 2024-10-01 | 2024-11-05 | Inhoused. | Size set running- All Materils Inhoused. | [7 empty] | 40 | 7.312 | 32 | 71080 | 12993.424 | 56864
36 | SS25 | NAPAPIJRI | 2024-08-23 | RAINFOREST M SUM 3 | PASS | DUE. Plan 11/05 | ok | OK | 2004 | LY-14 | 2024-11-21 | 2004 | 0 | Ok | NA | Plan 11/05 |  | 2024-11-15 | 2024-12-17 | [9 empty] | 67 | 8.0014 | 23.7 | 134268 | 16034.8056 | 47494.8
37 | SS25 | NAPAPIJRI | 2024-07-25 | RAINFOREST NEXT SUM | PASS | Given | ok | OK | 4675 | LY-4 | 2024-10-29 | 4675 | 0 | OK | NA | Done. | Jibo- CN(MON/TH) & Wu luen ( Lining) TW(WE) | 2024-10-12 | 2024-11-19 |  | PPS Req. Given 10/9, Size set need to Handover 10/15. | TTL LT with GR 120 Days and without GR 140 Days | Relocation-3 |  | 0 | No Materials UC |  |  | 81.5 | 9.7913 | 35.5 | 381012.5 | 45774.3275 | 165962.5
38 | SS25 | NAPAPIJRI | 2024-07-25 | RAINFOREST OPEN S | PASS | Given | ok | OK | 1008 | LS-5 | 2024-10-22 | 1008 | 0 | Ok | NA | Done. | Red House - TW( WE) & Jibo - CN( MON/TH)Wu luen ( Lining) TW(WE) | 2024-10-05 | 2024-11-05 | Inhoused. |  |  | Relocation-3 |  | 0 |  |  |  | 68 | 7.5467 | 23.38 | 68544 | 7607.0736 | 23567.04
39 | SS25 | NAPAPIJRI | 2024-07-25 | RAINFOREST S W PKT 3 | PASS | PASS | ok | OK | 3416 | LS- 05 | 2024-10-24 | 3416 | 0 | Ok | NA | 2024-10-27 | Red House - TW( WE) & Jibo - CN( MON/TH)Wu luen ( Lining) TW(WE) | 2024-10-05 | 2024-12-03 | Inhoused. |  |  | 4.costing on 20th Feb |  | 0 | No Materials UC |  |  | 74 | 8.7071 | 23.47 | 252784 | 29743.4536 | 80173.52
40 | SS25 | NAPAPIJRI | 2024-07-25 | RAINFOREST WB PKT V2 | PASS | Given | ok | OK | 4867 | LY- 12 | 2024-10-17 | 4867 | 0 | Ok | NA | Done. | JIbo- CN(MON/TH) & Wu luen ( Lining) TW(WE) | 2024-10-05 | 2024-11-05 | Inhoused. | The PPS Will be ready for review today. All Materils Ok 2054 Pcs 1Wk CRD 12 Nov Extention Req.-Approved. Pick up 10/28- 5 Th Inhoused. | 5 Days CRD Extention Proposal 11/26 from LT | Relocation-3 |  | 600 | 1952240N REC LINING 210T. Lining MOQ/MCQ: 3000/1000 Yds. |  |  | 65 | 6.2959 | 27.9396 | 316355 | 30642.1453 | 135982.0332
41 | SS25 | NAPAPIJRI | 2024-08-23 | RAINFOREST WB PKT V2 | PASS | C/O | ok | OK | 1560 | LY-2 |  | 1560 | 0 | Ok |  | Done. |  | 2024-11-05 | 2024-12-17 |  | Shell- OK + Lining: ETA. 10/24. 54 Roll/ @7. Jefswin Zipper being delay 12 dyas. ETD: 10/14-T.InH. 11/10.- pls keep line plan as per TNA> | [7 empty] | 65 | 6.3136 | 27.8 | 101400 | 9849.216 | 43368
42 | SS25 | NAPAPIJRI | 2024-07-31 | VERONA 2 | PASS | DUE- plan 11/ 10 | DUE | OK | 2955 | RS-9 |  | 2955 | 0 | Ok |  | 2024-11-14 | Red House - TW( WE) & Wu luen ( Lining) TW(WE) | 2024-11-24 | 2024-12-24 | [5 empty] | 0 | No Materials UC |  |  | 14.5 | 2.4781 | 7 | 42847.5 | 7322.7855 | 20685
43 | SS25 | NAPAPIJRI | 2024-09-26 | VERONA 2 | PASS | Given | DUE | OK | 4217 | RS-9 |  | 4217 | 0 | Ok |  | CO |  | 2024-12-25 | 2025-01-28 |  | As per Lead time Ex- Mill 17 Nov, need to improve Ex.mill 10th Nov to inhoused 10 Dec(by Sea)- connecting with July Buy (24th Nov. TNA for 24th Dec CRD) or should late start sew for Jul Buy TNA from 7 th Dec to catch Sep Buy. | [7 empty] | 14.5 | 2.2469 | 7 | 61146.5 | 9475.1773 | 29519
44 | SS25 | NAPAPIJRI | 2024-08-23 | V-IAATO | PASS | DUE. Plan 11/05 | DUE | OK | 3886 | RS-08 |  | 3886 | 0 | Ok |  | 2024-11-15 |  | 2024-11-15 | 2024-12-17 |  | Lining- 10/24/. Shell: ETD. 10/27 Red hous. | [7 empty] | 16.5 | 2.1413 | 7.31 | 64119 | 8321.0918 | 28406.66
[9 empty] | 111230 |  |  | 107344 | 0 | [18 empty] | 5404882.5 | 900284.373 | 2560176.5879 | 0.16657
[34 empty] | 2.5602 | M
| NAPA S25 | BULK SUMMARY: 12/29 | [22 empty] | Jibo | 2040
| Total TNA | 44 |  | RUNNING: 0 | [20 empty] | Red House | 2070
| Total PO Qty. | 111230 | [22 empty] | Wu Luen | 2000
| Total Production | 107344 | TNA Closed: | 44 | [12 empty] | 2024-06-13 | [7 empty] | SEOJIN | 1670
| Total Shipment | 101532 | TNA Balance | 0 | [12 empty] | 2024-07-28 | [7 empty] | HUAJIN | 3484
| Ready to ship | 5812 | [22 empty] | Shin han | 1550
| Production Balance | 3886
[13 empty] | FOB | 9.85
[13 empty] | Payemnt Term | 70% Advance TT and after BL Submit. Need Pyament within 7 Days.
[13 empty] | Delivery | Partial Ship from 1st May to End Of May. 3 Time
[13 empty] | Shell + Lining Fabric. | As per Original Sample.( Estimated Fabric composition : 100% Nylon downrpoof plain PU clear coated, PFC Free DWRM1NQ)
[13 empty] | Trims | Original as per Sample
[13 empty] | Special requiremrnt | GSP Certificat. No any more requiremnt.
[13 empty] | Facroty Condition | Any whewre of Bangladesh
After Vessel Depart, ETD to ETA 12/13Days+4/5Days ETA to Berthing + 2days for Container Discharge+5/7days (Minimum) for unstuffing & take Delivery.
Formulas:
Early Input Plan Start = [Buy Date]+175
E.Final TNA = [Vendor Last Revised CRD]-35
Long LT Mill:/ Cut Off = [Long LT Mill:/ Cut Off, row above]+45
Note on J11: Author: Blu marine color drop 901 pcs. 10/24
Note on E25: Author: Need to creat an issue for add Air collect materils UC- $ 0.80 Unit
Note on E43: Author: 254 Pcs(Requested to Reduce on 9/3)

## BIG BILL CANADA (hidden)
SL | Brand | Style | Description | Fabrication | SMS Qty | Bulk Qty. | CRD | SMV | FOB | SMS Delivery | PS. Status. | Plan Close | Wating for SMS Feedback
1 | BIG BILL CANADA /Fashion Pride | LH-100 | Men's Athletic Work Pant |  | 48 | 15200 | 2025-09-25 | 32 | 11.45 | 2025-03-29 | Running | 2025-03-28
2 | BIG BILL CANADA /Fashion Pride | LH-100W | WOMEN'S ATHLETIC WORK PANTS |  | 34 | 10000 | 2025-09-25 | 32 | 11.45 | 2025-03-29 | Running | 2025-03-28
3 | BIG BILL CANADA /Fashion Pride | LHU-S1100ARD | MEN'S COVERALL | TWILL 65/35 7,5oz |  | 8000 | TBA | 95

## NAPA RED HOUSE Challange (hidden)
Short Description | Vendor Last Revised CRD | Order Qty. | Partial Sew. Plan TNA 3/12 | Fabric Delivery Before CNY/ Yds. | Balance Qty. | Air Suport Request Qty. to keep connceting Sewing slot. | CRD Extention Proposal by Ex- Mill 2/28 by Sea. | CRD Remarks
ASHERMAN BEIGE ROCKY | 2025-05-06 | 216 |  |  | 216 |  |  | On- Time
ASHERMAN BLACK 041 | 2025-05-06 | 788 |  |  | 788 |  |  | On- Time
ASHERMAN BLU MARINE | 2025-05-06 | 395 |  |  | 395 |  |  | On- Time
ASHERMAN GREEN URBAN | 2025-05-06 | 210 |  |  | 210 |  |  | On- Time
ASHERMAN GREEN DEPTHS | 2025-05-06 | 258 |  |  | 258 |  |  | On- Time
ASHERMAN BEIGE ROCKY | 2025-07-08 | 210 |  |  | 210 |  |  | On- Time
ASHERMAN BLACK 041 | 2025-07-08 | 782 |  |  | 782 |  |  | On- Time
ASHERMAN BLU MARINE | 2025-07-08 | 389 |  |  | 389 |  |  | On- Time
ASHERMAN GREEN URBAN | 2025-07-08 | 210 |  |  | 210 |  |  | On- Time
ASHERMAN GREEN DEPTHS | 2025-07-08 | 258 |  |  | 258 |  |  | On- Time
ASHERMAN GREEN URBAN | 2025-04-15 | 1871 | 593 | 985 | 1278 | 2146 | 2025-04-29 | CRD can Improved On- Time or 1Wk Extention if mill Air Suport
ASHERMAN BLU MARINE | 2025-04-15 | 2410 | 2766 | 4591 | 0 |  | 2025-04-15 | On- Time
ASHERMAN BLACK 041 | 2025-04-15 | 3066 | 874 | 1451 | 2192 |  | 2025-04-29 | Delay 2 Wks
ASHERMAN BEIGE ROCKY | 2025-04-15 | 1837 | 613 | 1018 | 1224 |  | 2025-04-29 | Delay 2 Wks
ASHERMAN GREEN DEPTHS | 2025-04-15 | 1945 | 413 | 685 | 1532 | 2574 | 2025-04-29 | CRD can Improved On- Time or 1Wk Extention if mill Air Suport
| Total | 14845 | 5320 |  | 9942 | 4,721 Yds,

## WAIHING CHALLANGES (hidden)
WAI HING RIB Challenges Style in F25
SKU Number | Colorway Name | Final Buy Date | Revised CRD with Sufficient Leadtime | NTB Forecast Qty
TB0A6VUE317 | GREEN GABLES | 2025-01-24 | 2025-06-17 | 1479
TB0A6VUE001 | BLACK | 2025-01-24 | 2025-06-17 | 663
TB0A6VUEP47 | WHEAT BOOT | 2025-02-21 | 2025-07-15 | 1518
3660
TB0A62CF317 | GREEN GABLES | 2025-01-24 | 2025-06-13 | 700
TB0A62CF433 | DARK SAPPHIRE | 2025-01-24 | 2025-06-13 | 1292
TB0A62CFBK0 | CHOCOLATE CHIP | 2025-01-24 | 2025-06-13 | 600
2592
TB0A62CFBK0 | CHOCOLATE CHIP | 2025-02-21 | 2025-06-24 | 600
TB0A62CF433 | DARK SAPPHIRE | 2025-02-21 | 2025-06-24 | 621
TB0A62CF317 | GREEN GABLES | 2025-02-21 | 2025-06-24 | 996
TB0A62CF001 | BLACK | 2025-02-21 | 2025-06-24 | 36
2253
TB0A62CF001 | BLACK | 2025-03-21 | 2025-07-22 | 115
115
Total same Style |  |  |  | 8620
TB0A6927P47 | WHEAT BOOT | 2025-01-24 | 2025-07-12 | 1013
TB0A6927243 | CHOCOLATE BROWN | 2025-01-24 | 2025-07-12 | 1216
Same Quality Rib others style. |  |  |  | 2229
Total Qty. | Not Sure can adjust color and size wise with Nov buy Qty. |  |  | 10849
Season | Buyer | Buy Date | Style | O/Qty | E.TNA | Style 1st CRD | Remarks
F25 | TIMBELAND | 2024-11-22 | TB0A62CF | 13113 | 2025-02-25 | 2025-04-08 | Option 1- we can secure on Time CRD with our own source Rib without any liability. Option 2-If mill handover rib after CNY it will be inhouse on 15 Mar 2025, Then revised CRD will be 25th April 2025, without OTP Impact. Option 3-Mill need to deliver Rib by air PP for on time CRD. Approx Air cost
F25 | TIMBELAND | 2024-11-22 | TB0A6VUE | 5660 | 2025-03-05 | 2025-04-15
F25 | TIMBELAND | 2024-12-20 | TB0A5M9T | 3835 | 2025-05-15 | 2025-06-22 | we would like to go with own source RIB
F25 | TIMBELAND | 2024-12-20 | TB0A22W2 | 3838 | 2025-05-08 | 2025-06-17 | we would like to go with own source RIB
TIMBELAND | 2025-01-23 | TB0A62CF | D. BUY CO | 2592
TIMBELAND | 2025-01-23 | TB0A6VUE | Buy CO | 2117
Note on C2: Author: If Revised Buy Date is blank then take Original Buy Date. Else take Original Buy Date
Note on D2: • Buy date + LT1 + Shutdown(mills) if CRD for affected COO for relevant holiday is within blackout period, formula will adjust to date AFTER blackout period